## Slide 1
Periodic Revision Request Implementation Review – Q4 2012
December 13, 2012

## Slide 2: PPL Prioritization Discussion
On a periodic basis, PRS conducts a review of upcoming revision request project efforts in order to get stakeholder input on the priority of items in the project queue
Today’s discussion will center on the timing of 14 upcoming efforts
  14 NPRRs, SCRs and NOGRRs that are Board-approved with PPL projects that have not yet started and are planned to start between 1/2013 and 4/2013

## Slide 3: 2013 Revision Request Funding Reconciliation
2013 Target Funding for Revision Requests = $3.0M
Board Approved – In Flight (10) = ($1.3M)
  NPRRs: 260, 272, 313, 327, 393, 416, 456, 463
  SCRs: 760, 770
Board Approved – Not Yet Started (19) = ($1.9M)
  NPRRs: 153, 207, 240, 256, 385, 407, 419, 425, 439, 457, 461, 467, 476, 479, 481
  NOGRRs: 084, 093
  SCRs: 769, 771
In Stakeholder Process (10) = ($1.6M)
  NPRRs: 210, 340, 484, 487, 492, 493, 494, 495
  NOGRRs: 101
  SCRs: 756
“Remaining” 2013 Revision Request Funding = ($1.8M)
Summary: Close oversight of 2013 project initiations will be needed.
ERCOT will strive to work on the most important projects by confirming priorities with PRS.

## Slide 4: Revision Requests “Not Started” – Scheduled to Start by 4/2013
Revision Request | Start Date | Cost
NPRR256 – Sync PRR787, Add Non-Compliance Lang. to QSE Perf. Standards | Jan 2013 | $100k-$250k
NPRR425 – Creation of a WGR Group for GREDP and Base Point Deviation… | Jan 2013 | $250k-$350k
NPRR461 – Energy Storage Settlement Consistent with PUCT Project 39917 | Jan 2013 | $200k-$300k
NOGRR093 – Synchronization with NPRR365 | Jan 2013 | $20k-$25k
NOGRR084 – Daily Grid Operations Summary Report | Feb 2013 | $300k-$500k
NPRR153 – Generation Resource Fixed Quantity Block Offer | Mar 2013 | $12k-$16k
NPRR407 – Credit Monitoring Posting Requirements – CRR Portion | Mar 2013 | $90k-$110k
SCR769 – CRRAH Digital Certificate New Role for Read Only Access | Mar 2013 | $100k-$110k
SCR771 – Allow Independent Master QSE to Represent Split Gen. Resources | Mar 2013 | $95k-$110k
NPRR207 – Unit Deselection | Apr 2013 | $45k-$55k
NPRR439 – Updating a Counter-Party's Avail. Credit Limit for Current Day DAM | Apr 2013 | $120k-$130k
NPRR476 – Market Submitted Energy Offer Curves | Apr 2013 | $45k-$60k
NPRR479 – Daily Net Outage MW Report | Apr 2013 | $50k-$60k
NPRR481 – Report Hourly Actual System Load | Apr 2013 | $25k-$35k