|  |  |  |  | System Planning |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Monthly Status Report November 2012 |  |  |
|  |  | Report Highlights |  |  |  |  |  |  |
|  | - ERCOT is currently tracking 152 active generation interconnection requests totaling over 43,000 MW. This includes over 20,000 MW of wind generation. |  |  |  |  |  |  |  |
|  | - ERCOT is currently reviewing proposed transmission improvements with a total cost of $228.9 Million - Transmission Projects endorsed in 2012 total $596.8 Million - All projects (in engineering, routing, licensing and construction) total approximately $9.68 Billion. - Transmission Projects energized in 2012 total about $732.2 million. |  |  |  |  |  |  |  |

Table of Contents

1.	Generation Interconnection	1

1.1	Signed Generation Interconnection Agreements	1

1.2	New Generation Registering for Commercial Operations - none	1

1.3	Summary of Generation Interconnection Requests	1

1.4	Projects with Interconnection Agreements	4

1.5	Generation Projects Undergoing Full Interconnection Studies with Confidentiality Waived by Developer	4

1.6	Generation Projects Undergoing Full Interconnection Studies	5

1.7	Wind Generation Capacity Installed by Year  	6

2.	Regional Planning Group Project Reviews	7

3.	Congestion Costs	8

4.	Wind Generation as a Percent of Load	11

5.	Planning Model Activities	12

6.	Other Notable Activities	13

# 1.	Generation Interconnection

Additional information regarding detailed generation interconnection and impact studies is contained in the “Generation Project Interconnection Information” folder in the “Operations and System Planning” area on the ERCOT website:  http://planning.ercot.com/login/login.

## Signed Generation Interconnection Agreements

13INR0005 – Conway Windfarm  – 600 MW of Wind in Carson County

## New Generation Registering for Commercial Operations - none

The total installed wind capacity is now reported as 10,035 MW by the resource owners through the registration process. Capacity by North, South and West is 519 MW,  2,283 MW, and 7,233 MW respectively. 850 MW is able to switch between the West and South zones and is currently shown in the South zone.

## Summary of Generation Interconnection Requests

| GENERATION INTERCONNECTION REQUESTS CURRENTLY UNDER REVIEW |  |  |  |  |
| --- | --- | --- | --- | --- |
| Currently tracking 162 generation interconnection or change requests |  |  |  |  |
| As of November 28, 2012 |  |  |  | Total |
| Security Screening Study | 17 |  |  |  |
| SSS Completed | 15 |  |  |  |
| Full Interconnect Study | 81 |  |  |  |
| FIS Completed | 12 |  |  |  |
| Suspended Studies | 10 |  |  |  |
| Capacity of Suspended Study Projects | 7,512 |  |  |  |
| Interconnect Agreement Completed | 27 |  |  |  |
| Capacity under Interconnection Agreements | 11,345 |  |  |  |
| Capacity for Grid, MW | 43,650 |  |  |  |
| Wind Capacity, MW | 20,056 |  |  |  |

| Fuel Type | Confidential Projects (MW) | Projects Under Full Study (MW) | Public Projects (MW) | Suspended Studies (MW) | Grand Total (MW) |
| --- | --- | --- | --- | --- | --- |
| Gas-AllOther |  |  |  |  | 5,940 |
| Gas-CombinedCycle |  |  | 5,686 |  | 12,863 |
| Total Gas | 9,035 | 4,082 | 5,686 |  | 18,803 |
| Nuclear |  |  |  | 3,200 | 3,200 |
| Coal |  | 850 | 1,165 |  | 2,015 |
| Wind | 2,577 | 14,400 | 3,078 | 4,273 | 24,329 |
| Solar | 664 | 657 | 60 | 38 | 1,419 |
| Biomass |  |  |  |  |  |
| Storage |  | 40 | 36 |  | 76 |
| Petroleum Coke |  |  | 1,320 |  | 1,320 |
| Grand Total | 12,276 | 20,029 | 11,346 | 7,512 | 51,162 |

County Location of Installed Generation and Interconnection Requests (all fuels)

## Projects with Interconnection Agreements

| Generation Interconnections as of November 28, 2012 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| INR | Site Name | County | COD | Fuel | MW For Grid | Change from Last Report |
| 12INR0076 | Notrees Battery Storage | Winkler | Nov-12 | Storage | 36 | Date |
| 12INR0075 | Blue Summit Windfarm | Wilbarger | Nov-12 | Wind | 135 |  |
| 08INR0011 | Senate Wind Project | Jack | Dec-12 | Wind | 150 |  |
| 11INR0091 | Whitetail Wind Energy Project | Webb | Dec-12 | Wind | 92 |  |
| 12INR0072 | Anacacho Windfarm | Kinney | Dec-12 | Wind | 100 |  |
| 09INR0061 | WKN Mozart | Kent | Dec-12 | Wind | 30 |  |
| 11INR0033 | Los Vientos | Cameron | Dec-12 | Wind | 400 |  |
| 08INR0049 | Bobcat Bluff (Briar Creek) | Clay | Dec-12 | Wind | 163 |  |
| 09INR0001 | Sandy Creek 1 | McLennan | Apr-13 | Coal | 925 |  |
| 11INR0086 | RRE Austin Solar | Travis | Oct-13 | Solar | 60 |  |
| 06INR0022c | Penascal Wind Farm 3 | Kenedy | Dec-13 | Wind | 202 |  |
| 11INR0013 | Goldthwaite Wind Energy | Mills | Dec-13 | Wind | 150 |  |
| 11INR0054 | Midway Farms Wind | San Patricio | Dec-13 | Wind | 161 |  |
| 12INR0034 | Stephens-Borlynn Wind Project | Borden | Dec-13 | Wind | 378 |  |
| 13INR0021 | Ferguson Replacement Project | Llano | Jul-14 | Gas-CC | 116 |  |
| 10INR0021 | Panda Sherman Power | Grayson | Aug-14 | Gas-CC | 809 |  |
| 10INR0020a | Panda Temple Power | Bell | Aug-14 | Gas-CC | 809 |  |
| 11INR0050 | Moore Wind 1 | Crosby | Aug-14 | Wind | 149 |  |
| 10INR0023 | Baker Ranch | Haskell | Sep-14 | Wind | 400 |  |
| 13INR0005 | Conway Windfarm | Carson | Dec-14 | Wind | 600 | new |
| 09INR0051 | Mesquite Creek | Borden | Mar-15 | Wind | 249 |  |
| 06INR0006 | Cobisa-Greenville | Hunt | May-16 | Gas-CC | 1,792 | Date |
| 08INR0018 | Gunsight Mountain | Howard | Aug-15 | Wind | 120 |  |
| 13INR0023 | Texas Clean Energy Project | Ector | Jan-16 | Coal | 240 |  |
| 10INR0020b | Panda Temple Power | Bell | May-16 | Gas-CC | 780 |  |
| 10INR0022 | Pondera King Power Project | Harris | Jun-16 | Gas-CC | 1,380 |  |
| 12INR0016a | Las Brisas Energy Center | Nueces | May-18 | PetCoke | 660 |  |
| 12INR0016b | Las Brisas Energy Center | Nueces | May-18 | PetCoke | 660 |  |

## Generation Projects Undergoing Full Interconnection Studies with Confidentiality Waived by Developer

None

## Generation Projects Undergoing Full Interconnection Studies

| INR | County | Grid | COD | Fuel |  | INR | County | Grid | COD | Fuel |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 13INR0040 | Harris | 0 | Jan-13 | Gas |  | 13INR0010a | Parmer | 200 | Jan-13 | Wind |
| 13INR0010d | Parmer | 200 | Jan-13 | Wind |  | 13INR0010e | Parmer | 200 | Jan-13 | Wind |
| 13INR0010f | Parmer | 200 | Jan-13 | Wind |  | 13INR0045 | Castro | 288 | Apr-13 | Wind |
| 11INR0094 | Kent | 100 | Apr-13 | Solar |  | 13INR0020a | Glasscock | 200 | May-13 | Wind |
| 13INR0058 | Bexar | 50 | May-13 | Solar |  | 10INR0089 | Harris | 40 | May-13 | Storage |
| 12INR0086 | Fort Bend | 89 | May-13 | Gas |  | 12INR0045 | Kleberg | 135 | Jun-13 | Wind |
| 13INR0057 | Archer | 65 | Jun-13 | Wind |  | 13INR0049 | Harris | 352 | Jul-13 | Gas |
| 13INR0025 | Randall | 150 | Sep-13 | Wind |  | 13INR0046 | Limestone | 71 | Sep-13 | Wind |
| 13INR0059 | Castro | 499 | Oct-13 | Wind |  | 13INR0028 | Hale | 392 | Nov-13 | Gas |
| 14INR0030a1 | Carson | 322 | Nov-13 | Wind |  | 14INR0030a2 | Carson | 322 | Nov-13 | Wind |
| 12INR0002a | Briscoe | 200 | Dec-13 | Wind |  | 11INR0062 | Nueces | 178 | Dec-13 | Wind |
| 11INR0085 | Nolan | 106 | Dec-13 | Wind |  | 13INR0026 | Oldham | 201 | Dec-13 | Wind |
| 12INR0054 | Jones | 200 | Dec-13 | Wind |  | 12INR0059 | Pecos | 50 | Dec-13 | Solar |
| 13INR0007 | Pecos | 200 | Dec-13 | Wind |  | 13INR0036 | Hidalgo | 200 | Dec-13 | Wind |
| 13INR0038 | Swisher | 300 | Dec-13 | Wind |  | 13INR0050 | Comanche | 200 | Dec-13 | Wind |
| 13INR0052 | Starr | 200 | Dec-13 | Wind |  | 13INR0055 | Zapata | 250 | Dec-13 | Wind |
| 13INR0056 | Scurry | 366 | Dec-13 | Wind |  | 12INR0079 | Kenedy | 200 | Dec-13 | Wind |
| 11INR0057 | Cameron | 165 | Dec-13 | Wind |  | 11INR0093 | San Patricio | 41 | Dec-13 | Wind |
| 12INR0068 | Jim Hogg | 80 | Dec-13 | Wind |  | 13INR0048 | Oldham | 161 | Dec-13 | Wind |
| 12INR0088 | Crosby | 201 | Dec-13 | Wind |  | 14INR0024 | Kinney | 42 | Dec-13 | Solar |
| 13INR0006 | Gray | 750 | Jan-14 | Wind |  | 12INR0055 | Baylor | 40 | Jan-14 | Wind |
| 14INR0013 | Cameron | 103 | Jan-14 | Wind |  | 14INR0014 | Val Verde | 100 | Jan-14 | Solar |
| 12INR0084 | Randall | 242 | Jan-14 | Wind |  | 13INR0010b | Parmer | 200 | Jan-14 | Wind |
| 12INR0060 | Schleicher | 58 | Apr-14 | Wind |  | 13INR0020b | Glasscock | 150 | May-14 | Wind |
| 14INR0027 | Guadalupe | 471 | May-14 | Gas |  | 08INR0019a | Gray | 250 | Jun-14 | Wind |
| 08INR0019b | Gray | 250 | Jun-14 | Wind |  | 08INR0019c | Gray | 250 | Jun-14 | Wind |
| 14INR0011 | Swisher | 270 | Jun-14 | Gas |  | 14INR0012 | Gray | 401 | Jun-14 | Wind |
| 14INR0015 | Harris | 192 | Jun-14 | Gas |  | 14INR0016 | Harris | 190 | Jun-14 | Gas |
| 14INR0031 | Harris |  | Jun-14 | Gas |  | 12INR0085 | Stonewall | 24 | Jul-14 | Wind |
| 14INR0025 | Floyd | 500 | Jul-14 | Wind |  | 12INR0042a | Deaf Smith | 265 | Sep-14 | Wind |
| 12INR0042b | Deaf Smith | 135 | Sep-14 | Wind |  | 12INR0070 | Knox | 300 | Oct-14 | Wind |
| 13INR0031 | Travis | 30 | Oct-14 | Solar |  | 09INR0034 | Coryell | 200 | Oct-14 | Wind |
| 12INR0002b | Briscoe | 200 | Dec-14 | Wind |  | 11INR0081 | Live Oak | 72 | Dec-14 | Wind |
| 11INR0082A | Val Verde | 50 | Dec-14 | Wind |  | 11INR0082B | Val Verde | 150 | Dec-14 | Wind |
| 14INR0009 | Kent | 248 | Dec-14 | Wind |  | 12INR0071 | Caldwell | 30 | Dec-14 | Wind |
| 10INR0085 | Ector | 40 | Dec-14 | Solar |  | 14INR0020 | Floyd | 150 | Dec-14 | Wind |
| 14INR0023 | Briscoe | 361 | Dec-14 | Wind |  | 13INR0054 | Bexar |  | Dec-14 | Gas |
| 11INR0079a | Clay | 200 | Dec-14 | Wind |  | 08INR0031 | Childress | 120 | Dec-14 | Wind |
| 12INR0029 | Swisher | 500 | Dec-14 | Wind |  | 15INR0021 | Starr | 200 | Dec-14 | Wind |
| 13INR0010c | Parmer | 200 | Jan-15 | Wind |  | 10INR0009 | Castro | 300 | Mar-15 | Wind |
| 12INR0057 | Ector | 40 | Apr-15 | Solar |  | 15INR0013 | Anderson | 324 | Oct-15 | Gas |
| 15INR0014 | Matagorda | 280 | Oct-15 | Gas |  | 11INR0065 | Nueces | 350 | Oct-15 | Wind |
| 12INR0002c | Briscoe | 350 | Dec-15 | Wind |  | 14INR0018 | Nolan | 35 | Dec-15 | Solar |
| 15INR0015 | Pecos | 140 | Dec-15 | Solar |  | 13INR0032 | Andrews | 30 | Dec-15 | Solar |
| 12INR0018 | Gray | 500 | Dec-15 | Wind |  | 16INR0005 | Cameron | 871 | Apr-16 | Gas |
| 16INR0003 | Brazoria | 11 | Jun-16 | Gas |  | 11INR0040 | freestone | 640 | Mar-18 | Gas |
| 14INR0003 | Nolan | 850 | Jun-19 | Coal |  |  |  |  |  |  |

Note:  Projects that are classified as “Cancelled” or “Suspended” are excluded from this table.

## Wind Generation Capacity Installed by Year

# Regional Planning Group Project Reviews

- AEPSC has submitted the Airline/North Padre Island Area Improvements project. This project is submitted as a revision to the Barney Davis to Laguna 138 kV line (AEPSC Corpus Christi Improvements Project ) that was endorsed by ERCOT in November 2009. This is a Tier 1 project that is estimated to cost approximately $58.1 million. This project is currently under ERCOT independent review.

- CPS Energy has submitted the TCC Transmission project to support load growth on the west side of San Antonio.  The project is Tier 2 project estimated to cost $10.9 million.  This project is currently under ERCOT independent review.

- Sharyland has submitted the Atlas-Driver Load Integration project, this is a Tier 2 project that is estimated to cost approximately $15.4 million. This project is currently under ERCOT independent review.

- American Electric Power Service Corporation (AEPSC) has submitted the Sinton-Beeville-Kenedy Area Improvements project to accommodate load additions due to Eagle Ford Shale development in South Texas.  This is a Tier 1 project that is estimated to cost $89.2 million. This project is currently under ERCOT independent review.

- LCRA TSC, Guadalupe Valley Electric Cooperative (GVEC), American Electric Power (AEP), and South Texas Electric Cooperative (STEC) have jointly submitted the Kenedy Switch to Nixon to Seguin Line Upgrade. This is a Tier 1 project that is estimated to cost approximately $55.3 million. This project is currently under ERCOT independent review.

# Congestion Costs

Dollars shown in RUC Make Whole payment graph are of settlement quality.

RUC net Make Whole payment in $mm

Monthly Average LMP

Binding Constraints – Year to Date

| Contingency | Binding Element | Number of 5-min intervals | Shadow Price Range $/MWh | Estimated Congestion Rent $ (Shadow Price*Limit) | Transmission Project |
| --- | --- | --- | --- | --- | --- |
| Amoco North Cowden Tap - Moss 138kV | Odessa North 138/69 kV Autotransformer | 16957 | 0 - 2800 | 134,188,994 | 5YTP [2010-R7, R8] 12TPIT0214, 13TPIT0136 |
| Quail Switch - Odessa EHV 345 kV & Longshore Switch - Odessa EHV 345 kV; Golden Switch - Sun Switch 138 kV; Falcon Seaboard - Midland East 345 kV; etc. | China Grove - Bluff Creek 138 kV | 2777 | 0 - 3500 | 63,879,472 | 13TPIT0098, 13TPIT0093 |
| BASE CASE | West to North Stability Limit | 8647 | 0 - 436 | 29,201,770 | CREZ |
| Batesville Switching Station - Paloduro Substation 138 kV; Batesville 138/69 kV Autotransformer; West Batesville - Uvalde 138 kV; etc | Moore Switching Station - Downie Switching Station 138 kV | 1971 | 0 - 3500 | 20,422,574 | 08TPIT0018 |
| Midland East - Odessa EHV 345 kV; or Moss Switch 345/138 kV Autotransformer | Odessa - Odessa North 138 kV | 609 | 0 - 3500 | 18,830,852 | 14TPIT0054 |
| Twin Buttes 345/138 kV Autotransformer | San Angelo Red Creek 345/138 kV Autotransformer 2 | 113 low-side; and 262 high-side | 19 - 3500 low-side; and 2 - 4500 high-side | 18,360,051 | 14TPIT0067 |
| Kyle - San Marcos 138 kV; or Lytton Spring - Zorn 345 kV & Austrop - Zorn 345 kV | Turnersville - Buda 138 kV | 568 | 0 - 3500 | 17,352,442 | 09TPIT0060 |
| Lewisville Switch - Carrollton Northwest 345 kV; or Lewisville Switch - Carrollton Northwest 345 kV double-circuit | Lewisville Switch - Jones Street TNP 138 kV | 4666 | 0 - 3500 | 17,099,428 | CREZ, 07TPIT0042 |
| Morgan Creek SES 345/138 kV Autotransformer 1 | Morgan Creek SES 345/138 kV Autotransformer 4 high-side | 150 | 3 - 4500 | 14,673,592 |  |
| Salado - Killeen 345 kV double-circuit | Belton - Belton Southwest 138 kV | 258 | 0 - 3500 | 14,490,150 |  |

Binding Constraints – Nov 2012

| Contingency | Binding Element | Number of 5-min intervals | Shadow Price Range $/MWh | Estimated Congestion Rent $ (Shadow Price*Limit) | Transmission Project | Comments |
| --- | --- | --- | --- | --- | --- | --- |
| Leon Switch - Cisco - Putnam 138 kV | Leon Switch - Putnam 138 kV | 1498 | 0 - 3500 | 7,213,417 |  | Maintenance outage and high wind |
| Greens Bayou - King 345 kV double-circuit | Greens Bayou 345/138 kV Autotransformer A2 low-side | 42 | 26 - 3500 | 5,069,923 | 13TPIT0102 | Maintenance at Greens Bayou |
| Ajo - Rio Hondo 345 kV | North Edinburg - Lon Hill 345 kV | 12 | 4500 - 4500 | 4,366,163 | 14TPIT0050 | Outage of Falfurrias to Rachal 138 kV line |
| Skyline - Calaveras 345 kV double-circuit | Pawnee - Spruce 345 kV | 2285 | 0 - 4500 | 3,078,583 |  | Outages of Calaveras to Braunig and Calaveras to Cagnon 345 kV lines |
| Andrews North - Holt Switch 138 kV & Andrews North - No Tree 138 kV; Golden Switch - Sun Switch 138 kV; Falcon Seaboard - Midland East 345 kV; or Falcon Seaboard - Morgan Creek SES 345 kV | China Grove - Bluff Creek 138 kV | 127 | 0 - 3500 | 1,980,625 | 13TPIT0098, 13TPIT0093 | Outage of Odessa EHV 345 kV bus and connected 345/138 kV autotransformer #1 and 345 kV lines |
| Watermill - Limestone 345 kV double-circuit | Jewett - Big Brown SES 345 kV | 60 | 0 - 4500 | 1,824,357 |  | 345 kV bus outage at Big Brown SES |
| Morgan Creek SES - China Grove 138 kV double-circuit | Morgan Creek SES 345/138 kV Autotransformer 3 low-side | 103 | 2800 - 2800 | 1,779,190 |  | Outage of Odessa EHV 345 kV bus and connected 345/138 kV autotransformer #1 and 345 kV lines |
| BASE CASE | West to North Stability Limit | 239 | 0 - 64 | 1,377,443 |  | High west wind |
| Permian Basin SES - Wink 138 kV & Permian Basin SES - Wickett 138 kV | Northward - Wink 69 kV | 138 | 0 - 2800 | 1,285,671 |  |  |
| Odessa EHV 345/138 kV Autotransformer 2 | Odessa EHV 345/138 kV Autotransformer 3 high-side | 222 | 1 - 3748 | 1,188,991 |  | Outage of Odessa EHV 345 kV bus and connected 345/138 kV autotransformer #1 and 345 kV lines |

# Wind Generation as a Percent of Load

One-hour average of total wind power output as a percentage of ERCOT load.

# Planning Model Activities

- Data Set B work began on August 1, 2012 with a Topology Processor case extracted from NMMS with a build date of January 1, 2013.  Process is underway with creation of Pass 1 cases on Aug 31, 2012.

- The short term calendar of major planning model events follows:

  - Nov 16, 2012	Posted Sept TPIT update to 12 DSA and 13 DSA cases.

  - Nov 14, 2012	Begin Contingency database update for 13 DSA and DSB cases.

  - Nov 19, 2012	Begin Transmission Loss Factor Calculations

  - Dec 12, 2012	Begin Planning Data Dictionary Update

  - Dec 19, 2012	Post Contingency database update for 13 DSA and DSB cases

  - Dec 21, 2012	Complete Transmission Loss Factor Calculations

  - Jan 11, 2013	Complete Planning Data Dictionary Update

- Status update on SCR760, Changes Needed for Information Model Manager and Topology Processor for Planning Models, which was approved by the ERCOT Board in March 2011.

  - Bundle 1 (Items 3, 7 and 8): In Production.

  - Bundle 2 (Items 2a, 4, 9):  In Production.

  - Bundle 3 (Item 5, 2b, 2c):  In Production

  - Bundle 4 (Items 1, 6):  Requirements agreed to by ERCOT and Vendor.  Vendor proposal approved by ERCOT.  SOW amendment underway.  Vendor has begun work.  Expect to receive first release in April 2013.

| SCR Sub Part | SCR Description | Status |
| --- | --- | --- |
| SCR760-1 | Upgrade to PSS/E v32 | Production |
| SCR760-2 | Distribution Capacitor banks | Production |
| SCR760-3 | Zero Impedance Line Ratings | Production |
| SCR760-4 | Associate Loads and Capacitor banks with the correct CNG | Production |
| SCR760-5 | Additional Transformer Data for Planning | Production |
| SCR760-6 | FACTS Devices | Planning |
| SCR760-7 | Assign valid PSSE IDs to Breakers/ Switches/ Series Devices | Production |
| SCR760-8 | Phase shift of Autos for short circuit studies | Production |
| SCR760-9 | Multisection Line Grouping | Production |

Table 1:  In the following table:

- Red will be used to show status of Not Submitted, meaning that the SCR sub part has not been submitted to Siemens as a Service Request.

- Yellow will indicate that the SCR sub part has been submitted.  The color will remain yellow and the status will change in order to Submitted, Planning (Requirements, SOW, Code Writing), Release (Siemens produces first code to test), and Testing (code has completed internal test and is moving through release management).

- Green will indicate that the code has been tested and installed on the machines that ERCOT uses to produce Topology Processor output for Planning and CRR.

# Other Notable Activities

- All of the reliability projects for the 2012 Five-Year Transmission Plan have been identified and the results posted at the ERCOT POI. The ERCOT 5YTP team is current working on the draft 5YTP report for reliability analysis section and concurrently working on the economic analysis.