| # ID | STEPS | WHO | TARGET NO LATER THAN DATE | STATUS |
| --- | --- | --- | --- | --- |
| STEP-001 | Receive PUCT Directional Commitment | Staff & JDOA | 2012/12/6 | COMPLETE |
| STEP-002 | Revise Storyboards based on New Business Requirements | AMIT | Early January 2013 | COMPLETE |
| STEP-003A | Revisions to Business Process Definitions, Assumptions, Touch Points, and Documentation based on Revised Storyboards | SMT | Early January 2013 | COMPLETE |
| STEP-003B | Create Descriptive Narrative of Project Requirements, Business Processes, Assumptions, Customer Protections, and Regulatory and Business Drivers (High to Mid-Level with Executive Summary) | Mary | 2013/03/31 |  |
| STEP-004 | Present Final Storyboard / Business Process with AMIT | AMIT | 2013/1/23 | IN PROCESS |
| LINE IN THE SAND DECISION |  |  |  |  |
| STEP-005 | TENTATIVE: Prepare packet for Public Comment | Staff | End of January 2013 | NOT REQUIRED |
| STEP-006 | TENTATIVE: 30 Day Public Comment Period (Pre-design) | Staff | End of February 2013 | NOT REQUIRED |
| STEP-007 | TENTATIVE: Review and Assess Public Comments for Incorporation into Design (based on PUCT direction and decision) | Staff | Mid-March 2013 | NOT REQUIRED |
| STEP-008 | Document New Design | SMT |  | IN PROCESS |
| STEP-009 | F2F End to End Design Review Workshop(s) to Get Approval on the Design | AMIT | 2013/3/5 and 2013/3/6 |  |
| LINE IN THE SAND DECISION |  |  |  |  |
| STEP-010 | Review and Finalize Content (screen content, emails, FAQs) | TBD | TBD |  |
| STEP-011 | Final Presentation Content | Staff | TBD |  |
| STEP-012 | Development, Testing, UAT | SMT | TBD |  |
| STEP-013 | Present 3rd Party Functionality Demo to Consumer Focus Groups on Usability: - Residential Customers - Non-residential customers | Usability Consultant & SMT | TBD |  |
| STEP-014 | Review and Assess Focus Group Feedback for Incorporation into Site Usability | Staff & JDOA | TBD |  |
| STEP-015 | Development, Testing, UAT of any changes identified in Focus Group | SMT | TBD |  |
| STEP-016 | Deployment Goal | SMT | With Comment Period: No Later than End of Q3 2013 Without Comment Period: No Later than End of Q2 2013 |  |