## Slide 1
Periodic Revision Request Implementation Review – Q1 2013
January 17, 2013

## Slide 2: PPL Prioritization Discussion
On a periodic basis, PRS conducts a review of upcoming revision request project efforts in order to get stakeholder input on the priority of items in the project queue
Today’s discussion will center on the timing of several upcoming efforts
  NPRRs, SCRs and NOGRRs that are Board-approved with PPL projects that have not yet started

## Slide 3: 2013 Revision Request Funding Reconciliation
2013 Target Funding for Revision Requests = $3.0M
Board Approved – Projects are Underway (17) = ($1.8M)
  NPRRs: 260, 272, 313, 322, 327, 377, 393, 397, 407, 416, 456, 461, 463, 469
  SCRs: 760, 768, 770
Board Approved – Projects Not Yet Started (17) = ($1.6M)
  NPRRs: 153, 207, 210, 256, 385, 407, 419, 425, 439, 457, 476, 479, 481
  NOGRRs: 084, 093
  SCRs: 769, 771
In Stakeholder Process (10) = ($1.7M)
  NPRRs: 340, 484, 487, 492, 493, 494, 495, 500
  NOGRRs: 101
  SCRs: 756
“Remaining” 2013 Revision Request Funding = ($2.1M)
Summary: Close oversight of 2013 project initiations will be needed.
ERCOT will strive to work on the most important projects by confirming priorities with PRS.

## Slide 4: Revision Requests “Not Started” – Scheduled to Start in 2013
Revision Request | Start Date | Cost
NPRR256 – Sync PRR787, Add Non-Compliance Lang. to QSE Performance Standards | Jan 2013 | $100k-$250k
NPRR425 – Creation of a WGR Group for GREDP and Base Point Deviation… | Jan 2013 | $250k-$350k
NOGRR093 – Synchronization with NPRR365 | Jan 2013 | $20k-$25k
NPRR385 – Negative Price Floor | Feb 2013 | $75k-$90k
NOGRR084 – Daily Grid Operations Summary Report | Feb 2013 | $300k-$500k
NPRR153 – Generation Resource Fixed Quantity Block Offer | Mar 2013 | $12k-$16k
NPRR407 – Credit Monitoring Posting Requirements – CRR Portion | Mar 2013 | $90k-$110k
SCR769 – CRRAH Digital Certificate New Role for Read Only Access | Mar 2013 | $100k-$110k
SCR771 – Allow Independent Master QSE to Represent Split Gen. Resources | Mar 2013 | $95k-$110k
NPRR207 – Unit Deselection | Apr 2013 | $45k-$55k
NPRR439 – Updating a Counter-Party's Avail. Credit Limit for Current Day DAM | Apr 2013 | $120k-$130k
NPRR476 – Market Submitted Energy Offer Curves | Apr 2013 | $45k-$60k
NPRR479 – Daily Net Outage MW Report | Apr 2013 | $40k-$50k
NPRR481 – Report Hourly Actual System Load by Weather Zone | Apr 2013 | $25k-$35k
NPRR457 – Daily Update of New ESI IDs and AMS Meter and Switch Hold Indicators Change | Jun 2013 | $40k-$60k
NPRR210 – Wind Forecasting Change to P50, Sync with PRR841 | Jul 2013 | $45k-$55k
NPRR419 – Revise Real Time Energy Imbalance and RMR Adjustment Charge | Jul 2013 | $25k-$30k
* Based on this start date, the majority of the cost would be incurred in 2014

## Slide 5: ERCOT Recommendations (seeking PRS input)
Revision Request | Recommendation
NPRR256 – Sync PRR787, Add Non-Compliance Lang. to QSE Performance Standards | Defer start to March 2013 (or hold pending GREDP discussions)
NPRR425 – Creation of a WGR Group for GREDP and Base Point Deviation Evaluation and Mixing Turbine Types Within a WGR | Convert to 2 phase approach 1 – Registration portion 2 – GREDP portion Begin Registration portion in the immediate term Hold GREDP portion pending market discussion on GREDP
NOGRR084 – Daily Grid Operations Summary Report | Defer start to October 2013 (resource limitations and high funding requirement)
NPRR210 – Wind Forecasting Change to P50, Sync with PRR841 | Reprioritize to 2014 (avoid resource conflict with Settlement System Upgrade)
NPRR240 – Proxy Energy Offer Curve | Reprioritize to 2014 ($0 spend projected in 2013)
NPRR181 – FIP Definition Revision | Remove from PPL, return to Parking Deck ($0 spend projected in 2013)