## Slide 1
Business Integration Update to PRS
January 17, 2013

## Slide 2: Business Integration Update – Agenda
  Project Portfolio Update p. 3-9
    Upcoming Project Implementations
    2012 Release Results
    2013 Release Targets
    2012 Project Spending Results
    2013 Project Spending Update
    2013 Revision Request Cash Flow Projection
    PPL Updates
  Appendix
    Project Portfolio Gantt Chart p. 10-19
Location of Project Priority List (PPL): http://www.ercot.com/services/projects/index

## Slide 3: Upcoming Project Implementations
Due to ERCOT the systems outage and subsequent restoration activities, the 2012-R6 release was postponed. ERCOT is expecting to include all 2012-R6 items in the 2013-R1 release in February. Please watch for market notices for more details.
Release 1 Go-Lives (2/11/2013 - 2/13/2013)
  NPRR260 – MIS Secure Access
  NPRR313 – Revisions to the Resource Plan Reference to Current Operating Plan for EILS and Synchronous Condensers and Black Start Notification Requirements
  NPRR322 – Real-Time PTP Option Modeling
  NPRR377 – Alternate Inputs to Base Point Deviation Charge
  NPRR397 – Balance of the Day Ancillary Service Market
  NPRR407 – Credit Monitoring Posting Requirements (MMS/CDR portion)
  NPRR464 – SASM Procurement Reporting
  NPRR469 – Modifications to CCTs
  SCR768 – Automatic Non-Spin Redeployment and Deployment Based on Resource Availability
  Security and Reliability Compliance Business Enterprise Tracking and Support Software
  Cyber Security Project #1
  MAI Conversion to iGrid
Note: Projected Go-Live dates are subject to change. Please watch for market notices as the effective dates approach.

## Slide 4: 2012 Release Targets – Board-Approved NPRRs/SCRs/xGRRs
Release Approach | Release 1 2/2012 | Release 2 4/2012 | Release 3 6/2012 | Release 4 8/2012 | Release 5 10/2012 | Release 6 Canceled | TBD
On-Cycle | NPRR326 NPRR355 SCR760(b) SCR761 SCR764(e) | NPRR314 NPRR359 NPRR361 NPRR395 NPRR434 | NPRR351 NPRR354(a) NPRR360 NPRR379 NPRR437 SCR760(c) | NPRR348 NPRR354(b) NPRR382 NPRR383 NPRR422 NPRR442 |  | NPRR260 NPRR322 NPRR377 NPRR397 NPRR407(a) NPRR464 NPRR469 SCR768 | 
Off-Cycle |  |  | NPRR294 NPRR403 RMGRR100 SCR756(a) | NPRR357 NPRR430 |  | NPRR347 NPRR365 NPRR391 NPRR400 | NPRR222
Counts Total = 33 | 5 | 5 | 10 | 8 | 0 | 4 | 1
Bold indicates inclusion in the original Board-approved 2012 PPL
(a), (b), etc. indicates multiple release phases
Release targets are subject to change
November
Mid-Sept
Early June
None
Early Oct
None
Deleted
Red Text: New additions and target release changes
Strike-Through Text: Previous target release changes

## Slide 5: 2013 Release Targets – Board-Approved NPRRs/SCRs/xGRRs
Release Approach | Release 1 2/2013 | Release 2 4/2013 | Release 3 6/2013 | Release 4 7/2013 | Release 5 9/2013 | Release 6 12/2013 | 2013 TBD
On-Cycle | NPRR260 NPRR313 NPRR322 NPRR377 NPRR397 NPRR407(a) NPRR464 NPRR469 SCR768 | NPRR456 NOGRR093 | NPRR153 NPRR272 NPRR393 NPRR463 SCR760(d) SCR770 | NPRR207 NPRR327 NPRR407(b) NPRR416 NPRR439 | NPRR385 NPRR425 NPRR439 NPRR461 NPRR479 NPRR481 NOGRR093 SCR769 SCR771 | NPRR210 NPRR256 NPRR419 NPRR457 NPRR476 NOGRR084 | NPRR240 SCR756(b)
Off-Cycle |  |  |  |  |  |  | 
Counts Total = 37 | 9 | 1 | 6 | 5 | 8 | 6 | 1
None
None
None
None
None
None
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
(a), (b), etc. indicates multiple release phases
Release targets are subject to change
Red Text: New additions and target release changes
Strike-Through Text: Previous target release changes

## Slide 6: Project Spending Results – 2012
PPL – 2012 Project Categories | Portfolio Budget (effective 1/1/2012) | 2012 YTD Actual (as of 12/31/2012) | 2012 Spending Projection of In-Flight Projects (as of 11/30/2012) | Current 2012 Demand (as of 11/30/2012)
Business Strategy |  | $ 5,619,007 | $ 5,800,000 | $ 5,727,389
Regulatory |  | $ 1,078,010 | $ 1,100,000 | $ 1,075,535
Efficiencies/Enhancements |  | $ 2,793,293 | $ 2,700,000 | $ 2,827,630
Technical Foundation |  | $ 6,519,475 | $ 6,600,000 | $ 6,718,483
Totals | $ 15,000,000 | $ 16,009,785 | $ 16,200,000 | $ 16,349,037
ERCOT Public
Definitions:
Portfolio Budget: 2012 project budget approved as a part of the 2012 ERCOT budget
2012 Spending Projection of In-Flight Projects: Projected total 2012 spend for all projects that are in-flight or are complete
Current 2012 Demand: Total cost of all 2012 candidate projects (completed, in-flight, and not started)
2012 YTD Actual: Actual year to date charges recorded in the financial system at the end of the previous month

## Slide 7: Project Spending Update – 2013
PPL – 2013 Project Categories | Portfolio Budget (effective 1/1/2013) | 2013 YTD Actual (as of 1/1/2013) | 2013 Spending Projection of In-Flight Projects (as of 1/1/2013) | Current 2013 Demand (as of 1/1/2013)
Business Strategy |  | $ 0 | $ 4,153,450 | $ 6,529,387
Regulatory |  | $ 0 | $ 439,826 | $ 448,533
Efficiencies/Enhancements |  | $ 0 | $ 1,721,227 | $ 2,565,471
Technical Foundation |  | $ 0 | $ 11,103,947 | $ 12,295,333
Totals | $ 15,000,000 | $ 0 | $ 17,418,450 | $ 21,838,724
ERCOT Public
Definitions:
Portfolio Budget: 2013 project budget approved as a part of the 2013 ERCOT budget
2013 Spending Projection of In-Flight Projects: Projected total 2013 spend for all projects that are in-flight or are complete
Current 2013 Demand: Total cost of all 2013 candidate projects (completed, in-flight, and not started)
2013 YTD Actual: Actual year to date charges recorded in the financial system at the end of the previous month

## Slide 8: 2013 Revision Request Cash Flow Projection
ERCOT Public

## Slide 9: PPL Updates
2013 Release Dates Set
  Release week noted in header of PPL
    R1 2/11 - 2/15
    R2 4/22 - 4/26
    R3 6/10 - 6/14
    R4 7/29 - 8/2
    R5 9/23 - 9/27
    R6 12/9 - 12/13
  There is also an alternate “release weekend” that may be used each month
    Coincides with Retail SLA
  As always, the specific timeline for each Revision Request will be specified in a market notice
PPL Format Notes
  “Release” column revised to included all years (not just 2012)
  “Multiyear” removed from file name

## Slide 10: Business Integration Update – Appendix
  Appendix
    1/11/2013 Project Gantt
      In-flight items sorted by Project End Date
      “Not Started” items sorted by Project Start Date

## Slide 11
Project Portfolio Status – as of 1/11/2013

## Slide 12
Project Portfolio Status – as of 1/11/2013

## Slide 13
Project Portfolio Status – as of 1/11/2013

## Slide 14
Project Portfolio Status – as of 1/11/2013

## Slide 15
Project Portfolio Status – as of 1/11/2013

## Slide 16
Project Portfolio Status – as of 1/11/2013

## Slide 17
Project Portfolio Status – as of 1/11/2013

## Slide 18
Project Portfolio Status – as of 1/11/2013

## Slide 19
Project Portfolio Status – as of 1/11/2013