| NPRR Number | 484 | NPRR Title | Revisions to Congestion Revenue Rights Credit Calculations and Payments |
| --- | --- | --- | --- |
| Impact Analysis Date |  | January 30, 2013 |  |
| Cost/Budgetary Impact |  | Between $950,000 and $1,200,000 Annual recurring Operations and Maintenance (O&M) Budget Cost: $120k – $130k (See ERCOT Staffing Impacts) |  |
| Estimated Project Time Requirements |  | The timeline for implementing this Nodal Protocol Revision Request (NPRR) is dependent upon ERCOT Board prioritization and approval. Please see the Project Priority List (PPL) for additional information. Estimated project duration: Phase 1 - 10 to 14 months * Phase 2 - 5 to 7 months ** |  |
| ERCOT Staffing Impacts (across all areas) |  | There will be an ongoing operational impact of 0.6 FTEs in Credit Management. ERCOT has assessed its ability to absorb the ongoing efforts of this NPRR with current staff. The Credit Management department is unable to absorb the effort and requires 1 FTE additional staff. |  |
| ERCOT Computer System Impacts |  | The following ERCOT systems would be impacted: - Congestion Revenue Right (CRR) - Credit Monitoring and Management (CMM) - System Integration - Settlements and Billing (S&B) - Current Day Reports (CDR) - Enterprise Information Services (EIS) |  |
| ERCOT Business Function Impacts |  | No impacts to ERCOT business functions. |  |
| Grid Operations & Practices Impacts |  | No impacts to ERCOT grid operations and practices. |  |

Alternatives for a More Efficient Implementation

Implement the change in two phases: PHASE 1: Path specific adders in CRR credit lock calculations & FCE calculations to include Path-Specific Adders and Portfolio Weighting (Protocol Sections 7.5.3, 7.5.5.3, 16.11.4.5): - Impact Analysis: $850k-$1M; Duration estimate – 10-14 months*; System impacts - CRR, CMM, CDR, System Integration, EIS PHASE 2: Deferred Invoice Responsibility (Protocol Sections 7.8, 9.8, 9.9, 9.9.1, 9.9.2): - Impact Analysis - $100k-$150k; Duration estimate - approximately 5-7 months **; System impacts - S&B, CMM, System Integration, EIS

Evaluation of Interim Solutions (e.g., manual workarounds)

None offered.

Feasibility of Implementation

Impact on Resource Availability: None identified. Impact on Other Projects: None identified.

Comments

* Due to the volume and complexity of the calculations, estimates for Infrastructure & licensing may increase based on performance test results. ** This project will be constrained by resource availability in the Commercial Applications Development area and have cross impacts with the Settlements Upgrade project and may result in longer implementation timelines and changes needing to be coded twice.