## Sheet1
DSWG Goals for 2013
Ranking (1 to 17) | Goal Description | Deliverable | Scheduled Completion | Market Champion | Contributors
| Weather-Sensitive ERS Loads | NPRR 505 approval | End of Q1 | Robert King | Perrin Wall, Michael Cozzi, Jay Zarnikau | 3.9474
| ERS Clearing Price | Draft NPRR | End of Q1 | Joel Obillo | John Tipton, Michael Cozzi, Malcolm Ainspan, Perrin Wall, Robert King | 4.1579
| ERS-30 | Complete Pilot Project and Introduce NPRR | 2013-09-01 | Robert King | Malcolm Ainspan, Joel Obillo, Michael Cozzi | 4.5789
| ERS Deployment Time Limit | Draft NPRR |  | Robert King | John Tipton, Malcolm Ainspan, Joel Obillo, Perrin Wall | 5.7895
| Aggregated Load Resources | Document, develop and/or file any necessary rule change requests to enable ALR participation in Ancillary Services |  |  | Jay Zarnikau, Perrin Wall, Justin Louis, Robert King | 7.3684
| DR Participation in the Real-Time Energy Market | Lessons Learned document from DR community; collect input from other regions |  |  | Joel Obillo, Suzanne Bertin, Perrin Wall, Caryn Rexrode, Cyrus Reed, Jay Zarnikau, John Tipton, Robert King | 7.9737
| Adjust DR Capacity for T&D Losses | Complete and file NPRR | End of Q1 | Tim Carter | Joel Obillo | 8.7895
| Assessment of ERS Potential | Report posted to ERCOT.com |  |  | Robert King | 10.1316
| DR components of CDR | Provide input to GATF consistent with outcome of PUC project |  |  | Cyrus Reed, Malcolm Ainspan, Jay Zarnikau, Robert King | 10.5526
| DR components of SARA | Provide input to GATF |  |  | Cyrus Reed, Jay Zarnikau, Robert King | 10.6579
| ERS-30 Include ERS Generators | Draft NPRR |  |  | John Tipton, Robert King | 10.6842
| Load Resource M&V via Baseline Methodology | Draft NPRR |  |  | Caryn Rexrode, Justin Louis, Robert King | 10.7105
| ERS Training/Outreach | Workshop; online training session |  |  |  | 10.9737
| Update Load Participation in ERCOT Markets document | Finish and post consistent with outcome of PUC project | End of Q1 | Tim Carter | Joel Obillo, Caryn Rexrode | 11.3421
| Retail DR/Dynamic Pricing Project | Support ERCOT/LSEproject on data collection & analysis |  |  | Suzanne Bertin, Michael Cozzi, Jay Zarnikau | 11.4474
| DR Asset Mapping | Explore locational mapping for ERS and retail demand response, potentially in support of NPRR 491 | 3rd Quarter 2013 | Perrin Wall |  | 11.6053
| Accuracy of NPRR 351 Price Forecasts | Review and provide recommendations for reports from ERCOT |  |  |  | 11.7105
Y, N or A | Move DSWG meetings to Wednesdays? | 7N, 5Y, 7A