## Slide 1
2013 Project Funding Review
February 7, 2013

## Slide 2: Background
ERCOT has a $15M project budget in 2013 (same as 2012)
  To allow for new additions to the 2013 project plan, $3M was forecasted for revision requests on the 2013 PPL
    There were only a few 2013 revision requests known at the time totaling less than $1M
  Previous year revision request spending indicated $3M was a reasonable starting point

## Slide 3: Moving Forward… ERCOT Recommendations
In order to effectively manage to our $15M budget it is critical that PRS and TAC continue to prioritize revision requests
  Continue monthly PRS review of upcoming revision request project efforts to obtain stakeholder input on the target start dates of items in the project queue
  Similarly, ERCOT leadership regularly reviews PPL projections and makes adjustments to ERCOT-sponsored projects
  Now that 2013 is underway, project financial reporting will focus on overall portfolio demand and forecast spending
Stakeholder discussions should focus on prioritization, not funding
  Funding is only one type of resource constraint
  Human resource and environment constraints continue to factor significantly into our project forecasting efforts
  ERCOT will continue to assess the effect of all resources to produce a proposed timeline for approved projects with highest priority
    Reported monthly at PRS and in the posted PPL (see slide 6)

## Slide 4: Moving Forward… ERCOT Recommendations
The next slide (#5) shows 2013 forecast spending and includes:
  Projects that are in flight
  Projects that are planned to start in 2013
    Slide 6 shows the planned Start Dates for revision requests that are “Not Started”
  A forecast variance based on historical trends

## Slide 5: 2013 Cash Flow Projection – Approved Projects

## Slide 6: Approved Revision Requests “Not Started” – Planned to Start in 2013
Revision Request | Target Start Date | Target End Date | Cost Estimate
NPRR385 – Negative Price Floor | Feb 2013 | Oct 2013 | $75k-$90k
NOGRR084 – Daily Grid Operations Summary Report | Feb 2013 | Dec 2013 | $300k-$500k
NPRR153 – Generation Resource Fixed Quantity Block Offer | Mar 2013 | Jun 2013 | $12k-$16k
NPRR256 – Sync PRR787, Add Non-Compliance Lang. to QSE Performance Standards | Mar 2013 | Dec 2013 | $100k-$250k
NPRR407 – Credit Monitoring Posting Requirements – CRR Portion | Mar 2013 | Jul 2013 | $90k-$110k
SCR769 – CRRAH Digital Certificate New Role for Read Only Access | Mar 2013 | Sep 2013 | $100k-$110k
SCR771 – Allow Independent Master QSE to Represent Split Gen. Resources | Mar 2013 | Sep 2013 | $95k-$110k
NPRR207 – Unit Deselection | Apr 2013 | Jul 2013 | $45k-$55k
NPRR439 – Updating a Counter-Party's Avail. Credit Limit for Current Day DAM | Apr 2013 | Sep 2013 | $120k-$130k
NPRR476 – Market Submitted Energy Offer Curves | Apr 2013 | Dec 2013 | $45k-$60k
NPRR479 – Daily Net Outage MW Report | Apr 2013 | Sep 2013 | $40k-$50k
NPRR481 – Report Hourly Actual System Load by Weather Zone | Apr 2013 | Sep 2013 | $25k-$35k
NPRR457 – Daily Update of New ESI IDs and AMS Meter and Switch Hold Indicators Change | Jun 2013 | Dec 2013 | $40k-$60k
NOGRR093 – Synchronization with NPRR365 | Jun 2013 | Sep 2013 | $20k-$25k
NPRR210 – Wind Forecasting Change to P50, Sync with PRR841 | Jul 2013 | Dec 2013 | $45k-$55k
NPRR419 – Revise Real Time Energy Imbalance and RMR Adjustment Charge | Jul 2013 | Dec 2013 | $25k-$30k
ERCOT requests your input: Are these the most important revision requests to work on in 2013?