## Original
Sharyland Transition to Competition
| 2013 | [17 empty] | 2014
| September |  |  |  |  | October |  |  |  | November |  |  |  | December |  |  |  |  | January |  |  |  | February |  |  |  | March |  |  |  |  | April |  |  |  | May |  |  |  | June | July |  |  |  | August |  |  |  | September |  |  |  |  | October |  |  |  | November |  |  |  | December
Week | 2 | 9 | 16 | 23 | 30 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 1 | 8 | 15 | 22 | 29
Sharyland -Education | [10 empty] | Host meetings in each division to explain competition and transition | [21 empty] | 4/15-4/17 - Assign ESI IDs to Default REPs |  |  | Customers are transitioned to REPs on their normal scheduled meter read date, with no out-of-cycle reads. Goal is 100% reads. No additional move-in or switch transactions, except new service requests will be handled through an exception process. |  |  |  | Transition Complete by May 31 and normal processes resume on June 4
Sharyland - Customer and REPs | [5 empty] | Finalize list of Default REPs (up to 15 for each rate class) | [9 empty] | Provide Mass Customer List to REPs |  |  |  |  | Inform Customers of Default REPs if they do not select
Sharyland - Transactions | ESI ID info loaded via 814_20s | [8 empty] | 12 months of historical usage data for ESI IDs loaded | [12 empty] | Process CR transactions | [10 empty] | Process Default REP transactions
Competitive REPs (CRs) | [15 empty] | Receive Mass Customer List | [6 empty] | CRs submit transactions to be executed on the meter read date through April 15 until the Default REP moratorium (request may not be pending for more than 90 days before date requested)
Default REPs | [5 empty] | List of Default REPs finalized (up to 15 for each rate class) | [9 empty] | Receive Mass Customer List | [16 empty] | Default REPs submit transsactions for assigned customers (4/17 - 4/30)
ERCOT |  |  |  | Sharyland ESI ID Information begins showing on TDSP extract | [18 empty] | Process CR transactions | [9 empty] | Process Default REP transactions
Default REP Moratorium and Transition Moratorium | [32 empty] | Default REP Moratorium SU will not honor Competitive REP transactions to focus on Default REP transactions |  |  | Transition Moratorium SU will not honor move-in or switch requests to focus on transitioning customers.

## Amended Default REP Calendar
Sharyland Transition to Competition
| 2013 | [17 empty] | 2014
| September |  |  |  |  | October |  |  |  | November |  |  |  | December |  |  |  |  | January |  |  |  | February |  |  |  | March |  |  |  |  | April |  |  |  | May |  |  |  | June | July |  |  |  | August |  |  |  | September |  |  |  |  | October |  |  |  | November |  |  |  | December
Week | 2 | 9 | 16 | 23 | 30 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 1 | 8 | 15 | 22 | 29
Sharyland -Education | [10 empty] | Host meetings in each division to explain competition and transition | [18 empty] | 3/24-3/25 - Assign ESI IDs to Default REPs | [5 empty] | Customers are transitioned to REPs on their normal scheduled meter read date, with no out-of-cycle reads. Goal is 100% reads. No additional move-in or switch transactions, except new service requests will be handled through an exception process. |  |  |  | Transition Complete by May 31 and normal processes resume on June 4
Sharyland - Customer and REPs | [5 empty] | Finalize list of Default REPs (up to 15 for each rate class) | [9 empty] | Provide Mass Customer List to REPs |  |  |  |  | Inform Customers of Default REPs if they do not select
Sharyland - Transactions | ESI ID info loaded via 814_20s | [8 empty] | 12 months of historical usage data for ESI IDs loaded | [12 empty] | Process CR transactions | [7 empty] | Process Default REP/CR transactions |  | Process CR Transactions
Competitive REPs (CRs) | [15 empty] | Receive Mass Customer List | [6 empty] | CRs submit transactions to be executed on the meter read date. through April 15 until the Default REP moratorium (request may not be pending for more than 90 days before date requested)
Default REPs | [5 empty] | List of Default REPs finalized (up to 15 for each rate class) | [9 empty] | Receive Mass Customer List | [14 empty] | Default REPs submit transsactions for assigned customers.
ERCOT |  |  |  | Sharyland ESI ID Information begins showing on TDSP extract | [18 empty] | Process CR transactions | [7 empty] | Process Default/CR REP transactions |  | Process CR transactions
Default REP Moratorium and Transition Moratorium | [32 empty] | Default REP Moratorium SU will not honor Competitive REP transactions to focus on Default REP transactions |  |  | Transition Moratorium SU will not honor move-in or switch requests to focus on transitioning customers.