|  |  |  |  | System Planning |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Monthly Status Report January 2013 |  |  |
|  |  | Report Highlights |  |  |  |  |  |  |
|  | - ERCOT is currently tracking 159 active generation interconnection requests totaling over 48,000 MW. This includes over 20,000 MW of wind generation. |  |  |  |  |  |  |  |
|  | - ERCOT is currently reviewing proposed transmission improvements with a total cost of $278.9 Million - Transmission Projects endorsed in 2013 total $58.1 Million - All projects (in engineering, routing, licensing and construction) total approximately $9.97 Billion. - Transmission Projects energized in 2012 total about $854.2 million. |  |  |  |  |  |  |  |

Table of Contents

1.	Generation Interconnection	1

1.1	Signed Generation Interconnection Agreements	1

1.2	New Generation Registering for Commercial Operations  	1

1.3	Summary of Generation Interconnection Requests	1

1.4	Projects with Interconnection Agreements	4

1.5	Generation Projects Undergoing Full Interconnection Studies with Confidentiality Waived by Developer	4

1.6	Generation Projects Undergoing Full Interconnection Studies	5

1.7	Wind Generation Capacity Installed by Year  	6

2.	Regional Planning Group Project Reviews	7

3.	Congestion Costs	8

4.	Wind Generation as a Percent of Load	11

5.	Planning Model Activities	12

6.	Other Notable Activities	13

# 1.	Generation Interconnection

Additional information regarding detailed generation interconnection and impact studies is contained in the “Generation Project Interconnection Information” folder in the “Operations and System Planning” area on the ERCOT website:  http://planning.ercot.com/login/login.

## Signed Generation Interconnection Agreements

13INR0058 – OCI Alamo 1  – 50 MW of Solar in Bexar County

10INR0089 – Deepwater Energy Storage – 40 MW of Batteries in Harris County

14INR0015 – Deer Park Energy Center – 192 MW of Combined Cycle Gas in Harris County

## New Generation Registering for Commercial Operations

12INR0076 – NoTrees Battery Storage  – 36 MW of Batteries in Winkler County

The total installed wind capacity is now reported as 10,407 MW by the resource owners through the registration process. Capacity by North, South and West is 669 MW,  2,375 MW, and 7,363 MW respectively. 850 MW is able to switch between the West and South zones and is currently shown in the South zone.

## Summary of Generation Interconnection Requests

| GENERATION INTERCONNECTION REQUESTS CURRENTLY UNDER REVIEW |  |  |  |  |
| --- | --- | --- | --- | --- |
| Currently tracking 165 generation interconnection or change requests |  |  |  |  |
| As of January 31, 2013 |  |  |  | Total |
| Security Screening Study | 9 |  |  |  |
| SSS Completed | 25 |  |  |  |
| Full Interconnect Study | 86 |  |  |  |
| FIS Completed | 12 |  |  |  |
| Suspended Studies | 6 |  |  |  |
| Capacity of Suspended Study Projects | 951 |  |  |  |
| Interconnect Agreement Completed | 27 |  |  |  |
| Capacity under Interconnection Agreements | 11,932 |  |  |  |
| Capacity for Grid, MW | 48,025 |  |  |  |
| Wind Capacity, MW | 20,147 |  |  |  |

| Fuel Type | Confidential Projects (MW) | Projects Under Full Study (MW) | Public Projects (MW) | Suspended Studies (MW) | Grand Total (MW) |
| --- | --- | --- | --- | --- | --- |
| Gas-AllOther |  |  | 89 |  | 8,439 |
| Gas-CombinedCycle |  |  | 5,878 |  | 13,833 |
| Total Gas | 11,227 | 5,078 | 5,967 |  | 22,272 |
| Nuclear |  |  |  |  |  |
| Coal |  | 850 | 1,165 |  | 2,015 |
| Wind | 2,076 | 14,681 | 3,390 | 913 | 21,060 |
| Solar | 770 | 537 | 50 | 38 | 1,395 |
| Biomass |  |  |  |  |  |
| Storage |  | 874 | 40 |  | 914 |
| Petroleum Coke |  |  | 1,320 |  | 1,320 |
| Grand Total | 14,073 | 22,020 | 11,932 | 951 | 48,976 |

County Location of Installed Generation and Interconnection Requests (all fuels)

## Projects with Interconnection Agreements

| Generation Interconnections as of January 31, 2013 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| INR | Site Name | County | COD | Fuel | MW For Grid | Change from Last Report |
| 12INR0075 | Blue Summit Windfarm | Wilbarger | Feb-13 | Wind | 135 | Date |
| 08INR0049 | Bobcat Bluff | Clay | Feb-13 | Wind | 163 | Date |
| 11INR0033 | Los Vientos | Cameron | Feb-13 | Wind | 400 | Date |
| 09INR0001 | Sandy Creek 1 | McLennan | Apr-13 | Coal | 925 |  |
| 13INR0058 | OCI Alamo 1 | Bexar | May-13 | Solar | 50 | NEW |
| 10INR0089 | Deepwater Energy Storage | Harris | May-13 | Storage | 40 | NEW |
| 12INR0086 | WA Parish Addition | Fort Bend | May-13 | Gas | 89 |  |
| 11INR0013 | Goldthwaite Wind Energy | Mills | Sep-13 | Wind | 150 |  |
| 14INR0030a2 | Panhandle Wind | Carson | Nov-13 | Wind | 322 |  |
| 11INR0054 | Midway Farms Wind | San Patricio | Dec-13 | Wind | 161 |  |
| 12INR0034 | Stephens-Borlynn Wind Project | Borden | Dec-13 | Wind | 378 |  |
| 14INR0015 | Deer Park Energy Center | Harris | Jun-14 | Gas-CC | 192 | NEW |
| 13INR0021 | Ferguson Replacement Project | Llano | Jul-14 | Gas-CC | 116 |  |
| 10INR0020a | Panda Temple Power | Bell | Aug-14 | Gas-CC | 809 |  |
| 10INR0021 | Panda Sherman Power | Grayson | Aug-14 | Gas-CC | 809 |  |
| 11INR0050 | Moore Wind 1 | Crosby | Aug-14 | Wind | 149 |  |
| 14INR0023 | Longhorn Energy Center | Briscoe | Dec-14 | Wind | 361 |  |
| 13INR0005 | Conway Windfarm | Carson | Dec-14 | Wind | 600 |  |
| 06INR0022c | Penascal Wind Farm 3 | Kenedy | Dec-14 | Wind | 202 |  |
| 09INR0051 | Mesquite Creek | Borden | Mar-15 | Wind | 249 |  |
| 08INR0018 | Gunsight Mountain | Howard | Aug-15 | Wind | 120 |  |
| 13INR0023 | Texas Clean Energy Project | Ector | Jan-16 | Coal | 240 |  |
| 06INR0006 | Cobisa-Greenville | Hunt | May-16 | Gas-CC | 1,792 |  |
| 10INR0020b | Panda Temple Power | Bell | May-16 | Gas-CC | 780 |  |
| 10INR0022 | Pondera King Power Project | Harris | Jun-16 | Gas-CC | 1,380 |  |
| 12INR0016a | Las Brisas Energy Center | Nueces | May-18 | PetCoke | 660 |  |
| 12INR0016b | Las Brisas Energy Center | Nueces | May-18 | PetCoke | 660 |  |

## Generation Projects Undergoing Full Interconnection Studies with Confidentiality Waived by Developer

None

## Generation Projects Undergoing Full Interconnection Studies

| INR | County | Fuel | MW | COD |  | INR | County | Fuel | MW | COD |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 11INR0094 | Kent | Solar | 100 | Apr-13 |  | 12INR0045 | Kleberg | Wind | 135 | Jun-13 |
| 13INR0057 | Archer | Wind | 65 | Jun-13 |  | 13INR0060 | Hidalgo | Gas | 50 | Jun-13 |
| 13INR0025 | Randall | Wind | 150 | Sep-13 |  | 13INR0046 | Limestone | Wind | 71 | Sep-13 |
| 13INR0059 | Castro | Wind | 499 | Oct-13 |  | 13INR0028 | Hale | Gas | 359 | Nov-13 |
| 14INR0030a1 | Carson | Wind | 322 | Nov-13 |  | 11INR0062 | Nueces | Wind | 178 | Dec-13 |
| 11INR0085 | Nolan | Wind | 106 | Dec-13 |  | 12INR0002a | Briscoe | Wind | 200 | Dec-13 |
| 12INR0054 | Jones | Wind | 200 | Dec-13 |  | 12INR0059 | Pecos | Solar | 50 | Dec-13 |
| 13INR0007 | Pecos | Wind | 200 | Dec-13 |  | 13INR0036 | Hidalgo | Wind | 200 | Dec-13 |
| 13INR0038 | Swisher | Wind | 300 | Dec-13 |  | 13INR0050 | Comanche | Wind | 200 | Dec-13 |
| 13INR0052 | Starr | Wind | 200 | Dec-13 |  | 13INR0055 | Zapata | Wind | 250 | Dec-13 |
| 13INR0056 | Scurry | Wind | 366 | Dec-13 |  | 12INR0079 | Kenedy | Wind | 200 | Dec-13 |
| 11INR0057 | Cameron | Wind | 165 | Dec-13 |  | 11INR0093 | San Patricio | Wind | 41 | Dec-13 |
| 12INR0068 | Jim Hogg | Wind | 80 | Dec-13 |  | 12INR0088 | Crosby | Wind | 201 | Dec-13 |
| 13INR0048 | Oldham | Wind | 161 | Dec-13 |  | 14INR0024 | Kinney | Solar | 42 | Dec-13 |
| 12INR0055 | Baylor | Wind | 40 | Jan-14 |  | 12INR0084 | Randall | Wind | 242 | Jan-14 |
| 13INR0006 | Gray | Wind | 750 | Jan-14 |  | 13INR0045 | Castro | Wind | 288 | Jan-14 |
| 14INR0013 | Cameron | Wind | 103 | Jan-14 |  | 14INR0014 | Val Verde | Solar | 100 | Jan-14 |
| 13INR0010b | Parmer | Wind | 200 | Jan-14 |  | 12INR0060 | Schleicher | Wind | 58 | Apr-14 |
| 13INR0020b | Glasscock | Wind | 150 | May-14 |  | 14INR0027 | Guadalupe | Gas | 471 | May-14 |
| 08INR0019a | Gray | Wind | 250 | Jun-14 |  | 08INR0019b | Gray | Wind | 250 | Jun-14 |
| 08INR0019c | Gray | Wind | 250 | Jun-14 |  | 13INR0026 | Oldham | Wind | 201 | Jun-14 |
| 13INR0049 | Harris | Gas | 352 | Jun-14 |  | 14INR0011 | Swisher | Gas | 270 | Jun-14 |
| 14INR0012 | Gray | Wind | 401 | Jun-14 |  | 14INR0016 | Harris | Gas | 190 | Jun-14 |
| 14INR0031 | Harris | Gas | 0 | Jun-14 |  | 14INR0040 | Hidalgo | Gas | 225 | Jun-14 |
| 12INR0085 | Stonewall | Wind | 24 | Jul-14 |  | 14INR0025 | Floyd | Wind | 500 | Jul-14 |
| 14INR0026 | Presidio | Solar | 28 | Jul-14 |  | 14INR0029 | Uvalde | Solar | 42 | Jul-14 |
| 13INR0040 | Harris | Gas | 0 | Aug-14 |  | 12INR0042a | Deaf Smith | Wind | 265 | Sep-14 |
| 12INR0042b | Deaf Smith | Wind | 135 | Sep-14 |  | 14INR0032 | Randall | Wind | 501 | Sep-14 |
| 12INR0070 | Knox | Wind | 300 | Oct-14 |  | 13INR0031 | Travis | Solar | 30 | Oct-14 |
| 10INR0085 | Ector | Solar | 40 | Dec-14 |  | 11INR0081 | Live Oak | Wind | 72 | Dec-14 |
| 11INR0082A | Val Verde | Wind | 50 | Dec-14 |  | 11INR0082B | Val Verde | Wind | 150 | Dec-14 |
| 12INR0002b | Briscoe | Wind | 200 | Dec-14 |  | 12INR0071 | Caldwell | Wind | 30 | Dec-14 |
| 13INR0054 | Bee | Gas | 0 | Dec-14 |  | 14INR0009 | Kent | Wind | 248 | Dec-14 |
| 14INR0020 | Floyd | Wind | 150 | Dec-14 |  | 14INR0028 | Live Oak | Wind | 300 | Dec-14 |
| 11INR0079a | Clay | Wind | 200 | Dec-14 |  | 08INR0031 | Childress | Wind | 120 | Dec-14 |
| 12INR0029 | Swisher | Wind | 500 | Dec-14 |  | 13INR0020a | Glasscock | Wind | 200 | Dec-14 |
| 14INR0045 | Webb | Wind | 251 | Dec-14 |  | 15INR0021 | Starr | Wind | 200 | Dec-14 |
| 13INR0010c | Parmer | Wind | 200 | Jan-15 |  | 10INR0009 | Castro | Wind | 300 | Mar-15 |
| 12INR0057 | Ector | Solar | 40 | Apr-15 |  | 15INR0032 | Hale | Gas | 197 | Jun-15 |
| 15INR0033 | Hale | Gas | 197 | Jun-15 |  | 15INR0013 | Anderson | Gas | 324 | Oct-15 |
| 15INR0014 | Matagorda | Gas | 280 | Oct-15 |  | 11INR0065 | Nueces | Wind | 350 | Oct-15 |
| 12INR0002c | Briscoe | Wind | 350 | Dec-15 |  | 14INR0018 | Nolan | Solar | 35 | Dec-15 |
| 12INR0018 | Gray | Wind | 500 | Dec-15 |  | 13INR0032 | Andrews | Solar | 30 | Dec-15 |
| 16INR0005 | Cameron | Gas | 871 | Apr-16 |  | 16INR0003 | Brazoria | Gas | 11 | Jun-16 |
| 16INR0004 | Cameron | Gas | 730 | Jun-16 |  | 16INR0006 | Angelina | Gas | 785 | Jun-16 |
| 11INR0040 | Freestone | Gas | 640 | Mar-18 |  | 14INR0003 | Nolan | Coal | 850 | Jun-19 |
| 13INR0010a | Parmer | Wind | 200 | TBD |  | 13INR0010d | Parmer | Wind | 200 | TBD |
| 13INR0010e | Parmer | Wind | 200 | TBD |  | 13INR0010f | Parmer | Wind | 200 | TBD |
| 12INR0081a | Upton | Wind | 112 | TBD |  |  |  |  |  |  |

Note:  Projects that are classified as “Cancelled” or “Suspended” are excluded from this table.

## Wind Generation Capacity Installed by Year

# Regional Planning Group Project Reviews

- AEPSC has submitted the Airline/North Padre Island Area Improvements project. This project was submitted as a revision to the Barney Davis to Laguna 138 kV line (AEPSC Corpus Christi Improvements Project ) that was endorsed by ERCOT in December 2009. This is a Tier 1 project that is estimated to cost approximately $58.1 million. ERCOT has completed the independent review and the project was endorsed by the ERCOT Board of Directors on January 15, 2013.

- Sharyland has submitted the Atlas-Driver Load Integration project, this is a Tier 2 project that is estimated to cost approximately $15.4 million. This project is currently under ERCOT independent review.

- American Electric Power Service Corporation (AEPSC) has submitted the Sinton-Beeville-Kenedy Area Improvements project to accommodate load additions due to Eagle Ford Shale development in South Texas.  This is a Tier 1 project that is estimated to cost $89.2 million. ERCOT has completed the independent review. ERCOT will present the project to TAC on February 7, 2013 and at the Board of Directors in March 2013 for their endorsement.

- LCRA TSC, Guadalupe Valley Electric Cooperative (GVEC), American Electric Power (AEP), and South Texas Electric Cooperative (STEC) have jointly submitted the Kenedy Switch to Nixon to Seguin Line Upgrade project. This is a Tier 1 project that is estimated to cost approximately $55.3 million. ERCOT has completed the independent review. ERCOT will present the project to TAC on February 7, 2013 and at the Board of Directors in March 2013 for their endorsement.

- Guadalupe Valley Electric Cooperative (GVEC) has submitted the McQueeney-SMI-Geronimo 69 kV to 138 kV rebuild project. This is a Tier 2 project that is estimated to cost approximately $8.1 million. This project is currently under ERCOT independent review.

- Oncor has submitted the Permian Basin to Culberson 138 kV line project. The project is estimated to cost approximately $73 million. The Permian Basin to Culberson 138 kV line project is classified as a Tier 3 project and once the RPG comments are resolved it will be reclassified as a Tier 4 Neutral project. This project has been submitted for RPG comments.

- LCRA TSC, Guadalupe Valley Electric Cooperative (GVEC) and American Electric Power (AEP) have jointly submitted the Kenedy Switch to Guadalupe line upgrade project. This is a Tier 3 project that is estimated to cost approximately $37.9 million. This project has been submitted for RPG comments.

# Congestion Costs

Dollars shown in RUC Make Whole payment graph are of settlement quality.

RUC Net Make Whole Payment in $mm

Monthly Average LMP of “ERCOT 345”

Binding Constraints – January 2013

| Contingency | Binding Element | Number of 5-min intervals | Shadow Price Range $/MWh | Estimated Congestion Rent $ (Shadow Price*Limit) | Transmission Project | Comments |
| --- | --- | --- | --- | --- | --- | --- |
| Roanoke Switch - West Denton 345 kV & Roanoke Switch - Lewisville Switch 345 kV; West Denton - Roanoke Switch 345 kV; or RD Wells Interchange - West Denton 138 kV | Fort Worth - Teasley 138 kV | 643 | 0 - 3500 | 3,589,473 | 14TPIT0047 | Outage of the Jim Christal - North Denton 138 kV line |
| Morgan Creek SES - China Grove 138 kV double-circuit | Morgan Creek SES 138/69 kV Autotransformer 3 | 155 | 0 - 2800 | 2,650,503 |  | Invalid contingency |
| Los Fresnos - La Palma 138 kV | La Palma - Villa Cavazos 138 kV | 38 | 13 - 3500 | 1,234,584 | 16TPIT0029 | Forced Outage of 138 kV lines in the Valley area |
| Hamilton Road - Bracketville 138 kV | Hamilton Road - Maverick 138 kV | 818 | 0 - 384 | 585,057 | 16TPIT0024 |  |
| Base Case | West to North Stability | 135 | 0 - 60 | 561,348 | CREZ |  |
| Orange Grove Switching Station - Lon Hill 138 kV; or Whitepoint - Lon Hill 345 kV & Whitepoint - STP 345 kV | Sinton - Skidmore 69 kV | 595 | 0 - 2800 | 554,413 | 16TPIT0027 |  |
| Hiway 9 138/69 kV Autotransformer | Koch Up River 138/69 kV Autotransformer | 32 | 0 - 2800 | 528,694 |  |  |
| Skyline - Calaveras 345 kV double-circuit | Braunig - Cagnon 345 kV | 18 | 11 - 4500 | 508,147 |  | Outage of one Calaveras - Cagnon 345 kV circuit |
| Base Case | Bastrop Energy Center - Garfield AEN 345 kV | 2 | 5000 - 5000 | 495,542 |  | Lower line rating; corrected |
| Willow Creek Switch - Parker Switch 345 kV double-circuit | Graham SES - Parker Switch 345 kV | 73 | 20 - 656 | 490,136 |  | Bus outage at Willow Creek Switch and line outage of a Willow Creek Switch - Parker Switch 345 kV circuit |

# Wind Generation as a Percent of Load

One-hour average of total wind power output as a percentage of ERCOT load.

# Planning Model Activities

- The December TPIT updates are underway to the 13DSA and 13DSB cases.  Projected completion and posting is February 15, 2013.

- The first spreadsheet example for creating TPIT from Model On Demand (MOD) was populated and sent to SSWG for review.  This project will add additional fields to MOD for TSPs to populate during SSWG case building.  The TPIT spreadsheet will be created from the MOD database.  Projected completion July 2013.  The March TPIT spreadsheet will include additional data validation drop-down menus to make certain fields more consistent.

- The short term calendar of major planning model events follows:

  - Jan 16, 2013	Planning Data Dictionary Posted to POI.

  - Jan 17, 2013	Begin December TPIT update to 13 DSA and 13 DSB cases

  - Feb 15, 2013	Complete and Post December TPIT update to 13 DSA and 13 DSB cases.

- Status update on SCR760, Changes Needed for Information Model Manager and Topology Processor for Planning Models, which was approved by the ERCOT Board in March 2011.

  - Bundle 1 (Items 3, 7 and 8): In Production.

  - Bundle 2 (Items 2a, 4, 9):  In Production.

  - Bundle 3 (Item 5, 2b, 2c):  In Production

  - Bundle 4 (Items 1, 6):  Requirements agreed to by ERCOT and Vendor.  Vendor proposal approved by ERCOT.  SOW amendment underway.  Vendor has begun work.  Expect to receive first release in April 2013.

| SCR Sub Part | SCR Description | Status |
| --- | --- | --- |
| SCR760-1 | Upgrade to PSS/E v32 | Production |
| SCR760-2 | Distribution Capacitor banks | Production |
| SCR760-3 | Zero Impedance Line Ratings | Production |
| SCR760-4 | Associate Loads and Capacitor banks with the correct CNG | Production |
| SCR760-5 | Additional Transformer Data for Planning | Production |
| SCR760-6 | FACTS Devices | Planning |
| SCR760-7 | Assign valid PSSE IDs to Breakers/ Switches/ Series Devices | Production |
| SCR760-8 | Phase shift of Autos for short circuit studies | Production |
| SCR760-9 | Multisection Line Grouping | Production |

Table 1:  In the following table:

- Red will be used to show status of Not Submitted, meaning that the SCR sub part has not been submitted to Siemens as a Service Request.

- Yellow will indicate that the SCR sub part has been submitted.  The color will remain yellow and the status will change in order to Submitted, Planning (Requirements, SOW, Code Writing), Release (Siemens produces first code to test), and Testing (code has completed internal test and is moving through release management).

- Green will indicate that the code has been tested and installed on the machines that ERCOT uses to produce Topology Processor output for Planning and CRR.

# Other Notable Activities

- ERCOT has completed the 2012 Five-Year Transmission Plan and the final report was posted at the ERCOT Planning and Operations Information (POI) website on December 27, 2012.  The 5YTP team is currently working on the sensitivity analysis for the 2012 5YTP which is anticipated to be completed by February 28, 2013.

- The Long-Term Study team is wrapping up the scenario analysis for the Department of Energy project.