## Slide 1
Project Update and Summary of Project Priority List (PPL) Activity to Date
February 21, 2013

## Slide 2: 2013 Project Update – Agenda
  Project Portfolio Update p. 3-9
    Recent and Upcoming Project Implementations
    2013 Release Targets
    Review of 2/7/2013 TAC Project Spending Discussion
    2013 Project Spending Update
  Review of Pending Project Priorities p. 10-13
  Appendix
    Project Portfolio Gantt Chart p. 15-22
Location of Project Priority List (PPL): http://www.ercot.com/services/projects/index

## Slide 3: Recent and Upcoming Project Implementations
Due to the ERCOT systems outage and subsequent restoration activities, the 2012-R6 release was postponed. All 2012-R6 items were included in the 2013-R1 release in February. 2013-R1 was completed as planned.
Release 1 COMPLETE (2/11/2013 – 2/13/2013)
  NPRR260 – MIS Secure Access (effective 3/4/2013)
  NPRR313 – Revisions to the Resource Plan Reference to Current Operating Plan for EILS and Synchronous Condensers and Black Start Notification Requirements
  NPRR322 – Real-Time PTP Option Modeling
  NPRR377 – Alternate Inputs to Base Point Deviation Charge
  NPRR397 – Balance of the Day Ancillary Service Market (effective 3/4/2013)
  NPRR407 – Credit Monitoring Posting Requirements (MMS/CDR portion)
  NPRR464 – SASM Procurement Reporting
  NPRR469 – Modifications to CCTs
  SCR768 – Automatic Non-Spin Redeployment and Deployment Based on Resource Availability
  Security and Reliability Compliance Business Enterprise Tracking and Support Software
  Cyber Security Project #1
  Incremental Update Capability Phase 1
  MAI Conversion to iGrid

## Slide 4: Recent and Upcoming Project Implementations
Release 2 Go-Lives (4/22/2013 – 4/26/2013)
  NPRR456 – Clarification of Definition of Electrically Similar Settlement Points and Heuristic Pricing Posting
  NPRR463 – CRR Auction Structure Enhancements
  TSAT Wind Model
Note: Projected Go-Live dates are subject to change. Please watch for market notices as the effective dates approach.

## Slide 5: 2013 Release Targets – Board-Approved NPRRs/SCRs/xGRRs
Release Approach | Release 1 2/2013 | Release 2 4/2013 | Release 3 6/2013 | Release 4 7/2013 | Release 5 9/2013 | Release 6 12/2013 | 2013 TBD
On-Cycle | NPRR260 NPRR313 NPRR322 NPRR377 NPRR397 NPRR407(a) NPRR464 NPRR469 SCR768 | NPRR456 NPRR463 | NPRR153 NPRR272 NPRR393 NPRR463 NOGRR093 SCR760(d) SCR770 | NPRR207 NPRR327 NPRR407(b) NPRR416 NPRR461 NPRR479 NPRR481 | NPRR385 NPRR425 NPRR439 NPRR461 NPRR479 NPRR481 NOGRR093 SCR769 SCR770 SCR771 | NPRR210 NPRR256 NPRR327 NPRR419 NPRR457 NPRR476 NOGRR084 | SCR756(b)
Off-Cycle |  |  |  |  |  |  | SCR756(b) SCR771
Counts Total = 34 | 9 | 2 | 5 | 6 | 5 | 7 | 
None
None
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
(a), (b), etc. indicates multiple release phases
Release targets are subject to change
Red Text: New additions and target release changes
Strike-Through Text: Previous target release changes
None
None
None
None
2014

## Slide 6: Background
ERCOT has a $15M project budget in 2013 (same as 2012)
  To allow for new additions to the 2013 project plan, $3M was forecasted for revision requests on the 2013 PPL
    There were only a few 2013 revision requests known at the time totaling less than $1M
  Previous year revision request spending indicated $3M was a reasonable starting point
In order to effectively manage to our $15M budget it is critical that PRS and TAC continue to prioritize revision requests
  Continue monthly PRS review of upcoming revision request project efforts to obtain stakeholder input on the target start dates of items in the project queue
  Similarly, ERCOT leadership regularly reviews PPL projections and makes adjustments to ERCOT-sponsored projects
  Now that 2013 is underway, project financial reporting will focus on overall portfolio demand and forecast spending
Slide from 2/7/2013 TAC Meeting

## Slide 7: Moving Forward… ERCOT Recommendations
The next slide (#8) shows 2013 forecast spending and includes:
  Projects that are in flight
  Projects that are planned to start in 2013
    Slide 12 shows the planned Start Dates for revision requests that are “Not Started”
  A forecast variance based on historical trends
Slide from 2/7/2013 TAC Meeting

## Slide 8: 2013 Cash Flow Projection – Approved Projects
Slide from 2/7/2013 TAC Meeting

## Slide 9: 2013 Cash Flow Projection – Approved Projects – Revised

## Slide 10
Review of Pending Project Priorities
February 21, 2013

## Slide 11: Review of Pending Project Priorities
Guiding Principles of Project Prioritization
  Posted on the main PRS site on ERCOT.com
    http://www.ercot.com/committees/board/tac/prs/
  Dates back to the days of the prior PPL format with different Priority values
  Due to subsequent changes in the PPL and the prioritization approach, it would make sense that this document either be removed or updated
Review of Proposed Start Dates for Revision Requests
  Several changes since the January 2013 PRS meeting
    Several items have been accelerated due to resource availability
      No impact on 2013 cash flow
    SCR771 delayed due to resource constraints
      2013 cash flow impacts have been estimated
  Details on next slide

## Slide 12: Approved Revision Requests “Not Started” – Planned to Start in 2013
Revision Request | Target Start Date | Target End Date | Cost Estimate | Author
NPRR385 – Negative Price Floor | Feb 2013 | Oct 2013 | $75k-$90k | Luminant
NPRR479 – Daily Net Outage MW Report | Feb 2013 | Jul 2013 | $40k-$50k | Mercuria
NPRR481 – Report Hourly Actual System Load by Weather Zone | Feb 2013 | Jul 2013 | $25k-$35k | MISUG
NOGRR084 – Daily Grid Operations Summary Report | Feb 2013 | Dec 2013 | $300k-$500k | MISUG
NOGRR093 – Synchronization with NPRR365 | Feb 2013 | Jun 2013 | $20k-$25k | PLWG
NPRR153 – Generation Resource Fixed Quantity Block Offer | Mar 2013 | Jun 2013 | $12k-$16k | TPTF
NPRR256 – Sync PRR787, Add Non-Compliance Lang. to QSE Performance Standards | Mar 2013 | Dec 2013 | $100k-$250k | Luminant
NPRR407 – Credit Monitoring Posting Requirements – CRR Portion | Mar 2013 | Jul 2013 | $90k-$110k | Tenaska
SCR769 – CRRAH Digital Certificate New Role for Read Only Access | Mar 2013 | Sep 2013 | $100k-$110k | Austin Energy
NPRR207 – Unit Deselection | Apr 2013 | Jul 2013 | $45k-$55k | QSTF
NPRR439 – Updating a Counter-Party's Avail. Credit Limit for Current Day DAM | Apr 2013 | Sep 2013 | $120k-$130k | ERCOT
NPRR476 – Market Submitted Energy Offer Curves | Apr 2013 | Dec 2013 | $45k-$60k | MISUG
NPRR457 – Daily Update of New ESI IDs and AMS Meter and Switch Hold Ind. Change | Jun 2013 | Dec 2013 | $40k-$60k | MISUG
NPRR210 – Wind Forecasting Change to P50, Sync with PRR841 | Jul 2013 | Dec 2013 | $45k-$55k | Morgan Stanley
NPRR419 – Revise Real Time Energy Imbalance and RMR Adjustment Charge | Jul 2013 | Dec 2013 | $25k-$30k | ERCOT
SCR771 – Allow Ind. Master QSE to Represent Split Gen. Resources | Sep 2013 | Mar 2014 | $95k-$110k | Sandy Creek
ERCOT requests your input: Are these the most important revision requests to work on in 2013?
Moved from Apr 2013
Moved from Apr 2013
Moved from Jun 2013
Moved from Mar 2013

## Slide 13: Review of Pending Project Priorities
Review of ERCOT-sponsored Projects on the PPL
  In prior years, ERCOT held a special session with PRS to review the ERCOT-sponsored items on the proposed PPL for the upcoming year
  The new format of the PPL reduces the need to prioritize revision requests against ERCOT items; however, there is still benefit in providing the market with an overview of projects ERCOT deems necessary to support the ongoing operations of the market and ERCOT Inc.
  Rather than consume the resources needed to walk through the entire PPL in a PRS meeting, ERCOT proposes that we set aside time at an upcoming meeting (March?) to discuss any projects of interest to the market
    Action item for market participants: Email tanderson@ercot.com by Friday, 3/8, with any projects you would like to hear about at the 3/21 PRS meeting
    ERCOT will arrange for the proper subject matter experts (in person or on the phone) to assist in the overview and Q&A
  ERCOT is also working on a major project view that will highlight timeframes where the ability to make changes to certain systems is limited
    Ex. Settlements Upgrade, EMS Upgrade, MMS Refresh

## Slide 14: Business Integration Update – Appendix
  Appendix
    2/20/2013 Project Gantt
      In-flight items sorted by Project End Date
      “Not Started” items sorted by Project Start Date

## Slide 15
Project Portfolio Status – as of 2/20/2013

## Slide 16
Project Portfolio Status – as of 2/20/2013

## Slide 17
Project Portfolio Status – as of 2/20/2013

## Slide 18
Project Portfolio Status – as of 2/20/2013

## Slide 19
Project Portfolio Status – as of 2/20/2013

## Slide 20
Project Portfolio Status – as of 2/20/2013

## Slide 21
Project Portfolio Status – as of 2/20/2013

## Slide 22
Project Portfolio Status – as of 2/20/2013