## calendar (1)
Sharyland Transition to Competition - CR Proposal Option 1
| 2013 | [17 empty] | 2014
| September |  |  |  |  | October |  |  |  | November |  |  |  | December |  |  |  |  | January |  |  |  | February |  |  |  | March |  |  |  |  | April |  |  |  | May |  |  |  | June | July |  |  |  | August |  |  |  | September |  |  |  |  | October |  |  |  | November |  |  |  | December
Week | 2 | 9 | 16 | 23 | 30 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 1 | 8 | 15 | 22 | 29
Sharyland -Education | [10 empty] | Host meetings in each division to explain competition and transition | [21 empty] | 4/14-4/16: Assign remaining ESI IDs (ESI IDs which have not selected a CR) to Default REPs |  |  | Customers are transitioned to REPs on their normal scheduled MMRD, using MVIs. Goal is 100% reads. |  |  |  | Transition Complete by May 31
Sharyland - Customer and REPs | [5 empty] | Finalize list of Default REPs (up to 15 for each rate class) | [9 empty] | Provide Mass Customer List to REPs |  |  |  |  | Inform Customers of Default REPs if they do not select
Sharyland - Transactions | ESI ID info loaded via 814_20s | [8 empty] | 12 months of historical usage data for ESI IDs loaded | [12 empty] | Process CR transactions Sharyland will schedule requested MVI for MMRD | [10 empty] | Process DR MVIs 4/17 -- 4/27 |  | Resume processing CR transactions starting April 28
Competitive REPs (CRs) | [15 empty] | Receive Mass Customer List | [6 empty] | CRs submit MVI transactions Feb 1 - April 13 with a requested move in date on the May Meter Read Date (MMRD)…can't be more than 90 days before MMRD. | [11 empty] | CRs start submitting Move Ins for MMRD +1 (April 28-May 31)
Default REPs (DR) | [5 empty] | List of DRs finalized (up to 15 for each rate class) | [9 empty] | Receive Mass Customer List | [16 empty] | Receive customer list with no CR MVI requests (April 16)
DR | [32 empty] | DRs submit MVI transactions for assigned customers (April 16-25)
ERCOT |  |  |  | Sharyland ESI ID Information begins showing on TDSP extract | [18 empty] | Process CR transactions | [9 empty] | Process DR MVIs |  |  | DR Move In receives unexecutable (814_28). CR Move In +1 receives MMRD (CR Move In -1)
CR Transaction Hold | [32 empty] | CR Transaction Hold (April 14-27)

## calendar (2)
Sharyland Transition to Competition - CR Proposal Option 2
| 2013 | [17 empty] | 2014
| September |  |  |  |  | October |  |  |  | November |  |  |  | December |  |  |  |  | January |  |  |  | February |  |  |  | March |  |  |  |  | April |  |  |  | May |  |  |  | June | July |  |  |  | August |  |  |  | September |  |  |  |  | October |  |  |  | November |  |  |  | December
Week | 2 | 9 | 16 | 23 | 30 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 1 | 8 | 15 | 22 | 29
Sharyland -Education | [10 empty] | Host meetings in each division to explain competition and transition | [21 empty] | 4/15-4/17 - Assign ESI IDs to Default REPs |  |  | Customers are transitioned to REPs on their normal scheduled MMRD, using MVIs. Goal is 100% reads. |  |  |  | Transition Complete by May 31
Sharyland - Customer and REPs | [5 empty] | Finalize list of Default REPs (up to 15 for each rate class) | [9 empty] | Provide Mass Customer List to REPs |  |  |  |  | Inform Customers of Default REPs if they do not select
Sharyland - Transactions | ESI ID info loaded via 814_20s | [8 empty] | 12 months of historical usage data for ESI IDs loaded | [12 empty] | Process CR transactions | [10 empty] | Process DR MVIs |  | Process CR transactions starting April 28
Competitive REPs (CRs) | [15 empty] | Receive Mass Customer List | [6 empty] | CRs submit MVI transactions Feb 1 - April 13 to be executed on the May Meter Read Date (MMRD) | [11 empty] | CRs re-start submitting MVIs for MMRD (April 28-May 31)
CR | [35 empty] | CR submits switch for customers not wanting to pay DR deposit (May 1 - future)
Default REPs (DR) | [5 empty] | List of DRs finalized (up to 15 for each rate class) | [9 empty] | Receive Mass Customer List | [16 empty] | Receive customer list with no CR MVI requests (April 14)
DR | [32 empty] | DRs submit MVI transactions for assigned customers (April 14-25)
ERCOT |  |  |  | Sharyland ESI ID Information begins showing on TDSP extract | [18 empty] | Process CR transactions | [9 empty] | Process DR MVIs |  |  | Process CR transactions
Moratorium | [32 empty] | CR MVI Moratorium ERCOT will hold all CR MVI requests (April 14-27)

## Details
| Option 1 | Option 2
Moratorium (April 14-27) | CRs sends last transaction April 13 and sends transactions again on April 28 | ERCOT holds all transactions from CR and sends to Sharyland on April 28
April 28-May 31 Transactions | CRs submit switch with effective date 1 day after MMRD. DR is ROR via a MVI, then switch from CR changes ROR. | Only CRs send MVIs for MMRD for those ESIs with no ROR
| Sharyland will use the same read data as the MVI | Will use reverse stacking logic - last MVI received is valid MVI, therefore no NFI
Sharyland will waive date specific switch request due to using MVI data from DR; this is similar to Sharyland waiving the MVI fee for the initial MVI form the DR or CR
May 1- future | CR submits standard switch where DR is ROR for customer, and customer wants to switch from DR. An example is where customer does not want to pay required DR deposit | CR submits standard switch where DR is ROR for customer, and customer wants to switch from DR. An example is where customer does not want to pay required DR deposit
| CR submits a standard switch if customer wants to change CR | CR submits a standard switch if customer wants to change CR
| CR performs ESI lookup to see if there is a ROR. | CR performs ESI lookup to see if there is a ROR.
| If no ROR, then CR submits date specific switch for MMRD +1 | If no ROR, then CR submits MVI for MMRD
| If there is a ROR, then CR submits a standard switch | If there is a ROR, then CR submits a standard switch
CR Proposal Pros
Customer Choice: Customer is not burdened with a switching moratorium
Customer can actively choose a CR as all other customers in ERCOT currently do
Empowers customer to choose a CR if the DR requires a deposit
DR has no usage to write off if customer switches to CR with MMRD +1
Only 1 month of Option 1 work for ERCOT - extending 90 day MVI request date so MVI not cancelled
DR has plenty of time (2 weeks) to submit MVIs. Sharyland provides DR all required data
Timing of transactions uses stacking logic to minimize Sharyland manual work