## calendar (1)
Sharyland Transition to Competition - STTF Proposal - CR Transactions with two CRs
2014
| February | March |  |  |  |  | April |  |  | May |  |  |  | July |  |  |  | August |  |  |  | September |  |  |  |  | October |  |  |  | November |  |  |  | December
Date and Time |  | 10 | 10 | 11 | 11 | 11 |  |  |  | 15 - Meter Read Date | 16 |  | 16 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 1 | 8 | 15 | 22 | 29
Competitive Retailer (CR1 and CR2) |  | CR1 - Submits 814_16 Move In Request with/without Request for Usage History for May 15 Meter Read |  |  |  | CR1 Receives 814_05 CR Enrollment Notification Response and 867_02 Historical Usage if requested | CR2 - Submits 814_16 Move In Request with/without Request for Usage History for May 15 Meter Read |  | CR2 Receives 814_17 Move In Reject Response from ERCOT since not first in |  |  |  | 16: Receives 867_04 Initial Meter Read and begins serving customer
ERCOT |  |  | Receives 814_16 Move In Request from CR with/without Request for Historical Usage and Sends 814_03 Enrollment Notification Request to SU |  | Receives 814_04 Enrollment Notification Response and 867_02 Historical Usage if requested; Sends 814_05 CR Enrollment Notification Response & 867_02 Historical Usage if requested to CR |  |  | Receives 814_16 Move In Request from CR with/without Request for Historical Usage and sends 814_17 Move In Reject Response back since not first in |  |  |  | Receives 867_04 Initial Meter Read & updates Registration database | bar: 16
Sharyland (SU) |  |  |  | Receives 814_03 Enrollment Notification from ERCOT. Sends 814_04 Enrollment Notification Response & 867_02 Historical Usage if requested | [5 empty] | Reads meter | Sends 867_04 Initial Meter Read to ERCOT | bar: 16

## Details
Option 1
Moratorium (April 14-27) | CRs sends last transaction April 13 and sends transactions again on April 28
April 28-May 31 Transactions | CRs submit MVI with effective date 1 day after MMRD.
Sharyland will use the same read data for MMRD + 1 as the first MVI.
May 1- future | CR submits standard switch where DR is ROR for customer, and customer wants to switch from DR. An example is where customer does not want to pay required DR deposit
CR submits a standard switch if customer wants to change CR
CR performs ESI lookup to see if there is a ROR.
If no ROR, then CR submits date specific switch for MMRD +1
If there is a ROR, then CR submits a standard switch
CR Proposal Pros
Customer Choice: Customer is not burdened with a switching moratorium
Customer can actively choose a CR as all other customers in ERCOT currently do
Empowers customer to choose a CR if the DR requires a deposit
DR has no usage to write off if customer switches to CR with MMRD +1
DR has plenty of time (2 weeks) to submit MVIs. Sharyland provides DR all required data
Timing of transactions uses stacking logic to minimize Sharyland manual work