## Slide 1
Project Update and Summary of Project Priority List (PPL) Activity to Date
March 21, 2013

## Slide 2: 2013 Project Update – Agenda
  Project Portfolio Update p. 3-5
    Recent and Upcoming Project Implementations
    2013 Release Targets
    2013 Project Spending Update
  Project Prioritization Action Items p. 6-8
    Guiding Principles Document
    Review of ERCOT-Sponsored Projects
    Major Project Timelines
    Planned Revision Requests Starts – 2013
  Appendix
    Project Portfolio Gantt Chart p. 9-16
Location of Project Priority List (PPL): http://www.ercot.com/services/projects/index

## Slide 3: Upcoming Project Implementations
Off-Cycle Release (4/1/2013)
  NPRR463 – CRR Auction Structure Enhancements
Release 2 Go-Lives (4/22/2013 – 4/26/2013)
  NPRR456 – Clarification of Definition of Electrically Similar Settlement Points and Heuristic Pricing Posting
  TSAT Wind Model
Note: Projected Go-Live dates are subject to change. Please watch for market notices as the effective dates approach.

## Slide 4: 2013 Release Targets – Board-Approved NPRRs/SCRs/xGRRs
Release Approach | Release 1 2/2013 | Release 2 4/2013 | Release 3 6/2013 | Release 4 7/2013 | Release 5 9/2013 | Release 6 12/2013 | 2013 TBD
On-Cycle | NPRR260 NPRR313 NPRR322 NPRR377 NPRR397 NPRR407(a) NPRR464 NPRR469 SCR768 | NPRR456 NPRR463 | NPRR153 NPRR272 NPRR393 NOGRR093 SCR760(d) | NPRR207 NPRR407(b) NPRR416 NPRR461 NPRR479 NPRR481 | NPRR272 NPRR385 NPRR407(b) NPRR416 NPRR425 NPRR439 NPRR457 SCR769 SCR770 | NPRR210 NPRR256 NPRR327 NPRR419 NPRR457 NPRR476 NPRR520 NOGRR084 | 
Off-Cycle |  | NPRR463 | SCR760(d) |  |  |  | NPRR484 NOGRR084
Counts Total = 32 | 9 | 2 | 4 | 4 | 8 | 5 | 
Early April
None
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
(a), (b), etc. indicates multiple phases
Release targets are subject to change
Red Text: New additions and target release changes
Strike-Through Text: Previous target release changes
None
None
None
Late June
2014
407(a) – MMS portion
407(b) – CRR portion
SCR760(d) – final phase

## Slide 5: 2013 Cash Flow Projection – Approved Projects

## Slide 6: Guiding Principles Document – Discuss Revision Outline
Guiding Principles of Project Prioritization
  Current version posted at: http://www.ercot.com/committees/board/tac/prs/
  Draft revision still in progress
  Input requested on general structure:
    Definition/Usage of PPL Prioritization Elements
      Project Category
      Priority
      Rank
    Approach to Ranking New Additions to the PPL
      Consider qualitative and quantitative elements of the project
        Bring forward relevant points from current Guiding Principles doc
      Review “Not Started” projects on the PPL that impact similar systems
      Propose rank based on relative importance with similar projects
      Proposed Priority and Rank included in voting materials at TAC and Board
    Approach to Reprioritizing Projects on the PPL
      Consider merits of previously approved, but not yet started, projects in relation to current priorities
      Reprioritizing is recommended if a project is being moved between years
      Proposed Priority and Rank noted in presentations at TAC and Board

## Slide 7: Other Project Prioritization Action Items
Review of ERCOT-Sponsored Projects
  No requests received
  Open request for detailed project overviews at future PRS meetings
    Perhaps in conjunction with 2014 budget cycle
Major Project Timelines
  EMS Upgrade and MMS Tech Refresh are still in Planning phases
  When the Execution phase timelines of these major projects begin to take shape, a slide will be added to this deck with relevant information
  Prioritization of new requests will be the ultimate determining factor

## Slide 8: Approved Revision Requests “Not Started” – Planned to Start in 2013
Revision Request | Target Start Date | Release Target | Cost Estimate | Author
NPRR153 – Generation Resource Fixed Quantity Block Offer | Mar 2013 | 2013-R3 | $12k-$16k | TPTF
NPRR457 – Daily Update of New ESI IDs and AMS Meter and Switch Hold Ind. Change | Mar 2013 | 2013-R5 | $40k-$60k | MISUG
NPRR484 – Revisions to Congestion Revenue Rights Credit Calculations and Payments | Mar 2013 | 2014-R2 | $950k-$1.2M | Luminant
NPRR520 – RT Mitigation Rules and Creation of a RT Constraint Competitiveness Test | Mar 2013 | 2013-R6 | $180k-$200k | ERCOT
NPRR207 – Unit Deselection | Apr 2013 | 2013-R4 | $45k-$55k | QSTF
NPRR407 – Credit Monitoring Posting Requirements – CRR Portion | Apr 2013 | 2013-R5 | $90k-$110k | Tenaska
NPRR439 – Updating a Counter-Party's Avail. Credit Limit for Current Day DAM | Apr 2013 | 2013-R5 | $120k-$130k | ERCOT
NPRR476 – Market Submitted Energy Offer Curves | Apr 2013 | 2013-R6 | $45k-$60k | MISUG
SCR756 – MarkeTrak Enhancements - Remaining SCR756 Items | Jun 2013 | 2014-R2 | $250k-$300k | MkTrk TF
NPRR210 – Wind Forecasting Change to P50, Sync with PRR841 | Jul 2013 | 2013-R6 | $45k-$55k | Morgan Stanley
NPRR419 – Revise Real Time Energy Imbalance and RMR Adjustment Charge | Jul 2013 | 2013-R6 | $25k-$30k | ERCOT
SCR771 – Allow Ind. Master QSE to Represent Split Gen. Resources | Sep 2013 | 2014-R2 | $95k-$110k | Sandy Creek
NOGRR084 – Daily Grid Operations Summary Report | Sep 2013 | 2014-R4 | $300k-$500k | MISUG
NPRR256 – Sync PRR787, Add Non-Compliance Lang. to QSE Perf. Standards | Oct 2013 | 2014-R3 | $100k-$250k | Luminant
SCR769 – CRRAH Digital Certificate New Role for Read Only Access | Nov 2013 | 2014-R2 | $100k-$110k | Austin Energy
ERCOT requests your input: Are these the most important revision requests to work on in 2013?
Moved from Jun 2013
Moved from Mar 2013
Moved from Feb 2013
Moved from Mar 2013
Moved from Mar 2013

## Slide 9: Business Integration Update – Appendix
  Appendix
    3/15/2013 Project Gantt
      In-flight items sorted by Project End Date
      “Not Started” items sorted by Project Start Date

## Slide 10
Project Portfolio Status – as of 3/15/2013

## Slide 11
Project Portfolio Status – as of 3/15/2013

## Slide 12
Project Portfolio Status – as of 3/15/2013

## Slide 13
Project Portfolio Status – as of 3/15/2013

## Slide 14
Project Portfolio Status – as of 3/15/2013

## Slide 15
Project Portfolio Status – as of 3/15/2013

## Slide 16
Project Portfolio Status – as of 3/15/2013