|  |  |  |  | System Planning |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Monthly Status Report March 2013 |  |  |
|  |  | Report Highlights |  |  |  |  |  |  |
|  | - ERCOT is currently tracking 159 active generation interconnection requests totaling almost 48,000 MW. This includes almost 21,000 MW of wind generation. |  |  |  |  |  |  |  |
|  | - ERCOT is currently reviewing proposed transmission improvements with a total cost of $131 Million - Transmission Projects endorsed in 2013 total $282.5 Million - All projects (in engineering, routing, licensing and construction) total approximately $9.68 Billion. - Transmission Projects energized in 2013 total about $38.6 million. |  |  |  |  |  |  |  |

Table of Contents

1.	Generation Interconnection	1

1.1	Signed Generation Interconnection Agreements	1

1.2	New Generation Registering for Commercial Operations - none	1

1.3	Summary of Generation Interconnection Requests	1

1.4	Projects with Interconnection Agreements	4

1.5	Generation Projects Undergoing Full Interconnection Studies with Confidentiality Waived by Developer	4

1.6	Generation Projects Undergoing Full Interconnection Studies	5

1.7	Wind Generation Capacity Installed by Year  	6

2.	Regional Planning Group Project Reviews	7

3.	Congestion Costs	8

4.	Wind Generation as a Percent of Load	11

5.	Planning Model Activities	12

6.	Other Notable Activities	13

# 1.	Generation Interconnection

Additional information regarding detailed generation interconnection and impact studies is contained in the “Generation Project Interconnection Information” folder in the “Operations and System Planning” area on the ERCOT website:  http://planning.ercot.com/login/login.

## Signed Generation Interconnection Agreements

13INR0048 – Spinning Spur Wind II  – 161 MW of Wind in Oldham County

14INR0012 – Miami Wind  – 401 MW of Wind in Gray County

## New Generation Registering for Commercial Operations

08INR0049 – Bobcat Bluff Wind Farm – 163 MW of Wind in Clay County

The total installed wind capacity is now reported as 10,570 MW by the resource owners through the registration process. Capacity by North, South and West is 832 MW,  2,375 MW, and 7,363 MW respectively. 850 MW is able to switch between the West and South zones and is currently shown in the South zone.

## Summary of Generation Interconnection Requests

| GENERATION INTERCONNECTION REQUESTS CURRENTLY UNDER REVIEW |  |  |  |  |
| --- | --- | --- | --- | --- |
| Currently tracking 160 generation interconnection or change requests |  |  |  |  |
| As of March 31, 2013 |  |  |  | Total |
| Security Screening Study | 7 |  |  |  |
| SSS Completed | 30 |  |  |  |
| Full Interconnect Study | 85 |  |  |  |
| FIS Completed | 5 |  |  |  |
| Suspended Studies | 1 |  |  |  |
| Capacity of Suspended Study Projects | 200 |  |  |  |
| Interconnect Agreement Completed | 31 |  |  |  |
| Capacity under Interconnection Agreements | 11,802 |  |  |  |
| Capacity for Grid, MW | 47,518 |  |  |  |
| Wind Capacity, MW | 20,364 |  |  |  |

| Fuel Type | Confidential Projects (MW) | Projects Under Full Study (MW) | Public Projects (MW) | Suspended Studies (MW) | Grand Total (MW) |
| --- | --- | --- | --- | --- | --- |
| Gas-AllOther |  |  | 90 |  | 8,248 |
| Gas-CombinedCycle |  |  | 6,068 |  | 14,613 |
| Total Gas | 10,408 | 6,295 | 6,158 |  | 22,861 |
| Nuclear |  |  |  |  |  |
| Coal |  | 850 | 1,165 |  | 2,015 |
| Wind | 2,411 | 13,564 | 4,389 | 200 | 20,564 |
| Solar | 800 | 514 | 50 |  | 1,364 |
| Biomass |  |  |  |  |  |
| Storage |  | 874 | 40 |  | 914 |
| Petroleum Coke |  |  |  |  |  |
| Grand Total | 13,619 | 22,097 | 11,802 | 200 | 47,718 |

County Location of Installed Generation and Interconnection Requests (all fuels)

## Projects with Interconnection Agreements

| Generation Interconnections as of March 31, 2013 |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| INR | Site Name |  | County | COD |  | Fuel | MW For Grid | Change from Last Report |
| 11INR0033 |  | Los Vientos | Cameron |  | Apr-13 | Wind | 400 |  |
| 09INR0001 |  | Sandy Creek 1 | McLennan |  | Apr-13 | Coal | 925 |  |
| 12INR0075 |  | Blue Summit Windfarm | Wilbarger |  | Apr-13 | Wind | 135 |  |
| 12INR0086 |  | WA Parish Addition | Fort Bend |  | Jun-13 | Gas | 90 | Date |
| 10INR0089 |  | Deepwater Energy Storage | Harris |  | Jul-13 | Storage | 40 |  |
| 13INR0058 |  | OCI Alamo 1 | Bexar |  | Nov-13 | Solar | 50 | Date |
| 11INR0013 |  | Goldthwaite Wind Energy | Mills |  | Dec-13 | Wind | 150 |  |
| 11INR0054 |  | Midway Farms Wind | San Patricio |  | Dec-13 | Wind | 161 |  |
| 12INR0034 |  | Stephens Ranch Wind Energy | Borden |  | Dec-13 | Wind | 378 |  |
| 14INR0030a2 |  | Panhandle Wind | Carson |  | Feb-14 | Wind | 322 | Date |
| 14INR0016 |  | Channel Energy Center CT | Harris |  | Jun-14 | Gas-CC | 190 |  |
| 14INR0015 |  | Deer Park Energy Center | Harris |  | Jun-14 | Gas-CC | 192 |  |
| 13INR0048 |  | Spinning Spur Wind Two | Oldham |  | Jun-14 | Wind | 161 | New |
| 14INR0012 |  | Miami Wind 1 Project | Gray |  | Jun-14 | Wind | 401 | New |
| 13INR0021 |  | Ferguson Replacement Project | Llano |  | Jul-14 | Gas-CC | 116 | Date |
| 10INR0021 |  | Panda Sherman Power | Grayson |  | Aug-14 | Gas-CC | 809 |  |
| 13INR0040 |  | Agrifos Steam Unit | Harris |  | Aug-14 | Gas | 0 |  |
| 11INR0050 |  | Moore Wind 1 | Crosby |  | Aug-14 | Wind | 149 |  |
| 13INR0010a |  | Mariah Wind | Parmer |  | Oct-14 | Wind | 200 |  |
| 14INR0023 |  | Longhorn Energy Center | Briscoe |  | Dec-14 | Wind | 361 |  |
| 13INR0005 |  | Conway Windfarm | Carson |  | Dec-14 | Wind | 600 |  |
| 06INR0022c |  | Penascal Wind Farm 3 | Kenedy |  | Dec-14 | Wind | 202 |  |
| 09INR0051 |  | Mesquite Creek | Borden |  | Mar-15 | Wind | 249 |  |
| 10INR0020a |  | Panda Temple Power | Bell |  | May-15 | Gas-CC | 809 | Date |
| 08INR0018 |  | Gunsight Mountain | Howard |  | Aug-15 | Wind | 120 |  |
| 13INR0010b |  | Mariah Wind | Parmer |  | Oct-15 | Wind | 200 |  |
| 13INR0023 |  | Texas Clean Energy Project | Ector |  | Jan-16 | Coal | 240 |  |
| 06INR0006 |  | Cobisa-Greenville | Hunt |  | May-16 | Gas-CC | 1,792 |  |
| 10INR0020b |  | Panda Temple Power | Bell |  | May-16 | Gas-CC | 780 |  |
| 10INR0022 |  | Pondera King Power Project | Harris |  | Jun-16 | Gas-CC | 1,380 |  |
| 13INR0010c |  | Mariah Wind | Parmer |  | Oct-16 | Wind | 200 |  |

## Generation Projects Undergoing Full Interconnection Studies with Confidentiality Waived by Developer

None

## Generation Projects Undergoing Full Interconnection Studies

| INR | County | Fuel | MW | COD |  | INR | County | Fuel | MW | COD |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 13INR0010d | Parmer | Wind | 200 | TBD |  | 13INR0010e | Parmer | Wind | 200 | TBD |
| 13INR0010f | Parmer | Wind | 200 | TBD |  | 13INR0060 | Hidalgo | Gas | 50 | Jun-13 |
| 13INR0055 | Zapata | Wind | 250 | Dec-13 |  | 13INR0046 | Limestone | Wind | 71 | Sep-13 |
| 09INR0073 | Scurry | Wind | 200 | Dec-13 |  | 11INR0094 | Kent | Solar | 100 | Oct-13 |
| 11INR0093 | San Patricio | Wind | 41 | Dec-13 |  | 13INR0052 | Starr | Wind | 200 | Dec-13 |
| 12INR0081a | Upton | Wind | 112 | Dec-13 |  | 13INR0006 | Gray | Wind | 750 | Jan-14 |
| 12INR0055 | Baylor | Wind | 40 | Jan-14 |  | 14INR0014 | Val Verde | Solar | 100 | Jan-14 |
| 13INR0045 | Castro | Wind | 288 | Jan-14 |  | 13INR0059 | Castro | Wind | 499 | Mar-14 |
| 14INR0039 | Ector | Gas | 450 | Mar-14 |  | 12INR0060 | Schleicher | Wind | 58 | Apr-14 |
| 11INR0062 | Nueces | Wind | 178 | Apr-14 |  | 14INR0024 | Kinney | Solar | 42 | Apr-14 |
| 14INR0013 | Cameron | Wind | 103 | Apr-14 |  | 08INR0019a | Gray | Wind | 250 | Jun-14 |
| 14INR0027 | Guadalupe | Gas | 471 | May-14 |  | 08INR0019c | Gray | Wind | 250 | Jun-14 |
| 13INR0057 | Archer | Wind | 65 | Jun-14 |  | 14INR0011 | Swisher | Gas | 270 | Jun-14 |
| 12INR0059 | Pecos | Solar | 50 | Jun-14 |  | 14INR0048 | Wilbarger | Wind | 114 | Jun-14 |
| 08INR0019b | Gray | Wind | 250 | Jun-14 |  | 14INR0040 | Hidalgo | Gas | 225 | Jun-14 |
| 13INR0026 | Oldham | Wind | 201 | Jun-14 |  | 11INR0057 | Cameron | Wind | 165 | Jun-14 |
| 14INR0031 | Harris | Gas | 270 | Jun-14 |  | 14INR0025 | Floyd | Wind | 500 | Jul-14 |
| 13INR0049 | Harris | Gas | 352 | Jun-14 |  | 13INR0020b | Glasscock | Wind | 150 | Sep-14 |
| 12INR0085 | Stonewall | Wind | 24 | Jul-14 |  | 12INR0042b | Deaf Smith | Wind | 135 | Sep-14 |
| 14INR0029 | Uvalde | Solar | 42 | Jul-14 |  | 12INR0070 | Knox | Wind | 300 | Oct-14 |
| 13INR0025 | Randall | Wind | 150 | Aug-14 |  | 13INR0036 | Hidalgo | Wind | 200 | Oct-14 |
| 12INR0042a | Deaf Smith | Wind | 265 | Sep-14 |  | 12INR0045 | Kleberg | Wind | 135 | Oct-14 |
| 14INR0032 | Randall | Wind | 501 | Sep-14 |  | 14INR0030b | Carson | Wind | 322 | Nov-14 |
| 13INR0031 | Travis | Solar | 30 | Oct-14 |  | 12INR0068 | Jim Hogg | Wind | 80 | Dec-14 |
| 13INR0050 | Comanche | Wind | 200 | Dec-14 |  | 12INR0002b | Briscoe | Wind | 200 | Dec-14 |
| 13INR0020a | Glasscock | Wind | 200 | Dec-14 |  | 11INR0082A | Val Verde | Wind | 50 | Dec-14 |
| 13INR0038 | Swisher | Wind | 300 | Dec-14 |  | 11INR0085 | Nolan | Wind | 106 | Dec-14 |
| 11INR0081 | Live Oak | Wind | 72 | Dec-14 |  | 10INR0085 | Ector | Solar | 57 | Dec-14 |
| 11INR0082B | Val Verde | Wind | 150 | Dec-14 |  | 14INR0028 | Live Oak | Wind | 300 | Dec-14 |
| 14INR0009 | Kent | Wind | 248 | Dec-14 |  | 12INR0079 | Kenedy | Wind | 200 | Dec-14 |
| 13INR0054 | Bee | Gas | 0 | Dec-14 |  | 14INR0020 | Floyd | Wind | 150 | Dec-14 |
| 14INR0033 | Armstrong | Wind | 500 | Dec-14 |  | 14INR0045 | Webb | Wind | 251 | Dec-14 |
| 11INR0079a | Clay | Wind | 200 | Dec-14 |  | 12INR0029 | Swisher | Wind | 500 | Dec-14 |
| 15INR0021 | Starr | Wind | 200 | Dec-14 |  | 13INR0056 | Scurry | Wind | 366 | Mar-15 |
| 14INR0049 | Jack | Wind | 102 | Dec-14 |  | 15INR0032 | Hale | Gas | 197 | Jun-15 |
| 10INR0009 | Castro | Wind | 300 | Mar-15 |  | 14INR0026 | Presidio | Solar | 28 | Sep-15 |
| 13INR0028 | Hale | Gas | 359 | Mar-15 |  | 15INR0014 | Matagorda | Gas | 280 | Oct-15 |
| 15INR0033 | Hale | Gas | 197 | Jun-15 |  | 14INR0030a1 | Carson | Wind | 322 | Nov-15 |
| 15INR0013 | Anderson | Gas | 324 | Oct-15 |  | 12INR0002a | Briscoe | Wind | 200 | Dec-15 |
| 11INR0065 | Nueces | Wind | 350 | Oct-15 |  | 12INR0002c | Briscoe | Wind | 350 | Dec-15 |
| 14INR0018 | Nolan | Solar | 35 | Dec-15 |  | 13INR0032 | Andrews | Solar | 30 | Dec-15 |
| 16INR0005 | Cameron | Gas | 871 | Apr-16 |  | 16INR0008 | Grimes | Gas | 687 | May-16 |
| 16INR0006 | Angelina | Gas | 785 | Jun-16 |  | 16INR0003 | Brazoria | Gas | 11 | Jun-16 |
| 16INR0004 | Cameron | Gas | 730 | Jun-16 |  | 12INR0018 | Gray | Wind | 500 | Mar-17 |
| 11INR0040 | freestone | Gas | 640 | Mar-18 |  | 14INR0003 | Nolan | Coal | 850 | Jun-19 |

Note:  Projects that are classified as “Cancelled” or “Suspended” are excluded from this table.

## Wind Generation Capacity Installed by Year

# Regional Planning Group Project Reviews

- Sharyland has submitted the Atlas-Driver Load Integration project, this is a Tier 2 project that is estimated to cost approximately $15.4 million. This project is currently under ERCOT independent review.

- American Electric Power Service Corporation (AEPSC) has submitted the Sinton-Beeville-Kenedy Area Improvements project to accommodate load additions due to Eagle Ford Shale development in South Texas.  This is a Tier 1 project that is estimated to cost $89.2 million. ERCOT has completed the independent review. This project was endorsed by the Board of Directors on March 19, 2013.

- LCRA TSC, Guadalupe Valley Electric Cooperative (GVEC), American Electric Power (AEP), and South Texas Electric Cooperative (STEC) have jointly submitted the Kenedy Switch to Nixon to Seguin Line Upgrade project. This is a Tier 1 project that is estimated to cost approximately $55.3 million. ERCOT has completed the independent review. This project was endorsed by the Board of Directors on March 19, 2013.

- Guadalupe Valley Electric Cooperative (GVEC) has submitted the McQueeney-SMI-Geronimo 69 kV to 138 kV rebuild project. This is a Tier 2 project that is estimated to cost approximately $8.1 million. This project is currently under ERCOT independent review.

- Oncor has submitted the Permian Basin to Culberson 138 kV line project. The project is estimated to cost approximately $73 million. The Permian Basin to Culberson 138 kV line project is classified as a Tier 3 project and the project has statisfied all the RPG comments. In accordance with Protocol Section 3.11.4.5, the Permian Basin to Culberson 138 kV line project has been reclassified as a “Tier 4 Neutral Project.”

- Oncor submitted the Hicks to Elizabeth Creek 138 kV line project. This is a Tier 2 project that is estimated to cost approximately $42 million. The proposed Hicks to Elizabeth Creek 138 kV line project was identified as a reliability project (needed in 2016) in the 2011 Five-Year Transmission Plan (5YTP). The 2011 5YTP will serve as an ERCOT independent review for this project. This project has completed the RPG review and ERCOT will now prepare the RPG acceptance letter.

- LCRA TSC has submitted the McNeil-Marshall Ford line upgrade (69 kV to 138 kV conversion) project. This is a Tier 3 project that is estimated to cost approximately $20 million. This project is under study mode.

- Oncor submitted the Permian Basin to Moss to Odessa EHV 345 kV project. This is a Tier 1 project that is estimated to cost approximately $75 million. This project is currently under ERCOT independent review.

- Oncor has submitted the Collin-Payne 138 kV rebuild project. This is a Tier 3 project that is estimated to cost approximately $20.6 million. This project has been submitted for RPG comments.

# Congestion Costs

Dollars shown in RUC Make Whole payment graph are of settlement quality.

RUC net Make Whole payment in $mm

Monthly Average LMP

Binding Constraints – Year to Date

| Contingency | Binding Element | Number of 5-min intervals | Shadow Price Range $/MWh | Estimated Congestion Rent $ (Shadow Price*Limit) | Transmission Project |
| --- | --- | --- | --- | --- | --- |
| Roanoke Switch - West Denton 345 kV & Roanoke Switch - Lewisville Switch 345 kV | Fort Worth - Teasley 138 kV | 2813 | 0 - 3500 | 16,898,845 | 14TPIT0047 |
| Golden Switch - Sun Switch 138 kV; or Sacroc - Sun Switch 138 kV; or Snyder - China Grove 138 kV | China Grove - Bluff Creek 138 kV | 386 | 0 - 3500 | 6,643,122 | 12TPIT0058, 13TPIT0098 |
| Graham SES - Long Creek 345 kV; or Temple Pecan Creek - Tradinghouse SES 345 kV & Temple Switch - Lake Creek SES 345 kV; or Comanche Switch - Brown Switch 345 kV | Brown Switch - Killen Switch 345 kV | 1032 | 0 - 324 | 3,758,199 |  |
| Morgan Creek SES 345/138 kV Autotransformer 2 | Morgan Creek SES 345/138 kV Autotransformer 4 | 36 | 165 - 4500 | 3,305,461 |  |
| Morgan Creek SES - China Grove 138 kV double-circuit | Morgan Creek SES 138/69 kV Autotransformer 3 | 158 | 0 - 2800 | 2,677,907 |  |
| Asphalt Mines - Odlaw Switch 138 kV | Hamilton Road - Marverick 138 kV | 2756 | 0 - 685 | 2,186,995 | 16TPIT0024 |
| Odessa North 138/69 kV Autotransformer; or West Over - Odessa 138 kV | Moss Switch - Amoco North Cowden Tap 138 kV | 138 | 0 - 3500 | 1,742,105 | 13TPIT0098, 13TPIT0093 |
| Gila - Hiway 138 kV; or Koch Up River - Gila 138 kV | Gila - Hiway 138 kV | 167 | 0 - 3500 | 1,627,455 |  |
| Fort Stockton Switch -Barrilla 138 kV | Fort Stockton Switch -Barrilla 69 kV | 1032 | 0 - 1819 | 1,573,775 |  |
| Base Case | West to North Stability | 314 | 0 - 60 | 1,514,938 | CREZ |

Binding Constraints – Mar 2013

| Contingency | Binding Element | Number of 5-min intervals | Shadow Price Range $/MWh | Estimated Congestion Rent $ (Shadow Price*Limit) | Transmission Project | Comments |
| --- | --- | --- | --- | --- | --- | --- |
| Roanoke Switch - West Denton 345 kV & Roanoke Switch - Lewisville Switch 345 kV | Fort Worth - Teasley 138 kV | 1711 | 0 - 3500 | 10,754,098 | 14TPIT0047 | Outage on Jim Christal to North Denton 138 kV |
| Golden Switch - Sun Switch 138 kV; or Sacroc - Sun Switch 138 kV; or Snyder - China Grove 138 kV | China Grove - Bluff Creek 138 kV | 208 | 0 - 3500 | 5,434,212 | 12TPIT0058, 13TPIT0098 | High wind and low loads |
| Morgan Creek SES 345/138 kV Autotransformer 2 | Morgan Creek SES 345/138 kV Autotransformer 4 | 36 | 165 - 4500 | 3,305,461 |  | Continuous outage on the Morgan Creek SES 345/138 kV autotransformer 1 |
| Graham SES - Long Creek 345 kV; or Temple Pecan Creek - Tradinghouse SES 345 kV & Temple Switch - Lake Creek SES 345 kV; or Comanche Switch - Brown Switch 345 kV | Brown Switch - Killen Switch 345 kV | 820 | 0 - 324 | 3,031,668 |  | High wind and low loads in west texas |
| Odessa North 138/69 kV Autotransformer; or West Over - Odessa 138 kV | Moss Switch - Amoco North Cowden Tap 138 kV | 130 | 0 - 3500 | 1,681,007 | 13TPIT0098, 13TPIT0093 | Outage on Odessa North to Odessa 138 kV line |
| Gila - Hiway 138 kV; or Koch Up River - Gila 138 kV | Gila - Hiway 138 kV | 167 | 0 - 3500 | 1,627,455 |  | Forced outage on Gila - Hiway 2 138 kV line |
| Asphalt Mines - Odlaw Switch 138 kV | Hamilton Road - Marverick 138 kV | 919 | 0 - 685 | 844,803 | 16TPIT0024 | High McCamey wind |
| Base Case | West to North Stability | 135 | 2 - 30 | 769,345 | CREZ | High wind |
| Pawnee Switch - Lon Hill 345kV; or Pelican - Lon Hill 138 Kv | Rinco - Airco 138 kV | 259 | 0 - 3500 | 624,834 | 08TPIT0131 | Outage on Coleto Creek to Lon Hill 345 kV line |
| Bosque Switch - Elm Mott 345 kV | Rogers Hill BEPC - Elm Mott 138 kV | 524 | 0 - 2541 | 568,196 |  | Outage on the Elm Mott to Tradinghouse 345 kV line |

# Wind Generation as a Percent of Load

One-hour average of total wind power output as a percentage of ERCOT load.

# Planning Model Activities

- The short term calendar of major planning model events follows:

  - Apr 2, 2013	Begin 14 Data Set A case build

  - Apr 12,2013	Begin 13DSA/DSB March TPIT updates

  - May 24,2013	Post 13DSA/DSB March TPIT cases

  - Jun 11-13, 2013 	SSWG Data Set A meeting in Taylor

  - Jul 5, 2013	Projected posting 14 Data Set A

- Status update on SCR760, Changes Needed for Information Model Manager and Topology Processor for Planning Models, which was approved by the ERCOT Board in March 2011.

  - Bundle 1 (Items 3, 7 and 8): In Production.

  - Bundle 2 (Items 2a, 4, 9):  In Production.

  - Bundle 3 (Item 5, 2b, 2c):  In Production

  - Bundle 4 (Items 1, 6):  SOW completed, vendor coding underway.  First sample version PSS/E 33 formatted raw file expected April 10th.  Expect to receive first release in April 19, 2013.

| SCR Sub Part | SCR Description | Status |
| --- | --- | --- |
| SCR760-1 | Upgrade to PSS/E v32 | Production |
| SCR760-2 | Distribution Capacitor banks | Production |
| SCR760-3 | Zero Impedance Line Ratings | Production |
| SCR760-4 | Associate Loads and Capacitor banks with the correct CNG | Production |
| SCR760-5 | Additional Transformer Data for Planning | Production |
| SCR760-6 | FACTS Devices | Planning |
| SCR760-7 | Assign valid PSSE IDs to Breakers/ Switches/ Series Devices | Production |
| SCR760-8 | Phase shift of Autos for short circuit studies | Production |
| SCR760-9 | Multisection Line Grouping | Production |

Table 1:  In the following table:

- Red will be used to show status of Not Submitted, meaning that the SCR sub part has not been submitted to Siemens as a Service Request.

- Yellow will indicate that the SCR sub part has been submitted.  The color will remain yellow and the status will change in order to Submitted, Planning (Requirements, SOW, Code Writing), Release (Siemens produces first code to test), and Testing (code has completed internal test and is moving through release management).

- Green will indicate that the code has been tested and installed on the machines that ERCOT uses to produce Topology Processor output for Planning and CRR.

# Other Notable Activities

- ERCOT has contracted with Siemens PTI to complete the missing and questionable data for the remaining Resource Asset Registration Forms (RARF) that are still incomplete.  During the course of this project, Siemens will work closely with ERCOT to contact Resource Entities and Transmission Service Providers to find the best source of data for the incomplete RARFs. Once the best source of data is found, that data will be provided to the resource owner for inclusion and submission of their RARF to ERCOT.  ERCOT will start providing monthly updates for the May ROS meeting.

- The Transmission Project and Information Tracking (TPIT) process  is being modified to use the Model On-Demand (MOD) database as the source for future TPIT workbook postings starting with the July TPIT posting, which will be produced using the current process and the new process.  Starting with the November 1 TPIT posting, the new process will be used.  New fields have been added to the MOD user interface to hold the additional TPIT information not currely in MOD.  ERCOT and the Steady State Working Group are populating the new fields from the March TPIT and working on formatting and grouping of the new fields in MOD.

- ERCOT has completed sensitivity analysis for the 2012 Five-Year Transmission Plan and the report is posted at the ERCOT POI.

- Work on the 2013 Regional Transmission Plan (formerly the Five-Year Transmission Plan) has begun.

- ERCOT is currently performing the study to analyze the system needs in the West Texas area due to oil and gas load growth. The steady-state base cases used for this study are posted at the ERCOT POI.

- ERCOT is preparing the report on the results of the Long-Term System Assessment and the improvements to the long-term study process as a result of the grant received from the Department of Energy.  The report is expected to be published in July.

- ERCOT has begun a study to plan the long-term transmission roadmap for the Panhandle Region.  With CREZ lines now extending the ERCOT transmission system into the area, ERCOT has received a significant amount of wind generation interconnection study activity in the Panhandle.  Currently, there are almost 2600 MW of wind generation with signed generation interconnection agreeements in the region with another approximately 2500 MW that have completed the full interconnection study phase of the process.  An additional approximately 5400 MW is in the advanced stages of the interconnection study process.