## CON51
|  | Script ID | CON51 |  | Power Point
|  | Script Name | TDSP and CR NAESB Connectivity Test
|  | Script Storyline | Test NAESB connectivity, exchange of 814_PC and 814_PD file. The 814 transactions will be created by each Trading Partners translator system and run through the translator to verify EDI enveloping between partners. TDSPs will schedule actual start dates with each CR. NOTE: If connectivity information changes after this script is completed, this script will need to be re-executed with all Trading Partners.
|  | Success Criteria | TDSP and CR successfully send and receive encrypted files.
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  | Operating Rule |  |  | TRACK | New CR/Bank Change/Change of Service Provider
Simulated Entity
Duns Number
Number of CR's
|  |  | ERCOT | TDSP
PreTest Setup
Checkpoint Date |  | Calendar | Sender | Receiver | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 01 | Pre-Day 1 | TDSP | CR | website | TW | TDSP completes Testing Worksheet on the Retail Testing Website.
| Day 2 | Pre-Day 1 | CR | TDSP | website | TW | CR completes Testing Worksheet on the Retail Testing Website.
| Day 3 | Pre-Day 1 | CR | TDSP | email | Encryption Keys | CR emails encryption keys to TDSP and schedules connectivity testing
| Day 4 | Pre-Day 1 | TDSP | CR | email | Encryption Keys | TDSP emails encryption keys to CR and schedules connectivity testing
| Day 5 | Pre-Day 1 | CR | TDSP | 814_PC | Encrypted File | CR sends an encrypted file containing the TX SET 814_PC X12 formatted file. CR emails TDSP results of successful posting from their NAESB log. TDSP will process file through translator and verify envelope set-up. No 997 FA is required.
|  | Pre-Day 1 | TDSP | CR | email | TDSP verification | TDSP verifies that the 814_PC was received via NAESB.
Day 6
|  | Pre-Day 1 | TDSP | CR | 814_PD | Encrypted File | TDSP sends an encrypted file containing the TX SET 814_PC X12 formatted file. TDSP emails CR results of successful posting from their NAESB log. CR will process file through translator and verify envelope set-up. No 997 FA is required.
Day 7
| Day 8 | Pre-Day 1 | CR | TDSP | email | CR verification | CR verifies that the 814_PD was received via NAESB.

## CON52
|  | Script ID | CON52 |  | Power Point
|  | Script Name | Penny Test
|  | Script Storyline | TDSP and CR exchange banking information using EFT template; CR instructs their bank to send $.01 to the TDSP's bank. TDSP confirms receipt. This script is not performed for CRs/TDSPs where money is being received in production. TDSPs require that they receive both the EFT template and/or W-9 forms before Day 01 of flight test. TDSPs will send an e-mail to each testing MP informing them of this requirement on Day 0 of each testi flight.
|  | Success Criteria | CR sends and TDSP receives $.01 through their banking institutions.
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  | Operating Rule |  |  | TRACK | New CR/Bank Change
Simulated Entity
Duns Number
Number of CR's
|  |  | TDSP | CR
PreTest Setup
Checkpoint Date |  | Calendar | Sender | Receiver | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
|  | Pre-Day 1 | CR | CR Bank | Establish | CR establishes banking relationship. | The CR MUST establish a banking relationship before the beginning of the Penny Test testing period.
| Day 01 | Pre-Day 1 | CR | TDSP | email/fax | TDSP and CR primary testing contacts to exchange banking information using the EFT template. Any specific requirements by either party for the transmission of this information such as "wet" signatures, letterhead, etc., shall be communicated at this time. | Payment Type (ACH or Wire). If ACH, type of ACH (CTX, CCD) Company Name, Bank Name, ABA Number, Account Number, Tax ID, Nr Refund Type (Check, ACH). Contact/Address info for refund.
| Day 2 | Pre-Day 1 | CR | CR Bank |  | CR sends instructions their bank to transfer $0.01 to TDSP by ACH or Wire transfer.
| Day 3 | Pre-Day 1 | CR | TDSP |  | CR's Bank initiates transfer via NACHA of $0.01 to TDSP bank. | A penny will be sent.
| Day 4 | Pre-Day 1 | TDSP | CR | email | TDSP notifies CR by email that $0.01 has been successfully received. | Email sent to primary testing contact.

## CON56
|  | Script ID | CON56 |  | Power Point
|  | Script Name | NAESB connectivity with ERCOT and CR
|  | Script Storyline | Test NAESB connectivity; successful exchange of standard X12-encrypted handshake files. Note: the 814_01 sent by the CR is sent with an incorrect value in the REF*SU segment of the transaction in order to force it to automatically create an outbound 814_02 in ERCOT's system.
|  | Success Criteria | CR and ERCOT successfully send and receive encrypted files.
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  | Operating Rule |  |  | TRACK | New CR/Change of Service Provider
Simulated Entity
Duns Number
|  | Number of CR's | 1
|  |  | ERCOT | CR
PreTest Setup
Checkpoint Date |  | Calendar | Sender | Receiver | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 01 | Pre-Day 1 | CR1 | ERCOT | website | TW | CR completes Testing Worksheet on the Retail Testing Website.
| Day 2 | Pre-Day 1 | ERCOT | CR1 | website | TW | ERCOT completes Testing Worksheet on the Retail Testing Website.
| Day 3 | Pre-Day 1 | ERCOT | CR1 | email | Encryption Keys | ERCOT emails public keys, username and password, and schedules test date to CR
| Day 4 | Pre-Day 1 | CR1 | ERCOT | email | Encryption Keys | CR emails public keys, username and password to ERCOT
| Day 5 | Pre-Day 1 | CR1 | ERCOT | 814_01 | encrypted file | CR sends an encrypted X12 formatted 814_01 file containing an ESI ID of "CONNECTIVITYTESTESIID" and a "REF*SU*I". CR emails ERCOT results of successful posting from their NAESB log.
|  | Pre-Day 1 | ERCOT | CR1 | email | ERCOT verification | ERCOT verifies that the EDI file was received and successfully decrypted via email.
Day 6
|  | Pre-Day 1 | ERCOT | CR1 | 814_02 | Encrypted file | ERCOT sends an encrypted X12 formatted 814_02 containing an ESI ID of "CONNECTIVITYTESTESIID". ERCOT emails CR successful NAESB response message
Day 7
| Day 8 | Pre-Day 1 | CR1 | ERCOT | email | CR verification | CR verifies that the EDI transaction was received and decrypted successfully.
|  | Pre-Day 1 | ERCOT | CR1 | email | ERCOT verification | ERCOT sends confirmation e-mail of successful completion of connectivity test.

## DOA01
|  | Script ID | DOA01 |  | Power Point
|  | Script Name | Denial of Access - Option 1 CR
|  | Script Storyline | TDSP sends an 867_03 that indicates it is unable to read the meter because it is locked inside the premise. The TDSP then sends a 650_04 to suspend delivery of service. The CR then creates a reconnect request with text instructions to the TDSP on how to resolve the DOA issue. The TDSP resolves DOA and reconnects the premise.
|  | Success Criteria | CR's can accept the 650_04 TDSP disconnect for DOA
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential | Single Non IDR | None | CR1 | No
|  | Operating Rule | 2006-691, 2006_702 |  | TRACK | New CR
Simulated Entity
Duns Number
|  | Number of CR's | 1
|  |  | ERCOT | TDSP | CR1
|  | Pretest Setup | None | Choose an ESI ID with on-cycle bills on Day 3. | None
Checkpoint Date |  | Calendar | Sender | Receiver | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
Day 01
Day 02
|  | Day 03 |  |  |  |  | Day 3 cycle Date | 1 | Read
Day 04
Day 05
| Day 1 | Day 06 | TDSP | ERCOT | 867_03 | REF~5I must be included REF02 = D6 ESN = 3 | Usage sent, Estimate Sequence Number = 3. Meter is inaccessible. | 1 |  |  | CR1
| Day 2 | Day 07 | ERCOT | CR1 | 867_03 | REF~5I must be included REF02 = D6 ESN = 3 | Usage sent, Estimate Sequence Number = 3. Meter is inaccessible. | 1 |  |  | CR1
| Day 3 | Day 08
Day 09
| Day 17 | Day 10 | TDSP | CR1 | 650_04 | BGN08 = S2 REF~5H = GA001 | TDSP suspends service due to lack of access to meter. | 1 |  |  | CR1
|  | Day 11 | CR1 | TDSP | 650_01 | REF~8X~RC004 | Requires text instructions in the MTX segment | 1 |  |  | CR1
|  | Day 12 | TDSP | CR1 | 650_02 | REF~8X~RC004 | TDSP reconnects service | 1 |  |  | CR1

## DOA02
|  | Script ID | DOA02 |  | Power Point
|  | Script Name | Denial of Access - Option 2 & 3 CRs
|  | Script Storyline | TDSP sends an 867_03 that indicates it is unable to read the meter because it is locked inside the premise. The TDSP then sends a 650_04 to suspend delivery of service. The customer contacts the TDSP and resolves the access issue. The TDSP sends 650_04 indicating that service has been reconnected.
|  | Success Criteria | CR's can accept the 650_04 TDSP disconnect for DOA
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential | Single Non IDR | None | CR1 | No
|  | Operating Rule | 2006-691, 2006_702 |  | TRACK | New CR
Simulated Entity
Duns Number
|  | Number of CR's | 1
|  |  | ERCOT | TDSP | CR1
|  | Pretest Setup | None | Choose an ESI ID with on-cycle bills on Day 3. | None
Checkpoint Date |  | Calendar | Sender | Receiver | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
Day 01
Day 02
|  | Day 03 |  |  |  |  | Day 3 cycle Date | 1 | Read
Day 04
Day 05
| Day 1 | Day 06 | TDSP | ERCOT | 867_03 | REF~5I must be included REF02 = D6 ESN = 3 | Usage sent, Estimate Sequence Number = 3. Meter is inaccessible. | 1 |  |  | CR1
| Day 2 | Day 07 | ERCOT | CR1 | 867_03 | REF~5I must be included REF02 = D6 ESN = 3 | Usage sent, Estimate Sequence Number = 3. Meter is inaccessible. | 1 |  |  | CR1
| Day 3 | Day 08
Day 09
| Day 17 | Day 10 | TDSP | CR1 | 650_04 | BGN08 = S2 REF~5H = GA001 | TDSP suspends service due to lack of access to meter. | 1 |  |  | CR1
Day 11
Day 12
|  | Day 13 | TDSP | CR1 | 650_04 | REF~5H~RC004 | TDSP reconnects service | 1 |  |  | CR1
Day 20

## SCR33
|  | Script ID | SCR33 |  | Power Point
|  | Script Name | Invoice and bank payment with remittance advice via bank or NAESB
|  | Script Storyline | TDSP sends four invoices. The amount of the original (00) invoice can be any amount since it will be nullified by the cancel (01) invoice. The total amount of the rebill (05) and tampering (A5) invoices should not exceed $50.00. CR initiates live payment through bank. Remittance advice may travel with payment via bank or separately (point-to-point) via NAESB. TDSP refunds the dollar amount to CR within 30 days of end of test. TDSPs will not send usage; therefore, CRs must create matching usage or by-pass this functionality. Two ESI IDs are used: ESI 1: Original invoice, cancel and rebill (Original is sent in one envelope and cancel rebill in another) ESI 2: Original invoice with stand alone tampering charge. NOTE: Nueces does not execute this script
|  | Success Criteria | TDSP sends invoices to CR. CR responds with correct bank payment and remittance advice. TDSP reconciles and refunds the payment. NOTE: 867 meter usage are not sent with this script. CR's will need to bypass any invoice/usage matching and process the 810's for payment.
|  | Premise Information | Class | Meter Type | CSA CR | CR of Record | Customer Owned Meter
|  |  | Residential | Single Non IDR | None | CR1 | No
|  | Operating Rule |  |  | TRACK | New CR
Simulated Entity
Duns Number
|  | Number of CR's | 1
|  |  | ERCOT | TDSP | CR1
|  | Pretest Setup | None | Exchange banking information | Exchange banking information CON52 (Penny Test) must be complete
Checkpoint Date |  | Calendar | Sender | Receiver | Transaction | Transaction Details | Notes | Lifecycle | Event | Evaluation | Associated CR
| Day 1 | Day 01 | TDSP | CR1 | 810_02 | BIG08 = 00 | TDSP sends original cycle bill. | 1
| Day 2 | Day 02 | TDSP | CR1 | 810_02 | BIG08 = 01 | TDSP sends cancel of original cycle bill. | 1
| Day 3 | Day 03 | TDSP | CR1 | 810_02 | BIG08 = 05 | TDSP sends rebill. | 1
| Day 4 | Day 04 | TDSP | CR1 | 810_02 | BIG07 = A5 BIG08 = 00 | TDSP sends stand alone tampering charge. | 1
| Day 7 | Day 05 | CR1 | TDSP | ACH Payment | ACH or Wire | CR sends payment instruction to the bank for ACH or Wire Transfer. | 1
|  |  | CR1 | TDSP | 820_02 | Remit all 4 invoices | Remittance advice is sent by CR to Bank for TDSP or via NAESB to TDSP. All four invoices must be referenced on the 820_02. | 1
| Day 8 | Day 06
|  | Day 07 | TDSP | CR1 | Reconcile | Reconciliation of Payment to 820 | TDSP reconciles remittance advice to invoices and trace number to Bank payment. | 1
| Day 15 | Day 08
| Day 16 | Day 09
| Day 20 | Day 10 | TDSP | CR1 | Refund | ACH or Check | TDSP refunds payment to CR1 | 1