## Slide 1
Project Update and Summary of Project Priority List (PPL) Activity to Date
April 18, 2013

## Slide 2: 2013 Project Update – Agenda
  Project Portfolio Update p. 3-6
    Recent and Upcoming Project Implementations
    2013 Release Targets
    2013 Project Spending Update
    2014 Release Targets
  Appendix
    Project Portfolio Gantt Chart p. 8-15
Location of Project Priority List (PPL): http://www.ercot.com/services/projects/index

## Slide 3: Upcoming Project Implementations
Off-Cycle Release (4/1/2013)
  NPRR463 – CRR Auction Structure Enhancements
Release 2 Go-Lives (4/22/2013 – 4/26/2013)
  NPRR456 – Clarification of Definition of Electrically Similar Settlement Points and Heuristic Pricing Posting
  TSAT Wind Model
Note: Projected Go-Live dates are subject to change. Please watch for market notices as the effective dates approach.

## Slide 4: 2013 Release Targets – Board-Approved NPRRs/SCRs/xGRRs
Release Approach | Release 1 2/2013 | Release 2 4/2013 | Release 3 6/2013 | Release 4 7/2013 | Release 5 9/2013 | Release 6 12/2013 | 2013 TBD
On-Cycle | NPRR260 NPRR313 NPRR322 NPRR377 NPRR397 NPRR407(a) NPRR464 NPRR469 SCR768 | NPRR456 | NPRR153 NPRR393 NOGRR093 NPRR481 | NPRR207 NPRR461 NPRR479 NPRR481 SCR773 | NPRR272 NPRR385 NPRR407(b) NPRR416 NPRR425 NPRR439 NPRR457 NOGRR101 SCR770 | NPRR210 NPRR240 NPRR327 NPRR419 NPRR476 NPRR492 NPRR520 NOGRR105 | NPRR493
Off-Cycle |  | NPRR463 | SCR760(d) |  |  |  | NPRR439
Counts Total = 37 | 9 | 2 | 5 | 4 | 8 | 8 | 1
Early April
None
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
(a), (b), etc. indicates multiple phases
Release targets are subject to change
Red Text: New additions and target release changes
Strike-Through Text: Previous target release changes
None
None
None
Late June
Moved to 2014
407(a) – MMS portion
407(b) – CRR portion
SCR760(d) – final phase

## Slide 5: 2013 Cash Flow Projection – Approved Projects

## Slide 6: 2014 Release Targets – Board-Approved NPRRs/SCRs/xGRRs
Release Approach | Release 1 TBD | Release 2 TBD | Release 3 TBD | Release 4 TBD | Release 5 TBD | Release 6 TBD | 2014 TBD
On-Cycle |  | NPRR484 SCR756(b) SCR769 SCR771 | NPRR256 NPRR439 | NOGRR084 |  |  | NPRR455 NPRR467 NPRR485 NPRR487 NPRR500 NPRR509 SCR772
Off-Cycle |  |  |  |  |  |  | NPRR419
Counts Total = 14 | 0 | 4 | 2 | 1 | 0 | 0 | 7
Early April
None
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
(a), (b), etc. indicates multiple phases
Release targets are subject to change
Red Text: New additions and target release changes
Strike-Through Text: Previous target release changes
None
None
None
Late June
2015
SCR756(b) – Remaining portions of SCR

## Slide 7: Business Integration Update – Appendix
  Appendix
    4/12/2013 Project Gantt
      In-flight items sorted by Project End Date
      “Not Started” items sorted by Project Start Date

## Slide 8
Project Portfolio Status – as of 4/12/2013

## Slide 9
Project Portfolio Status – as of 4/12/2013

## Slide 10
Project Portfolio Status – as of 4/12/2013

## Slide 11
Project Portfolio Status – as of 4/12/2013

## Slide 12
Project Portfolio Status – as of 4/12/2013

## Slide 13
Project Portfolio Status – as of 4/12/2013

## Slide 14
Project Portfolio Status – as of 4/12/2013

## Slide 15
Project Portfolio Status – as of 4/12/2013