## calendar (1)
Attachment 1 - Sharyland Transition to Competition - Transaction Timeline
|  |  | 2013 | [17 empty] | 2014
| August |  | September |  |  |  |  | October |  |  |  | November |  |  |  | December |  |  |  |  | January |  |  |  | February |  |  |  | March |  |  |  |  | April |  |  |  | May |  |  |  | June | July |  |  |  | August |  |  |  | September |  |  |  |  | October |  |  |  | November |  |  |  | December
| 19 | 26 | 2 | 9 | 16 | 23 | 30 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 1 | 8 | 15 | 22 | 29
Rate Case | Process Rate Case | [20 empty] | File Tariffs
Transfer Load from SPP to ERCOT | All load transferred from SPP to ERCOT by 12/31
Sharyland -Customer Education | Provide information on competition and notice of Mass Customer List | [21 empty] | Inform Customers of Default REPs if they do not select |  | Host meetings in each division to explain competition and transition | [12 empty] | Customers are transitioned to REPs on their normal scheduled MMRD, using MVIs. Goal is 100% reads. |  |  |  | Transition Complete by May 31
Sharyland - REP | [7 empty] | Finalize list of DRs (up to 15 for each rate class) | [9 empty] | Provide Mass Customer List to REPs | [16 empty] | 4/14-4/16: Assign ESI IDs that have not selected a CR to DR
Sharyland - Transactions |  |  | ESI ID info loaded via 814_20s | [8 empty] | 12 months of historical usage data for ESI IDs loaded | [12 empty] | Process CR transactions Sharyland will schedule requested MVI for MMRD | [10 empty] | Process DR MVIs 4/17 - 4/27 |  | Resume processing CR transactions starting 4/28
Competitive REPs (CRs) | [17 empty] | Receive Mass Customer List | [6 empty] | CRs submit MVI transactions 2/1 - 4/13 with a requested move in date on the May Meter Read Date (MMRD), which can't be more than 90 days before MMRD. | [11 empty] | CRs submitting MVI for MMRD +1 (April 28-May 31)
Default REPs (DR) | [7 empty] | List of DRs finalized (up to 15 for each rate class) | [9 empty] | Receive Mass Customer List | [16 empty] | Receive customer list and submit MVI transactions for assigned customers 4/16 - 4/25
ERCOT | [5 empty] | Sharyland ESI ID Information begins showing on TDSP extract | [18 empty] | Process CR transactions | [9 empty] | Process DR MVIs |  |  | DR Move In receives unexecutable (814_28). CR Move In +1 receives MMRD (CR Move In -1)
CR Transaction Hold | [34 empty] | CR Transaction Hold (April 14-27)