|  |  |  |  | System Planning |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Monthly Status Report April 2013 |  |  |
|  |  | Report Highlights |  |  |  |  |  |  |
|  | - ERCOT is currently tracking 159 active generation interconnection requests totaling over 48,000 MW. This includes almost 20,000 MW of wind generation. |  |  |  |  |  |  |  |
|  | - ERCOT is currently reviewing proposed transmission improvements with a total cost of $75 Million - Transmission Projects endorsed in 2013 total $349.8 Million - All projects (in engineering, routing, licensing and construction) total approximately $9.68 Billion. - Transmission Projects energized in 2013 total about $38.6 million. |  |  |  |  |  |  |  |

Table of Contents

1.	Generation Interconnection	1

1.1	Signed Generation Interconnection Agreements	1

1.2	New Generation Registering for Commercial Operations	1

1.3	Summary of Generation Interconnection Requests	1

1.4	Projects with Interconnection Agreements	4

1.5	Generation Projects Undergoing Full Interconnection Studies with Confidentiality Waived by Developer	4

1.6	Generation Projects Undergoing Full Interconnection Studies	5

1.7	Wind Generation Capacity Installed by Year	6

2.	Regional Planning Group Project Reviews	7

3.	Asynchronous Tie Interconnection	8

4.	Congestion Costs	9

5.	Wind Generation as a Percent of Load	12

6.	Planning Model Activities	13

7.	Other Notable Activities	14

# 1.	Generation Interconnection

Additional information regarding detailed generation interconnection and impact studies is contained in the “Generation Project Interconnection Information” folder in the “Operations and System Planning” area on the ERCOT website:  http://planning.ercot.com/login/login.

## Signed Generation Interconnection Agreements

13INR0028 – Antelope Station  –  364 MW of Gas in Hale County

11INR0079a – South Clay Wind Farm – 200 MW of Wind in Clay County

## New Generation Registering for Commercial Operations

None

The total installed wind capacity is now reported as 10,570 MW by the resource owners through the registration process. Capacity by North, South and West is 832 MW, 2,375 MW, and 7,363 MW respectively.  Eight-hundred fifty MW is able to switch between the West and South zones and is currently shown in the South zone.

## Summary of Generation Interconnection Requests

| GENERATION INTERCONNECTION REQUESTS CURRENTLY UNDER REVIEW |  |  |  |  |
| --- | --- | --- | --- | --- |
| Currently tracking 159 generation interconnection or change requests |  |  |  |  |
| As of April 30, 2013 |  |  |  | Total |
| Security Screening Study | 8 |  |  |  |
| SSS Completed | 26 |  |  |  |
| Full Interconnect Study | 83 |  |  |  |
| FIS Completed | 9 |  |  |  |
| Suspended Studies | 0 |  |  |  |
| Capacity of Suspended Study Projects | 0 |  |  |  |
| Interconnect Agreement Completed | 33 |  |  |  |
| Capacity under Interconnection Agreements | 12,815 |  |  |  |
| Capacity for Grid, MW | 48,148 |  |  |  |
| Wind Capacity, MW | 19,964 |  |  |  |

| Fuel Type | Confidential Projects (MW) | Projects Under Full Study (MW) | Public Projects (MW) | Suspended Studies (MW) | Grand Total (MW) |
| --- | --- | --- | --- | --- | --- |
| Gas-AllOther |  |  | 449 |  | 8,053 |
| Gas-CombinedCycle |  |  | 6,522 |  | 15,918 |
| Total Gas | 10,622 | 6,378 | 6,971 |  | 23,971 |
| Nuclear |  |  |  |  |  |
| Coal |  | 850 | 1,165 |  | 2,015 |
| Wind | 2,111 | 13,264 | 4,589 |  | 19,964 |
| Solar | 710 | 524 | 50 |  | 1,284 |
| Biomass |  |  |  |  |  |
| Storage |  | 874 | 40 |  | 914 |
| Petroleum Coke |  |  |  |  |  |
| Grand Total | 13,443 | 21,890 | 12,815 |  | 48,148 |

County Location of Installed Generation and Interconnection Requests (all fuels)

## Projects with Interconnection Agreements

| Generation Interconnections as of April 30, 2013 |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| INR | Site Name |  | County |  | COD |  | Fuel | MW For Grid | Change from Last Report |
| 12INR0075 |  | Blue Summit Windfarm |  | Wilbarger |  | May-13 | Wind | 135 | date |
| 11INR0033 |  | Los Vientos |  | Cameron |  | May-13 | Wind | 400 | date |
| 09INR0001 |  | Sandy Creek 1 |  | McLennan |  | May-13 | Coal | 925 | date |
| 12INR0086 |  | WA Parish Addition |  | Fort Bend |  | Jun-13 | Gas | 90 |  |
| 10INR0089 |  | Deepwater Energy Storage |  | Harris |  | Jul-13 | Storage | 40 |  |
| 13INR0058 |  | OCI Alamo 1 |  | Bexar |  | Nov-13 | Solar | 50 |  |
| 11INR0013 |  | Goldthwaite Wind Energy |  | Mills |  | Dec-13 | Wind | 150 |  |
| 12INR0034 |  | Stephens Ranch Wind Energy |  | Borden |  | Dec-13 | Wind | 378 |  |
| 14INR0030a2 |  | Panhandle Wind |  | Carson |  | Feb-14 | Wind | 322 |  |
| 13INR0048 |  | Spinning Spur Wind Two |  | Oldham |  | Jun-14 | Wind | 161 |  |
| 14INR0015 |  | Deer Park Energy Center |  | Harris |  | Jun-14 | Gas-CC | 192 |  |
| 14INR0016 |  | Channel Energy Center 138/345kV CT |  | Harris |  | Jun-14 | Gas-CC | 190 |  |
| 14INR0012 |  | Miami Wind 1 Project |  | Gray |  | Jun-14 | Wind | 401 |  |
| 10INR0021 |  | Panda Sherman Power |  | Grayson |  | Jun-14 | Gas-CC | 809 | date |
| 10INR0020a |  | Panda Temple Power |  | Bell |  | Jun-14 | Gas-CC | 809 | date |
| 13INR0021 |  | Ferguson Replacement Project |  | Llano |  | Jul-14 | Gas-CC | 570 |  |
| 13INR0040 |  | Agrifos Steam Unit |  | Harris |  | Aug-14 | Gas | 0 |  |
| 11INR0050 |  | Moore Wind 1 |  | Crosby |  | Aug-14 | Wind | 149 |  |
| 13INR0010a |  | Mariah Wind |  | Parmer |  | Oct-14 | Wind | 200 |  |
| 14INR0023 |  | Longhorn Energy Center |  | Briscoe |  | Dec-14 | Wind | 361 |  |
| 13INR0005 |  | Conway Windfarm |  | Carson |  | Dec-14 | Wind | 600 |  |
| 11INR0079a |  | South Clay Windfarm |  | Clay |  | Dec-14 | Wind | 200 | New |
| 06INR0022c |  | Penascal Wind Farm 3 |  | Kenedy |  | Dec-14 | Wind | 202 |  |
| 09INR0051 |  | Mesquite Creek |  | Borden |  | Mar-15 | Wind | 249 |  |
| 08INR0018 |  | Gunsight Mountain |  | Howard |  | Aug-15 | Wind | 120 |  |
| 13INR0010b |  | Mariah Wind |  | Parmer |  | Dec-15 | Wind | 200 | date |
| 13INR0023 |  | Texas Clean Energy Project |  | Ector |  | Jan-16 | Coal | 240 |  |
| 06INR0006 |  | Cobisa-Greenville |  | Hunt |  | May-16 | Gas-CC | 1,792 |  |
| 10INR0020b |  | Panda Temple Power |  | Bell |  | May-16 | Gas-CC | 780 |  |
| 13INR0028 |  | Antelope Station |  | Hale |  | Jun-16 | Gas | 359 | New |
| 10INR0022 |  | Pondera King Power Project |  | Harris |  | Jun-16 | Gas-CC | 1,380 |  |
| 13INR0010c |  | Mariah Wind |  | Parmer |  | Dec-16 | Wind | 200 | date |
| 11INR0054 |  | Midway Farms Wind |  | San Patricio |  | Oct-14 | Wind | 161 | date |

## Generation Projects Undergoing Full Interconnection Studies with Confidentiality Waived by Developer

| 14INR0040 | Redgate Power Plant | Hidalgo | Jun-14 | Gas | 225 | New |
| --- | --- | --- | --- | --- | --- | --- |

## Generation Projects Undergoing Full Interconnection Studies

| INR | County | Fuel | MW | COD |  | INR | County | Fuel | MW | COD |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 13DGR0001 | Presidio | Solar | 10 | Apr-13 |  | 13INR0060 | Hidalgo | Gas | 50 | Jun-13 |
| 13INR0046 | Limestone | Wind | 71 | Sep-13 |  | 11INR0094 | Kent | Solar | 100 | Oct-13 |
| 13INR0038 | Swisher | Wind | 300 | Dec-13 |  | 13INR0052 | Starr | Wind | 200 | Dec-13 |
| 13INR0055 | Zapata | Wind | 250 | Dec-13 |  | 13INR0056 | Scurry | Wind | 366 | Dec-13 |
| 12INR0068 | Jim Hogg | Wind | 80 | Dec-13 |  | 12INR0081a | Upton | Wind | 112 | Dec-13 |
| 14INR0014 | Val Verde | Solar | 100 | Jan-14 |  | 13INR0006 | Gray | Wind | 750 | Jan-14 |
| 12INR0055 | Baylor | Wind | 40 | Jan-14 |  | 14INR0059 | Kaufman | Gas | 52 | Feb-14 |
| 14INR0039 | Ector | Gas | 450 | Mar-14 |  | 13INR0059 | Castro | Wind | 499 | Mar-14 |
| 14INR0024 | Kinney | Solar | 42 | Apr-14 |  | 12INR0060 | Schleicher | Wind | 58 | Apr-14 |
| 14INR0013 | Cameron | Wind | 103 | Apr-14 |  | 11INR0062 | Nueces | Wind | 178 | Apr-14 |
| 14INR0027 | Guadalupe | Gas | 471 | May-14 |  | 14INR0031 | Harris | Gas | 270 | Jun-14 |
| 14INR0038 | Galveston | Gas | 390 | Jun-14 |  | 08INR0019a | Gray | Wind | 250 | Jun-14 |
| 08INR0019b | Gray | Wind | 250 | Jun-14 |  | 08INR0019c | Gray | Wind | 250 | Jun-14 |
| 11INR0057 | Cameron | Wind | 165 | Jun-14 |  | 13INR0026 | Oldham | Wind | 201 | Jun-14 |
| 13INR0057 | Archer | Wind | 65 | Jun-14 |  | 14INR0048 | Wilbarger | Wind | 114 | Jun-14 |
| 13INR0049 | Harris | Gas | 352 | Jun-14 |  | 14INR0040 | Hidalgo | Gas | 225 | Jun-14 |
| 12INR0059 | Pecos | Solar | 50 | Jun-14 |  | 14INR0029 | Uvalde | Solar | 42 | Jul-14 |
| 11INR0093 | San Patricio | Wind | 41 | Jul-14 |  | 12INR0085 | Stonewall | Wind | 24 | Jul-14 |
| 14INR0025 | Floyd | Wind | 500 | Jul-14 |  | 12INR0042a | Deaf Smith | Wind | 265 | Sep-14 |
| 12INR0042b | Deaf Smith | Wind | 135 | Sep-14 |  | 14INR0032 | Randall | Wind | 501 | Sep-14 |
| 12INR0070 | Knox | Wind | 300 | Oct-14 |  | 13INR0031 | Travis | Solar | 30 | Oct-14 |
| 12INR0045 | Kleberg | Wind | 135 | Oct-14 |  | 13INR0036 | Hidalgo | Wind | 200 | Oct-14 |
| 13INR0020a | Glasscock | Wind | 200 | Oct-14 |  | 13INR0020b | Glasscock | Wind | 150 | Oct-14 |
| 13INR0025 | Randall | Wind | 150 | Nov-14 |  | 14INR0030b | Carson | Wind | 322 | Nov-14 |
| 13INR0054 | Bee | Gas | 0 | Dec-14 |  | 10INR0085 | Ector | Solar | 57 | Dec-14 |
| 11INR0082A | Val Verde | Wind | 50 | Dec-14 |  | 11INR0082B | Val Verde | Wind | 150 | Dec-14 |
| 11INR0085 | Nolan | Wind | 106 | Dec-14 |  | 14INR0009 | Kent | Wind | 248 | Dec-14 |
| 13INR0050 | Comanche | Wind | 200 | Dec-14 |  | 14INR0028 | Live Oak | Wind | 300 | Dec-14 |
| 14INR0033 | Armstrong | Wind | 500 | Dec-14 |  | 11INR0081 | Live Oak | Wind | 72 | Dec-14 |
| 12INR0079 | Kenedy | Wind | 200 | Dec-14 |  | 13INR0045 | Castro | Wind | 288 | Dec-14 |
| 14INR0020 | Floyd | Wind | 150 | Dec-14 |  | 15INR0021 | Starr | Wind | 200 | Dec-14 |
| 13INR0010d | Parmer | Wind | 200 | Dec-14 |  | 14INR0045 | Webb | Wind | 251 | Dec-14 |
| 14INR0049 | Jack | Wind | 102 | Dec-14 |  | 14INR0055 | Mills | Wind | 101 | Dec-14 |
| 14INR0056 | Mills | Wind | 101 | Dec-14 |  | 14INR0057 | Erath | Wind | 48 | Dec-14 |
| 10INR0009 | Castro | Wind | 300 | Mar-15 |  | 15INR0032 | Hale | Gas | 197 | Jun-15 |
| 15INR0033 | Hale | Gas | 197 | Jun-15 |  | 14INR0026 | Presidio | Solar | 28 | Sep-15 |
| 15INR0013 | Anderson | Storage | 324 | Oct-15 |  | 15INR0014 | Matagorda | Storage | 280 | Oct-15 |
| 11INR0065 | Nueces | Wind | 350 | Oct-15 |  | 14INR0030a1 | Carson | Wind | 322 | Nov-15 |
| 14INR0018 | Nolan | Solar | 35 | Dec-15 |  | 13INR0032 | Andrews | Solar | 30 | Dec-15 |
| 13INR0010e | Parmer | Wind | 200 | Dec-15 |  | 12INR0002a | Briscoe | Wind | 200 | Dec-15 |
| 16INR0005 | Cameron | Gas | 871 | Apr-16 |  | 12INR0029 | Swisher | Wind | 500 | Dec-15 |
| 16INR0006 | Angelina | Gas | 785 | Jun-16 |  | 16INR0008 | Grimes | Gas | 687 | May-16 |
| 16INR0003 | Brazoria | Gas | 11 | Jun-16 |  | 16INR0004 | Cameron | Gas | 730 | Jun-16 |
| 12INR0002b | Briscoe | Wind | 200 | Dec-16 |  | 14INR0011 | Swisher | Storage | 270 | Jul-16 |
| 12INR0018 | Gray | Wind | 500 | Mar-17 |  | 13INR0010f | Parmer | Wind | 200 | Dec-16 |
| 14INR0003 | Nolan | Coal | 850 | Jun-19 |  | 11INR0040 | Freestone | Gas | 640 | Mar-18 |

## Wind Generation Capacity Installed by Year

# Regional Planning Group Project Reviews

- Sharyland submitted the Atlas-Driver Load Integration project, this is a Tier 2 project that is estimated to cost approximately $18.6 million. This project has completed the RPG review and ERCOT will now prepare the RPG acceptance letter.

- Guadalupe Valley Electric Cooperative (GVEC) submitted the McQueeney-SMI-Geronimo 69 kV to 138 kV rebuild project. This is a Tier 2 project that is estimated to cost approximately $8.1 million. This project has completed the RPG review and ERCOT has sent the RPG acceptance letter.

- LCRA TSC submitted the McNeil-Marshall Ford line upgrade (69 kV to 138 kV conversion) project. This is a Tier 3 project that is estimated to cost approximately $20 million. This project has completed the RPG review and ERCOT has sent the RPG acceptance letter.

- Oncor submitted the Permian Basin to Moss to Odessa EHV 345 kV project. This is a Tier 1 project that is estimated to cost approximately $75 million. This project is currently under ERCOT independent review.

- Oncor submitted the Collin-Payne 138 kV rebuild project. This is a Tier 3 project that is estimated to cost approximately $20.6 million. This project has completed the RPG review and ERCOT will now prepare the RPG acceptance letter.

# Asynchronous Tie Interconnection

| Project | Notification to ERCOT | Reliability Study | RPG Review | Interconnection Agreement | In-service Year |
| --- | --- | --- | --- | --- | --- |
| Railroad DC tie expansion (150 MW - CFE) |  |  |  |  | 2014 |
| Southern Cross HVDC (3000 MW - SERC) |  |  |  |  |  |
| Tres Amigas (1500 MW - SPP) |  |  |  |  |  |

Color Legend

|  | In progress |
| --- | --- |
|  | Complete |

# Congestion Costs

Dollars shown in RUC Make Whole payment graph are of settlement quality.

RUC net Make Whole payment in $mm

Monthly Average LMP

Binding Constraints – Year to Date

| Contingency | Binding Element | Number of 5-min intervals | Shadow Price Range $/MWh | Estimated Congestion Rent $ (Shadow Price*Limit) | Transmission Project |
| --- | --- | --- | --- | --- | --- |
| Roanoke Switch - West Denton 345 kV & Roanoke Switch - Lewisville Switch 345 kV; or West Denton - Roanoke Switch 345 kV; or West Denton - Rdwells 138 kV | Jim Cristal - North Denton 138kV | 1407 | 0 - 3500 | 18,679,874 | 14TPIT0047 |
| Roanoke Switch - West Denton 345 kV & Roanoke Switch - Lewisville Switch 345 kV | Fort Worth - Teasley 138 kV | 2813 | 0 - 3500 | 16,898,845 | 14TPIT0047 |
| Morgan Creek SES 345/138 kV Autotransformer 2 | Morgan Creek SES 345/138 kV Autotransformer 4 | 150 | 29 - 4500 | 12,952,199 |  |
| West Denton - Rdwells 138 kV | Teasley - Pockrus Substation 138 kV | 728 | 0 - 3500 | 10,220,099 | 14TPIT0047 |
| Golden Switch - Sun Switch 138 kV; or Sacroc - Sun Switch 138 kV; or Snyder - China Grove 138 kV | China Grove - Bluff Creek 138 kV | 412 | 0 - 3500 | 7,008,745 | 12TPIT0058, 13TPIT0098 |
| Odessa North 138/69 kV Autotransformer; or West Over - Odessa 138 kV | Moss Switch - Amoco North Cowden Tap 138 kV | 461 | 0 - 3500 | 6,513,247 | 13TPIT0098, 13TPIT0093 |
| Asphalt Mines - Odlaw Switch 138 kV | Hamilton Road - Marverick 138 kV | 4176 | 0 - 2905 | 4,447,166 | 16TPIT0024 |
| Graham SES - Long Creek 345 kV; or Temple Pecan Creek - Tradinghouse SES 345 kV & Temple Switch - Lake Creek SES 345 kV; or Comanche Switch - Brown Switch 345 kV | Brown Switch - Killen Switch 345 kV | 1035 | 0 - 393 | 3,759,548 |  |
| Morgan Creek SES - China Grove 138 kV double-circuit | Morgan Creek SES 138/69 kV Autotransformer 3 | 158 | 0 - 2800 | 2,677,907 |  |
| Base Case | West to North Stability | 481 | 0 - 60 | 2,624,519 | CREZ |

Binding Constraints – Apr 2013

| Contingency | Binding Element | Number of 5-min intervals | Shadow Price Range $/MWh | Estimated Congestion Rent $ (Shadow Price*Limit) | Transmission Project | Comments |
| --- | --- | --- | --- | --- | --- | --- |
| Roanoke Switch - West Denton 345 kV & Roanoke Switch - Lewisville Switch 345 kV ; or West Denton - Roanoke Switch 345 kV; or West Denton - Rdwells 138 kV | Jim Cristal - North Denton 138kV | 1046 | 0 - 3500 | 17,473,024 | 14TPIT0047 | Outage on Teasley Substation to Fort Worth Substation 138kV |
| West Denton - Rdwells 138 kV | Teasley - Pockrus Substation 138 kV | 728 | 0 - 3500 | 10,220,099 | 14TPIT0047 | Outage on Jim Crystal to West Denton 138kV |
| Morgan Creek SES 345/138 kV Autotransformer 2 | Morgan Creek SES 345/138 kV Autotransformer 4 | 95 high-side; and 19 low side | 29 - 4500 high side; and 186 - 3500 low side | 9,646,738 |  | Outage on Morgan Creek SES 345/138kV Autotransformer |
| Odessa North 138/69 kV Autotransformer; or West Over - Odessa 138 kV | Moss Switch - Amoco North Cowden Tap 138 kV | 323 | 0 - 3500 | 4,771,142 | 13TPIT0098, 13TPIT0093 | Outage on Odessa EHV Switch to Big Three Odessa Tap (BTHOT), BTHOT to Odessa Southwest and BTHOT to Nylon Switch 138 kV |
| Asphalt Mines - Odlaw Switch 138 kV | Hamilton Road - Marverick 138 kV | 1420 | 0 - 2905 | 2,260,171 | 16TPIT0024 | High wind leading to west – south transfers |
| Ajo - Rio Hondo 345 kV | North Edinburg - Lon Hill 345 kV | 8 | 4 - 4500 | 1,500,659 | 14TPIT0050 | Planned unit outages in the valley |
| California Creek - Paint Creek 138 kV; or Vernon 138/69 kV Autotransformer | Lake Pauline 138/69 kV Autotransformer | 2943 | 1 - 2800 | 1,115,603 |  | Outage on Salt Creek BEPC to Scurry Switch 138kV |
| Base Case | West to North Stability | 167 | 0 - 28 | 1,109,581 | CREZ | High wind |
| La Palma - Los Fresnos 138 kV | La Palma - Villa Cavazos 138 kV | 16 | 3500 - 3500 | 983,471 | 16TPIT0029, 16TPIT0030 | Outage on East Riohondo to Central Avenue Sub 138 kV |
| Singleton - Zenith 345 kV | Singleton - Tomball 345 kV | 199 | 0 - 2167 | 869,416 |  | Outage on Kuykendahl to King REIT 345 kV and Kuykendahl to Roans Prairie 345 kV |

# Wind Generation as a Percent of Load

One-hour average of total wind power output as a percentage of ERCOT load.

# Planning Model Activities

- The short term calendar of major planning model events follows:

  - Apr 2, 2013	Begin 14 Data Set A case build

  - Apr 12, 2013	Begin 13DSA/DSB March TPIT updates

  - May 24, 2013	Post 13DSA/DSB March TPIT cases

  - Jun 11-13, 2013	SSWG Data Set A meeting in Taylor

  - Jul 5, 2013	Projected posting 14 Data Set A

- Status update on SCR760, Changes Needed for Information Model Manager and Topology Processor for Planning Models, which was approved by the ERCOT Board in March 2011.

  - Bundle 1 (Items 3, 7 and 8): In Production.

  - Bundle 2 (Items 2a, 4, 9):  In Production.

  - Bundle 3 (Item 5, 2b, 2c):  In Production

  - Bundle 4 (Items 1, 6):  First vendor release arrived at ERCOT on April 19, 2013.  ERCOT is testing the release for both Planning and CRR environments.  Expected off-cycle release to the environments used to create the products used for production planned for July 2013.

| SCR Sub Part | SCR Description | Status |
| --- | --- | --- |
| SCR760-1 | Upgrade to PSS/E v32 | Production |
| SCR760-2 | Distribution Capacitor banks | Production |
| SCR760-3 | Zero Impedance Line Ratings | Production |
| SCR760-4 | Associate Loads and Capacitor banks with the correct CNG | Production |
| SCR760-5 | Additional Transformer Data for Planning | Production |
| SCR760-6 | FACTS Devices | Release |
| SCR760-7 | Assign valid PSSE IDs to Breakers/ Switches/ Series Devices | Production |
| SCR760-8 | Phase shift of Autos for short circuit studies | Production |
| SCR760-9 | Multisection Line Grouping | Production |

Table 1:  In the following table:

- Red will be used to show status of Not Submitted, meaning that the SCR sub part has not been submitted to Siemens as a Service Request.

- Yellow will indicate that the SCR sub part has been submitted.  The color will remain yellow and the status will change in order to Submitted, Planning (Requirements, SOW, Code Writing), Release (Siemens produces first code to test), and Testing (code has completed internal test and is moving through release management).

- Green will indicate that the code has been tested and installed on the machines that ERCOT uses to produce Topology Processor output for Planning and CRR.

# Other Notable Activities

- ERCOT has contracted with Siemens PTI to complete the missing and questionable data for the remaining Resource Asset Registration Forms (RARF) that are still incomplete.  ERCOT and Siemens are working together to gather a list of all missing and suspect data that will be used to create metrics and track progress on this project.  So far, this list contains 3,000 individual data elements that are missing or suspect from 84 individual RE having between 1 and 389 missing or suspect values of required data elements.  Four-hundred thirty units are included in the count.

- The Transmission Project and Information Tracking (TPIT) process  is being modified to use the Model On-Demand (MOD) database as the source for future TPIT workbook postings starting with the July TPIT posting, which will be produced using the current process and the new process.  Starting with the November 1 TPIT posting, the new process will be used.  New fields have been added to the MOD user interface to hold the additional TPIT information not currely in MOD.

- Work on the 2013 Regional Transmission Plan (formerly the Five-Year Transmission Plan) has begun.

- ERCOT is currently performing the study to analyze the system needs in the West Texas area due to oil and gas load growth. The steady-state base cases used for this study are posted at the ERCOT POI.

- ERCOT is preparing the report on the results of the Long-Term System Assessment and the improvements to the long-term study process as a result of the grant received from the Department of Energy.  The report is expected to be published in July.

- ERCOT has begun a study to plan the long-term transmission roadmap for the Panhandle Region.  With CREZ lines now extending the ERCOT transmission system into the area, ERCOT has received a significant amount of wind generation interconnection study activity in the Panhandle.  Currently, there are almost 2,600 MW of wind generation with signed generation interconnection agreeements in the region with another approximately 2,500 MW that have completed the full interconnection study phase of the process.  An additional approximately 5,400 MW is in the advanced stages of the interconnection study process.