Guiding Principles for ERCOT Project Prioritization – Draft

- Definitions of Key Prioritization Terms

- Project Priority List (PPL)

  - Master list of projects in the ERCOT queue

  - Posted on a monthly basis at: http://www.ercot.com/services/projects/index

- Project Category

  - Mechanism for grouping projects on the PPL

  - Each project on the PPL is assigned one of four Project Categories by ERCOT Business Integration:

    - Business Strategy - Projects supporting Revision Requests and ERCOT strategic efforts

    - Regulatory - Projects required by regulatory bodies (Texas Legislature, PUCT, etc.)

    - Efficiencies & Enhancements - Projects that enhance internal ERCOT operational efficiency

    - Technical Foundation - Projects supporting the ERCOT technology infrastructure

- Priority

  - Year in which work on a project is to begin

  - Approvals:

    - Revision Requests

      - Recommended by PRS and TAC per respective Protocol or Market Guide revision process

      - Approved by ERCOT Board

    - Internal ERCOT Projects

      - Approved by ERCOT Executive Review

      - If project budget exceeds $1M, ERCOT Board approval is required.

- Rank

  - Numeric value to indicate relative importance of projects in the same Project Category

  - When possible, assigned in increments of 10 to allow for future additions

  - Approvals are same as noted above for “Priority”

- Approach to Project Prioritization

- New Additions to the PPL

  - Consider qualitative and quantitative elements of the project:

    - Information from source document

      - Project description and assumptions

      - Business Case

    - Costs and benefits to Market Participants

    - Enhancements to market efficiency and/or reliability

      - Credit implications

    - Impact Analysis results

      - ERCOT implementation cost

      - Estimated delivery time

      - ERCOT staffing, system, business function and/or grid operation impacts

      - Alternatives for more efficient implementation

    - Other Considerations

      - Availability of acceptable interim alternatives or work-arounds

      - Potential gained savings and/or efficiencies by combining with similar projects

      - Impact on previously approved and prioritized Revision Requests

      - Potential for a phased implementation approach

  - Projects requested to be worked in a particular year without displacing current projects, should be ranked at the end of the project list for that particular year

  - Review “Not Started” projects on the PPL that impact similar major systems

    - Project Status = “Not Started”

    - Impact Systems = Major system impacted

  - Propose Rank based on relative importance with similar projects

    - Rankings indicate which projects ERCOT should try to initiate earlier

  - Proposed Priority and Rank included in TAC and Board voting materials

- Reprioritizing Projects on the PPL

  - Consider merits of previously approved, but not yet started, projects in relation to current priorities

  - Reprioritizing and re-ranking is recommended if a project is being moved between years (i.e. Priority is being changed)

  - Revised Priority and Rank noted in TAC and Board presentations

- Periodic Review of Upcoming Project Starts

- At its regularly scheduled meetings, PRS reviews the staging of the next three months of planned Revision Request projects

  - Opportunity for Market Participants to adjust Priority and/or Rank based on current priorities

  - Chance for ERCOT to present resource constraints and/or project dependencies and recommend changes to Priority and Rankings

- PRS may elect to reprioritize or re-rank projects on the PPL

  - See Section 2, Approach to Project Prioritization, above