## Slide 1
Project Update and Summary of Project Priority List (PPL) Activity to Date
June 6, 2013

## Slide 2: 2013 Project Update – Agenda
  Project Portfolio Update p. 3-7
    2013 Release Targets
    2013 Project Spending Update
    2014 Release Targets
    2014 Project Funding
    Project Update – NPRR484
  Appendix
    Project Portfolio Gantt Chart p. 9-17
Location of Project Priority List (PPL): http://www.ercot.com/services/projects/index

## Slide 3: 2013 Release Targets – Board-Approved NPRRs/SCRs/xGRRs
Release Approach | Release 1 2/11 – 2/15 | Release 2 4/22 – 4/26 | Release 3 6/10 – 6/14 | Release 4 7/29 – 8/2 | Release 5 9/23 – 9/27 | Release 6 12/9-12/13 | 2013 TBD
On-Cycle | NPRR260 NPRR313 NPRR322 NPRR377 NPRR397 NPRR407(a) NPRR464 NPRR469 SCR768 | NPRR456 | NPRR481 NPRR520(a) NOGRR093 | NPRR207 NPRR393 NPRR461 NPRR479 NPRR520(b) | NPRR272 NPRR385 NPRR416 NPRR425 NPRR457 NOGRR101 SCR770 | NPRR210 NPRR240 NPRR476 NPRR492 NOGRR105 | NPRR153 NPRR484(1a) NPRR493 NPRR495 NPRR514
Off-Cycle |  | NPRR463 | SCR773 | SCR760(d) |  |  | 
Counts Total = 38 | 9 | 2 | 4 | 6 | 7 | 5 | 5
Early April
None
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
(a), (b), etc. indicates multiple phases
Release targets are subject to change
Red Text: New additions and target release changes
Strike-Through Text: Previous target release changes
Late June
None
None
Late May
Moved to Future Years
NPRR407(a) – MMS portion
NPRR407(b) – CRR portion
NPRR484(1a) – initial CMM/CRR components
NPRR520(a) – MMS, MIS, CDR portions
NPRR520(b) – EMS, NMMS, ICCP portions
SCR760(d) – final phase
ü
ü
ü
ü

## Slide 4: 2013 Cash Flow Projection – 4/30/2013 – Approved Projects
ERCOT Board of Directors approved a project budget increase of $1M on 5/14/2013
Revised 2013 project budget is now $16M

## Slide 5: 2014 Release Targets – Board-Approved NPRRs/SCRs/xGRRs
Release Approach | Release 1 TBD | Release 2 TBD | Release 3 TBD | Release 4 TBD | Release 5 TBD | Release 6 TBD | 2014 TBD
On-Cycle |  | NPRR327 SCR756(b) SCR769 SCR771 | NPRR256 NPRR407(b) NPRR439 | NOGRR084 |  |  | NPRR455 NPRR467 NPRR484(1b) NPRR485 NPRR487 NPRR500 NPRR509 SCR772
Off-Cycle |  |  |  |  |  |  | NPRR419 NPRR484(2)
Counts Total = 18 | 0 | 4 | 3 | 1 | 0 | 0 | 10
Early April
None
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
(a), (b), etc. indicates multiple phases
Release targets are subject to change
Red Text: New additions and target release changes
Strike-Through Text: Previous target release changes
None
None
None
Late June
2015
NPRR484(Ph1b) – Remaining Phase 1 items
NPRR484(Ph2) – S&B portions
SCR756(b) – Remaining portions of SCR

## Slide 6: 2014 Project Funding
ERCOT’s 2014 budget filing was previewed at the May Board meeting
  July Board review and approval targeted
$25M is being requested for capital projects in 2014
  ~$30M current demand in 2014
  Growing demand for Technical Foundation efforts
Multi-Year PPL is being used to forecast projects expected in 2014
For Revision Requests that may be filed and approved over the next 18 months, ERCOT has forecasted $4M in PPL funding
  This is in addition to $1.5M forecasted for Revision Requests that are already Board approved or in the stakeholder process

## Slide 7: Project Update – NPRR484
The project for NPRR484 is in the planning stages and portions are planned for implementation as early as October 2013
As discussed at PRS, NPRR484 phases:
  Phase 1 includes the CRR and Credit changes to implement path-specific adders
    Where each CRR (bid or owned) carries a path credit adder based on historical DAM and CRR clearing prices
  Phase 2 deferred invoicing in 2015
ERCOT plans to deliver Phase 1 in two deliveries across 2013 and 2014
    Phase 1a include path-specific adders in CRR and Credit calculations
    Phase 1b to complete any refinements in prices and reporting as needed
Presented today at TAC since:
  Market collateral requirements would be potentially impacted in October
  Credit and collateral logic is complex and dependent on market paths and portfolio composition for each company
  Market calls for specific scope/details/examples will be planned to support market details and questions for project as early as July 2013

## Slide 8: Business Integration Update – Appendix
  Appendix
    5/17/2013 Project Gantt
      In-flight items sorted by Project End Date
      “Not Started” items sorted by Project Start Date

## Slide 9
Project Portfolio Status – as of 5/17/2013

## Slide 10
Project Portfolio Status – as of 5/17/2013

## Slide 11
Project Portfolio Status – as of 5/17/2013

## Slide 12
Project Portfolio Status – as of 5/17/2013

## Slide 13
Project Portfolio Status – as of 5/17/2013

## Slide 14
Project Portfolio Status – as of 5/17/2013

## Slide 15
Project Portfolio Status – as of 5/17/2013

## Slide 16
Project Portfolio Status – as of 5/17/2013

## Slide 17
Project Portfolio Status – as of 5/17/2013