## Slide 1: Change Control Request # 1 – Execution
PR096-01 Backup Software Strategy
Project Information/Description
Change Request Summary
Installation and testing of the ComVault backup software has been completed on schedule. The final go-live (cutover) milestone is to complete backup of the ISM database to tape.
This task could not be completed as planned because the regular monthly backup schedule was interrupted due to issues within the ISM database. A full ISM backup to disk did not complete on time for the regularly scheduled backup to tape to occur, thus delaying the ComVault go-live.
Scope Change:
None
Reason: N/A
Original Go-Live Date: 6/07/2013 New Date: 7/12/2013
Original Execution End Date: 7/10/2013 New Date: 8/14/2013
Reason:
The full backup of ISM to disk did not complete on time. A clean backup to disk is a prerequisite of the ISM tape backup.
None
Reason:
N/A
06/12/13
Scope change
PR sponsor signoff
Schedule change
Business owner signoff
Scope Change
Budget change
New baseline
Updated IA*
Executive Summary
X
X
X
X
*for budget change
Budget Change
Schedule Change
Scope Change
Source: (ERCOT)
Priority: 2013 Rank: 160
Reference: Technical Foundation
Project Description:
The project will migrate the management and control of the ISM database backups from the current Symantec NetBackup environment (per TB licensing model) to a new CommVault Backup infrastructure (per client licensing model) resulting in significant savings.
Exec Sponsor: J. Dreyer PR Sponsor: B. Hanley Bus Owner: T. Culley PM: D. DICarlo Product Mgr: T. Culley