## Slide 1: PR048-01 TSAT Wind Model Tollgate – Project Closed
  Exec. Sponsor: K. McIntyre Business Owner: B. Blevins
  Project Sponsor: D. Woodfin Project Manager: G. Raina
Deliverables | Met (Y/N) | Comments
Conversion of wind models in TSAT format | Y | 
Complete Conversion Report | Y | 
TSAT Release | Y | 
On site training | Y | 
Execution Phase Start Baseline: 8/16/12
Execution Phase Complete Baseline: 5/31/13
Execution Phase Complete Actual: 5/24/13
% Under: 2%
Reason: N/A
  Reason: Less defects than anticipated
Scope:
Total Project Budget Baseline: | $298,680
Final Actual Spend: | $275,604
Under: | $23,076
% Under: | 7.7
Schedule:
Budget:
Executive Review
Notes: Item Where content comes from
Scope project signoff document
Project Signoff Baseline PSR
Project Signoff Actual PSR
Total Baseline Budget PSR
Final Actual Spend project balance sheet/Lawson actuals

## Slide 2: PR048-01 TSAT Wind Model Tollgate – Project Closed Post-Project CBA Metrics
Project Description:
Cost or Benefit? | Description of Metric to be Measured | Cost/Benefit Estimate from CBA | Timeframe Expected to Realize Cost/Benefit | Add’l Info to Assist in Follow-Up Reporting
Cost | Project Cost (required) | $275,604 |  | 
Benefit | Improved Real-Time Situational Awareness | Non-monetary | 3 years | 
Benefit | Improved Outage impacts visibility on stability limits day ahead | Non-monetary | 3 years | 
Benefit | Improved Operating limits for Market operations | Cost avoidance | 3 years | $16m in potential congestion cost savings (may be backcast)
Benefit | Increased efficiencies | $20,000/yr | 1 year | B. Blevins: Based on CBA assumption that Planning does not need to perform offline studies to give to Operations Ops engineer does not need to maintain separate tools
Executive Review
Notes: Item Where content comes from
Scope project signoff document
Project Signoff Baseline PSR
Project Signoff Actual PSR
Total Baseline Budget PSR
Final Actual Spend project balance sheet/Lawson actuals

## Slide 3: Tollgate – Project Closed Lessons Learned Recap
PR048-01 TSAT Wind Model
What went well ? What processes worked well ? | Excellent Training from PowerTech to explain a bit on technology, implementation & how to test & use the new models. Working with Business closely & knowledge sharing during TSAT testing. Taking a Phased approach - EMS changes that were required for this TSAT wind model project (like WGR number of turbine info, Derating of Pmax, Reactive curve derations, etc.) were available by the time TSAT wind model was available for testing.
What went wrong ? What processes caused problems? | Vendor Testing Document & test results – This information was not available and we had to come up with test steps based on our understanding. This caused some problems during testing.
What would we do differently? What are some suggestions for improvement? | Better involvement from EMMS PS during initial discussions between Planning & Operation group. Set expectations early rather than on setting expectations during testing phase. Example is what is the Pass/Fail criteria, how many Wind Turbine models are required during testing phase and such.
High-Level Recap: Lessons Learned
Executive Review
Notes: Item Where content comes from
Scope project signoff document
Project Signoff Baseline PSR
Project Signoff Actual PSR
Total Baseline Budget PSR
Final Actual Spend project balance sheet/Lawson actuals