## Slide 1: Gate to Execution
Executive Review
Date
PR101-01 ENS Hardware Refresh
Exec Sponsor: J. Dreyer PR Sponsor: B. Hanley Bus Owner: J. Chambers PM: D. DiCarlo Product Mgr: M. Stewart
Project Information/Description
Source: ERCOT
Priority: 2013 Rank: 250
Project Description:
Replace and upgrade the 6 year old Emergency Notification System hardware and upgrade the software to the latest release
Project Deliverables
Purchase new physical hardware and the latest Communicator NXT software for the Emergency Notification System
Execution Start : 6/12/13
Execution End : 8/28/13
No issues have been identified at this time
Milestone Dates
06/12/13
Project Schedule
Resource Plan
Cash Flow
Updated CBA*
RFI/RFP/SOW*
Detailed Req
Conceptual Des
Security Req
Detailed Design*
Test Plan
Executive Summary/Comments
Milestone | Schedule Completion Date
Server Build Complete | 7/26/2013
ENS Software Configured | 8/2/2013
ENS System Refreshed (Bastrop) | 8/6/2013
ENS System Refreshed (Taylor) | 8/8/2013
Go Live | 8/8/2013
Existing System Decommissioned | 8/28/2013
Schedule
X
N/A
X
X
X
N/A
X
X
X
X
*if applicable
Budget
Issues/Actions
 | 2013 | Total
PPL Budget | $69,128 | $69,128
Budget Change Amount | ($5,724) | ($5,724)
Revised Project Budget | $63,404 | $63,404
Committed * | $2,520 | $2,520
Expected for Execution / Closing | $60,884 | $60,884
* Estimated cost from last available accounting posting |  | 

## Slide 2: PR101-01 ENS Hardware Refresh Resource Plan – Execution Phase
Executive Review
Date
06/12/13
Project: PR101-01 ENS Hardware Refresh |  |  | 2013 |  |  |  |  |  |  |  | 
Department Name | Dept | Supporting Team | Jun | Jul | Aug | Sep | Oct | Nov | Dec | 2013 Hours | Execution Total Hours
Internal Resources |  |  |  |  |  |  |  |  |  |  | 
System Engineering & Admin | 310 | Generic Internal Resource Dept310; | 5 | 40 | 5 | 0 | 0 | 0 | 0 | 50 | 50
Network & Deskside Services | 330 | Chambers Jason; Simmons Ken; Stewart Mike; | 0 | 20 | 65 | 0 | 0 | 0 | 0 | 85 | 85
Release Management | 385 | Toth Cathy; | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 10 | 10
Enterprise Information Management | 585 | Lavas Jamie; | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 5 | 5
External Resources |  |  |  |  |  |  |  |  |  |  | 
Business Integration Projects | 670 | DiCarlo Dan; | 20 | 20 | 20 | 5 | 0 | 0 | 0 | 65 | 65
Vendor Resources |  |  |  |  |  |  |  |  |  |  | 
Total Hours - Internal |  |  | 5 | 60 | 85 | 0 | 0 | 0 | 0 | 150 | 150
Total Hours - External |  |  | 20 | 20 | 20 | 5 | 0 | 0 | 0 | 65 | 65
Total Hours - External - Vendor |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Slide 3: PR101-01 ENS Hardware Refresh Cash Flow – Execution Phase
Executive Review
Date
06/12/13
 |  | Project Name: |  | PR101-01 ENS Hardware Refresh |  |  |  |  |  |  |  |  | 
 |  | ERCOT Project Sponsor: |  | Bryan Hanley |  |  |  |  |  |  |  |  | 
 |  | EROCT Project Manager: |  | Dan DiCarlo |  |  |  |  |  |  |  |  | 
 |  |  |  | Current Yr Committed to Date |  |  |  |  |  |  |  |  | 
 |  |  | Prior Yr Spend |  | 6 | 7 | 8 | 9 | 10 | 11 | 12 | Phase Total | Project Total
 |  | Cost Category |  |  | Jun-13 | Jul-13 | Aug-13 | Sep-13 | Oct-13 | Nov-13 | Dec-13 |  | 
10 |  | ERCOT Labor - Capital | 0.00 | 0.00 | 325 | 3,900 | 5,525 | 0 | 0 | 0 | 0 | 9,750 | 9,750.00
15 |  | ERCOT Labor - O&M | 0.00 | 0.00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.00
20 |  | Tools, Equip, Mtls. & Supplies | 0.00 | 0.00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.00
30 |  | Consultants & Contractors | 0.00 | 2,520.00 | 2,800 | 2,800 | 9,500 | 700 | 0 | 0 | 0 | 15,800 | 18,320.00
40 |  | SW Licenses | 0.00 | 0.00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.00
41 |  | HW Licenses | 0.00 | 0.00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.00
70 |  | Employee Expenses | 0.00 | 0.00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.00
100 |  | Other | 0.00 | 0.00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.00
200 |  | Hardware | 0.00 | 0.00 | 0 | 26,340 | 0 | 0 | 0 | 0 | 0 | 26,340 | 26,340.00
300 |  | Software | 0.00 | 0.00 | 0 | 8,402 | 0 | 0 | 0 | 0 | 0 | 8,402 | 8,402.00
205 |  | Direct Purchase Hardware (immediately in service) | 0.00 | 0.00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.00
305 |  | Direct Purchase Software (immediately in service) | 0.00 | 0.00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.00
 |  | Capital Project Cost | 0.00 | 2,520.00 | 3,125.00 | 41,442.00 | 15,025.00 | 700.00 | 0.00 | 0.00 | 0.00 | 60,292.00 | 62,812.00
80 |  | Monthly Debt Finance Charge | 0.00 | 0.00 | 18.82 | 156.96 | 207.04 | 209.37 | 0.00 | 0.00 | 0.00 | 592.19 | 592.19
 |  | Total Project Cost | 0.00 | 2,520.00 | 3,143.82 | 41,598.96 | 15,232.04 | 909.37 | 0.00 | 0.00 | 0.00 | 60,884.19 | 63,404.19

## Slide 4: PR101-01 ENS Hardware Refresh Ongoing Annual Cost – Execution Phase
Executive Review
Date
* Whole numbers only
 | Manager | Department | Yearly Incremental Staff Support Hours | Additional FTEs Required*
ERCOT Staffing Impacts |  |  |  | 
 |  |  | N/A | N/A
ERCOT Software Maintenance |  |  | Annual Cost | 
 | J. Chambers | 330 | $12,681 | None
ERCOT Hardware Maintenance |  |  | Annual Cost | 
 |  |  | N/A | N/A
Infrastructure Growth |  |  | Annual Growth | 
 |  |  | N/A | N/A
06/12/13