## Slide 1: Change Control Request #1 – Planning
Project Information/Description
Change Request Summary
Upgrade the hardware and install the latest synchrophasor software in iTest. The synchrophasor solution will provide additional data on the situational awareness of the grid. The data will also be supplied the TSP’s that provide PMU data.
Schedule change is due to additional time spent defining the scope and business requirements.
Scope change is due to the extra effort during requirements gathering to evaluate multiple redundant and non-redundant designs and align all stakeholders on the best solution.
Budget change is to pay an outstanding software maintenance fee to the vendor during planning. There is no change to the overall project budget as the software cost was already contained within the project budget.
Scope Change:
The upgraded hardware & software solution will not be redundant as defined in the original project charter.
Reason: The current state of the synchrophasor strategy does not warrant the additional software licensing costs for a redundant configuration.
Original Date: 6/19/2013 New Date: 7/17/2013
Reason: The scope definition and requirements definition took longer than expected. To ensure stakeholder alignment, we evaluated multiple redundant and non-redundant designs which required additional planning and meetings with the vendor.
Reason: The software vendor is owed maintenance fees for 2013 ; therefore, moving the budget software costs into planning.
06/12/13
Scope change
PR sponsor signoff
Schedule change
Business owner signoff
Budget change
New baseline
Updated IA*
Executive Summary
N/A
X
X
X
X
X
*for budget change; total budget unchanged
Budget Change
Schedule Change
Scope Change
Source: ERCOT
Priority: 2013 Rank: 205
Reference:
Project Description:
Upgrade the hardware and install the latest scynchrophasor software in iTest.
PR098-01 EPG Synchrophasor Upgrade
Exec Sponsor: K. McIntyre PR Sponsor: D. Woodfin Bus Owner: B. Blevins PM: D. DiCarlo Product Mgr: S. White

## Slide 2: PR098-01 EPG Synchrophasor Upgrade Resource Plan – Planning
06/12/13
Project: PR098-01 EPG Synchrophasor Upgrade |  |  |  | 2013 |  |  |  |  |  |  |  | 
Department Name | Dept | Supporting Team | Rate | Jun | Jul | Aug | Sep | Oct | Nov | Dec | 2013 Hours | Execution Total Hours
Internal Resources |  |  |  |  |  |  |  |  |  |  |  | 
General Counsel | 120 | Barden Christopher; | 65 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4
System Engineering & Admin | 310 | Castro Frank; | 65 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 20 | 20
Network & Deskside Services | 330 | Strauss Ken; | 65 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4
Database Administration | 360 | Dahl Steve; Pradhan Puskar; Culley Tyrone; | 65 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 12
Critical Infrastructure Security | 370 | Breed Ryan; Choy Jackson; Quintanilla Luis; | 65 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 16 | 16
Release Management | 385 | Wyatt Lynn; | 65 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4
IT Support Services | 390 | Ebbers Tim; | 65 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4
EMMS Production Support | 395 | Gajjela Venkat; Liu Wei; Staples Sinoun; | 65 | 30 | 15 | 0 | 0 | 0 | 0 | 0 | 45 | 45
Advanced Network Applications | 424 | Nuthalapati Sarma; | 65 | 30 | 25 | 0 | 0 | 0 | 0 | 0 | 55 | 55
Operations Engineering | 426 | Blevins Bill; | 65 | 15 | 5 | 0 | 0 | 0 | 0 | 0 | 20 | 20
Integrated Testing & Portfolio Mgmt | 640 | Tummala Ravi; | 65 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4
External Resources |  |  |  |  |  |  |  |  |  |  |  | 
Business Integration Projects | 670 | DiCarlo Dan; | 140 | 30 | 30 | 0 | 0 | 0 | 0 | 0 | 60 | 60
Vendor Resources |  |  |  |  |  |  |  |  |  |  |  | 
Total Hours - Internal |  |  |  | 125 | 63 | 0 | 0 | 0 | 0 | 0 | 188 | 188
Total Hours - External |  |  |  | 30 | 30 | 0 | 0 | 0 | 0 | 0 | 60 | 60
Total Hours - External - Vendor |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Slide 3: PR098-01 EPG Synchrophasor Upgrade Cash Flow – Planning
06/12/13
 |  | Project Name: |  | PR098-01 EPG Synchrophasor Upgrade |  |  |  |  |  |  |  |  | 
 |  | ERCOT Project Sponsor: |  | Dan Woodfin |  |  |  |  |  |  |  |  | 
 |  | EROCT Project Manager: |  | Dan DiCarlo |  |  |  |  |  |  |  |  | 
 |  |  |  | Current Yr Committed to Date |  |  |  |  |  |  |  |  | 
 |  |  | Prior Yr Spend |  | 6 | 7 | 8 | 9 | 10 | 11 | 12 | Phase | 2013 Planning Total
 |  | Cost Category |  |  | Jun-13 | Jul-13 | Aug-13 | Sep-13 | Oct-13 | Nov-13 | Dec-13 | Total | 
10 |  | ERCOT Labor - Capital | 0.00 | 0.00 | 8,125 | 4,095 | 0 | 0 | 0 | 0 | 0 | 12,220 | 12,220.00
15 |  | ERCOT Labor - O&M | 0.00 | 1,836.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.00
20 |  | Tools, Equip, Mtls. & Supplies | 0.00 | 0.00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.00
30 |  | Consultants & Contractors | 0.00 | 6,020.00 | 4,200 | 4,200 | 0 | 0 | 0 | 0 | 0 | 8,400 | 8,400.00
40 |  | SW Licenses | 0.00 | 0.00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.00
41 |  | HW Licenses | 0.00 | 0.00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.00
70 |  | Employee Expenses | 0.00 | 0.00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.00
100 |  | Other | 0.00 | 0.00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.00
200 |  | Hardware | 0.00 | 0.00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.00
300 |  | Software | 0.00 | 0.00 | 0 | 75,250 | 0 | 0 | 0 | 0 | 0 | 75,250 | 75,250.00
205 |  | Direct Purchase Hardware (immediately in service) | 0.00 | 0.00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.00
305 |  | Direct Purchase Software (immediately in service) | 0.00 | 0.00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.00
 |  | Capital Project Cost | 0.00 | 6,020.00 | 12,325.00 | 83,545.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 95,870.00 | 95,870.00
80 |  | Monthly Debt Finance Charge | 0.00 | 0.00 | 61.15 | 339.63 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 400.78 | 400.78
 |  | Total Project Cost | 0.00 | 7,856.25 | 12,386.15 | 83,884.63 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 96,270.78 | 96,270.78
1 |  | Contingency | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00