## -- CBA --
Cost Benefit Analysis Data Entry Worksheet
Description: | Emergency Notification System Hardware Refresh
Sponsor: | Jerry Dreyer | Phase: | Initiation | Estimator: | Jason Chambers
Benefits and Impacts
INVESTMENT: Is the project an investment in new capability or does it support the current architecture?
1 | Moves existing functionality from a system that will not be supported much longer onto new hardware
2 | Increased supportability and increased reliability from the new platform
3
4
5
6
7
8
9
10
11
12
13
14
15
Feasibility
REQUIREMENTS: How complex are the potential solutions?
Dependencies | This is a stand alone system with few integration points to other systems. Thus there are minimal dependencies to address.
Other 1 | No anticipated issues during the migration from the old system to the new. Downtime during the switchover can be coordinated with currently planned failovers. Regardless, downtime for the ENS system would be minimal.
Other 2
Other 3
Other 4
Other 5
Alternatives
Click here for ideas on alternatives… ---------------------------------------------------------------------------------->>>
1 | Continue to use the existing system after the vendor stops supporting it.
2
3
4
Assumptions
Click here for ideas on assumptions… ---------------------------------------------------------------------------------->>>
1 | Assumes that short periods of downtime will be acceptable to the ENS systems in Bastrop and Taylor to do the switchover. Only one city would be down at a time.
2
3
4
5
6
7
8
9
10
Total Cost | 97300 |  | Net (Cost) - Benefit ($) |  | -97000
Total Benefit |  |  | Cost Benefit Ratio |  | 0
Summary values are rounded to 2 significant digits.
ERCOT Cost and Benefit Detail | [15 empty] | OPTIONAL WORK AREA FOR CALCULATING STAFFING IMPACTS
ERCOT Internal Cost | Type | Year 0 | Year 1 | Year 2 | Year 3 |  |  |  | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 | Year 10 | Task / Item | Labor Cost ($/hour) | Expected Cost in Labor Hours Per Time Period | Total Labor Hours Per Year | Estimated Cost = Total Labor Hours * Labor Cost | Time Periods/Year
Implementation Cost | Project | 63404 | 0 | 0 | 0 |  | NPV = | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 65 | 0 | 0 | 0 | 240
[17 empty] | 65 | 0 | 0 | 0 | 240
Ongoing Cost (O&M) | Select type… | 0 | 0 | 0 | 0 |  | NPV = | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 65 | 0 | 0 | 0 | 240
Yearly Maint/Support | Other | 0 | 12680.8 | 12680.8 | 12680.8 |  | NPV = | 33895.9299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 65 | 0 | 0 | 0 | 240
| Select type… | 0 | 0 | 0 | 0 |  | NPV = | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 65 | 0 | 0 | 0 | 240
| Present Value of Internal ERCOT Cost: | 97299.9299 | [16 empty] | Total | 0
OPTIONAL WORK AREA FOR CALCULATING STAFFING IMPACTS
ERCOT Internal Benefit | Type | Year 0 | Year 1 | Year 2 | Year 3 | Likelihood |  |  | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 | Year 10 | Task / Item | Labor Cost ($/hour) | Reduction in Labor Hours Per Time Period | Total Labor Hours Per Year | Estimated Benefit = Total Labor Hours * Labor Cost | Time Periods/Year
Direct Cost Savings | Select type… |  |  |  |  | 100% | NPV = | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 65 | 0 | 0 | 0 | 240
Direct Cost Savings | Select type… | 0 | 0 | 0 | 0 | 100% | NPV = | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 65 | 0 | 0 | 0 | 240
Increased Efficiencies | Select type… | 0 | 0 | 0 | 0 | 100% | NPV = | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Total | 0
Increased Efficiencies | Select type… | 0 | 0 | 0 | 0 | 100% | NPV = | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | OPTIONAL WORK AREA FOR CALCULATING OTHER IMPACTS
Cost Avoidance | Select type… | 0 | 0 | 0 | 0 | 100% | NPV = | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
Cost Avoidance | Select type… | 0 | 0 | 0 | 0 | 100% | NPV = | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
| Present Value of Internal ERCOT Benefit: | 0 | [16 empty] | Total | 0
Market Cost and Benefit Detail | [15 empty] | OPTIONAL WORK AREA FOR CALCULATING MARKET STAFFING IMPACTS
Market Cost | Type | Year 0 | Year 1 | Year 2 | Year 3 |  |  |  | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 | Year 10 | Task / Item | Labor Cost ($/hour) | Reduction in Labor Hours Per Time Period | Total Labor Hours Per Year | Estimated Benefit = Total Labor Hours * Labor Cost | Time Periods/Year
Implementation Cost |  |  | 0 | 0 | 0 |  | NPV = | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 65 | 0 | 0 | 0 | 240
[17 empty] | 65 | 0 | 0 | 0 | 240
Ongoing Cost | Select type… |  |  | 0 | 0 |  | NPV = | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 65 | 0 | 0 | 0 | 240
| Select type… | 0 | 0 | 0 | 0 |  | NPV = | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 65 | 0 | 0 | 0 | 240
| Select type… | 0 | 0 | 0 | 0 |  | NPV = | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 65 | 0 | 0 | 0 | 240
| Present Value of Market Cost: | 0 | [16 empty] | Total | 0
OPTIONAL WORK AREA FOR CALCULATING OTHER IMPACTS
Market Benefit | Type | Year 0 | Year 1 | Year 2 | Year 3 | Likelihood |  |  | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 | Year 10 | Item | Comment |  |  | Amount
Direct Cost Savings | Select type… | 0 | 0 | 0 | 0 | 100% | NPV = | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
Direct Cost Savings | Select type… |  |  |  | 0 | 100% | NPV = | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
Increased Efficiencies | Select type… | 0 | 0 | 0 | 0 | 100% | NPV = | 0 | [11 empty] | 0
Increased Efficiencies | Select type… | 0 | 0 | 0 | 0 | 100% | NPV = | 0 | [11 empty] | 0
Cost Avoidance | Select type… | 0 | 0 | 0 | 0 | 100% | NPV = | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
Cost Avoidance | Select type… | 0 | 0 | 0 | 0 | 100% | NPV = | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
| Total Present Value of Market Benefit: | 0 | [16 empty] | Total | 0
Calculation Parameters
[16 empty] | Present Value Interest Rate: |  | 6%
Changing this parameter is not recommended
It is used to calculate present value of future cash flows
Benefit and Impact Prompts
GOVERNANCE: Is the project required to support a PUCT rulemaking or government requirement?
GOVERNANCE: Is the project required by a market or ERCOT committee?
GOVERNANCE: Will the project provide better information for management decision making?
RELIABILITY: Does the project improve the reliability of the grid?
RELIABILITY: Does the project improve the reliability of ERCOT's computing infrastructure?
RELIABILITY: Is there a significant operational need for the project?
SAFETY: Will the project enhance safety within ERCOT?
SECURITY: Is there a physical or cyber-security issue that is addressed by this effort?
SECURITY: Does the project address an audit finding?
SECURITY: Will the project decrease the chance of fraud or help protect sensitive data?
RISK REDUCTION: Does this reduce risk to ERCOT in some significant manner?
RESOURCES: Does the project reduce the number of resources needed to support current operations?
RESOURCES: Does the project deliver infrastructure components that are more efficient or more easily upgraded?
DATA MANAGEMENT: Does this improve the accuracy, timeliness and transparency of transactions or settlements?
DATA MANAGEMENT: Does this enhance or optimize our data storage capability?
DATA MANAGEMENT: Does this improve reporting capabilities (financial, operational, etc.)?
EFFICIENCY: Does the project improve the efficiency or effectiveness of ERCOT?
EFFICIENCY: Does the project automate, improve or streamline a necessary function?
INVESTMENT: Is the project an investment in new capability or does it support the current architecture?
OTHER: Are there other areas that will indirectly benefit from this project?
Feasibility Prompts
REQUIREMENTS: Are high level requirements clearly defined?
REQUIREMENTS: How complex are the potential solutions?
REQUIREMENTS: Does a required completion date make delivery more difficult?
DELIVERY: Can the project be broken down into smaller sections or delivered in stages to reduce risk?
DELIVERY: Will training be required as the project is rolled out?
DEPENDENCIES: Are there major dependencies on other projects that make this difficult to implement?
Alternative Prompts
DELIVERY: Is a manual workaround an option (short-term or long-term)?
DELIVERY: Does a partial implementation provide enough value to be worth considering?
DELIVERY: Should a phased implementation be considered to reduce risk or accelerate key benefits?
DELIVERY: If this is an automation project is it reasonable to consider using the current process?
Assumption Prompts
DEPENDENCIES: Is this request is dependent on another ERCOT project (either active or planned)?
DELIVERABLES: Are specific key deliverables required from this project?
DELIVERABLES: What is the useful life of the deliverables of this project?
RESOURCES: Are computing resources assumed that are not to be delivered by this project?
RESOURCES: Are specific key resources assumed to be available for this project?
RESOURCES: Are there facilities requirements necessary for this project?
REQUIREMENTS: Is completion required by a specific date?