|  |  |  |  | System Planning |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Monthly Status Report May 2013 |  |  |
|  |  | Report Highlights |  |  |  |  |  |  |
|  | - ERCOT is currently tracking 158 active generation interconnection requests totaling over 48,000 MW. This includes over 20,000 MW of wind generation. |  |  |  |  |  |  |  |
|  | - ERCOT is currently reviewing proposed transmission improvements with a total cost of $81.2 Million - Transmission Projects endorsed in 2013 total $349.8 Million - All projects (in engineering, routing, licensing and construction) total approximately $9.68 Billion. - Transmission Projects energized in 2013 total about $38.6 million. |  |  |  |  |  |  |  |

Table of Contents

1.	Generation Interconnection	1

1.1	Signed Generation Interconnection Agreements	1

1.2	New Generation Registering for Commercial Operations	1

1.3	Summary of Generation Interconnection Requests	1

1.4	Projects with Interconnection Agreements	4

1.5	Generation Projects Undergoing Full Interconnection Studies with Confidentiality Waived by Developer	4

1.6	Generation Projects Undergoing Full Interconnection Studies	5

1.7	Wind Generation Capacity Installed by Year	6

2.	Regional Planning Group Project Reviews	7

3.	Asynchronous Tie Interconnection	8

4.	Congestion Costs	9

5.	Wind Generation as a Percent of Load	12

6.	Planning Model Activities	13

7.	Other Notable Activities	14

# 1.	Generation Interconnection

Additional information regarding detailed generation interconnection and impact studies is contained in the “Generation Project Interconnection Information” folder in the “Operations and System Planning” area on the ERCOT website:  http://planning.ercot.com/login/login.

## Signed Generation Interconnection Agreements

11INR0094 – White Camp Solar  –  100 MW of Solar in Kent County

## New Generation Registering for Commercial Operations

None

The total installed wind capacity is now reported as 10,570 MW by the resource owners through the registration process. Capacity by North, South and West is 832 MW, 2,375 MW, and 7,363 MW respectively.  Eight-hundred fifty MW is able to switch between the West and South zones and is currently shown in the South zone.

## Summary of Generation Interconnection Requests

County Location of Installed Generation and Interconnection Requests (all fuels)

## Projects with Interconnection Agreements

| Generation Interconnections as of May 30, 2013 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| INR | Site Name | County | COD | Fuel | MW For Grid | Change from Last Report |
| 09INR0001 | Sandy Creek 1 | McLennan | Jun-13 | Coal | 925 | date |
| 12INR0075 | Blue Summit Windfarm | Wilbarger | Jun-13 | Wind | 135 | date |
| 11INR0033 | Los Vientos | Cameron | Jun-13 | Wind | 400 | date |
| 12INR0086 | WA Parish Addition | Fort Bend | Jun-13 | Gas | 90 |  |
| 10INR0089 | Deepwater Energy Storage | Harris | Jul-13 | Storage | 40 |  |
| 13INR0058 | OCI Alamo 1 | Bexar | Oct-13 | Solar | 50 | date |
| 11INR0094 | White Camp Solar | Kent | Nov-13 | Solar | 100 | New |
| 11INR0013 | Goldthwaite Wind Energy | Mills | Dec-13 | Wind | 150 |  |
| 11INR0054 | Midway Farms Wind | San Patricio | Dec-13 | Wind | 161 | date |
| 12INR0034 | Stephens Ranch Wind Energy | Borden | Dec-13 | Wind | 378 |  |
| 14INR0012 | Miami Wind 1 Project | Gray | May-14 | Wind | 401 | date |
| 13INR0048 | Spinning Spur Wind Two | Oldham | Jun-14 | Wind | 161 |  |
| 14INR0015 | Deer Park Energy Center | Harris | Jun-14 | Gas | 192 |  |
| 14INR0016 | Channel Energy Center 138/345kV CT | Harris | Jun-14 | Gas | 190 |  |
| 13INR0021 | Ferguson Replacement Project | Llano | Jul-14 | Gas | 570 | date |
| 14INR0030a2 | Panhandle Wind | Carson | Aug-14 | Wind | 322 | date |
| 10INR0021 | Panda Sherman Power | Grayson | Jun-14 | Gas | 809 | date |
| 13INR0040 | Agrifos Steam Unit | Harris | Aug-14 | Gas | 0 |  |
| 11INR0050 | Moore Wind 1 | Crosby | Aug-14 | Wind | 149 |  |
| 13INR0010a | Mariah Wind | Parmer | Oct-14 | Wind | 200 |  |
| 14INR0023 | Longhorn Energy Center | Briscoe | Dec-14 | Wind | 361 |  |
| 13INR0005 | Conway Windfarm | Carson | Dec-14 | Wind | 600 |  |
| 11INR0079a | South Clay Windfarm | Clay | Dec-14 | Wind | 200 |  |
| 06INR0022c | Penascal Wind Farm 3 | Kenedy | Dec-14 | Wind | 202 |  |
| 13INR0010c | Mariah Wind | Parmer | Jan-15 | Wind | 200 | date |
| 09INR0051 | Mesquite Creek | Borden | Mar-15 | Wind | 249 |  |
| 10INR0020a | Panda Temple Power | Bell | Jun-14 | Gas | 809 | date |
| 08INR0018 | Gunsight Mountain | Howard | Aug-15 | Wind | 120 |  |
| 13INR0010b | Mariah Wind | Parmer | Dec-15 | Wind | 200 |  |
| 13INR0023 | Texas Clean Energy Project | Ector | Jan-16 | Coal | 240 |  |
| 06INR0006 | Cobisa-Greenville | Hunt | May-16 | Gas | 1,792 |  |
| 10INR0020b | Panda Temple Power | Bell | Aug-15 | Gas | 780 |  |
| 13INR0028 | Antelope Station | Hale | Jun-16 | Gas | 359 |  |
| 10INR0022 | Pondera King Power Project | Harris | Dec-16 | Gas | 1,380 |  |

## Generation Projects Undergoing Full Interconnection Studies with Confidentiality Waived by Developer

| INR | Site Name | County | COD | Fuel | MW for Grid | Change from Last Report |
| --- | --- | --- | --- | --- | --- | --- |
| 14INR0040 | Redgate Power Plant | Hidalgo | Jun-14 | Gas | 225 |  |

## Generation Projects Undergoing Full Interconnection Studies

| INR | County | Fuel | MW | COD |  | INR | County | Fuel | MW | COD |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 14INR0059 | Kaufman | Gas | 52 | 2/1/2014 |  | 14INR0060 | Haskell | Wind | 400 | 8/1/2014 |
| 14INR0048 | Wilbarger | Wind | 114 | 6/1/2014 |  | 13INR0020b | Glasscock | Wind | 150 | 9/1/2014 |
| 13INR0010f | Parmer | Wind | 200 | 1/31/2013 |  | 14INR0032 | Randall | Wind | 501 | 9/1/2014 |
| 14INR0011 | Swisher | Storage | 270 | 6/1/2014 |  | 14INR0042 | Deaf Smith | Solar | 80 | 9/30/2014 |
| 13INR0010e | Parmer | Wind | 200 | 1/31/2013 |  | 14INR0047 | Dickens | Wind | 301 | 10/1/2014 |
| 12INR0002a | Briscoe | Wind | 200 | 12/1/2013 |  | 12INR0070 | Knox | Wind | 300 | 10/15/2014 |
| 14INR0026 | Presidio | Solar | 28 | 7/1/2014 |  | 13INR0031 | Travis | Solar | 30 | 10/31/2014 |
| 13INR0010d | Parmer | Wind | 200 | 1/31/2013 |  | 14INR0030b | Carson | Wind | 322 | 11/1/2014 |
| 13INR0045 | Castro | Wind | 288 | 1/1/2014 |  | 10INR0085 | Ector | Solar | 56.5 | 12/1/2014 |
| 13INR0050 | Comanche | Wind | 200 | 12/1/2013 |  | 11INR0081 | Live Oak | Wind | 72 | 12/1/2014 |
| 13INR0025 | Randall | Wind | 150 | 9/1/2013 |  | 11INR0082A | Val Verde | Wind | 50 | 12/1/2014 |
| 12INR0045 | Kleberg | Wind | 135 | 3/31/2012 |  | 11INR0082B | Val Verde | Wind | 150 | 12/1/2014 |
| 13INR0020a | Glasscock | Wind | 200 | 5/1/2013 |  | 11INR0085 | Nolan | Wind | 106 | 12/1/2014 |
| 13INR0036 | Hidalgo | Wind | 200 | 12/1/2013 |  | 12INR0002b | Briscoe | Wind | 200 | 12/1/2014 |
| 11INR0093 | San Patricio | Wind | 41 | 12/31/2013 |  | 13INR0054 | Bee | Gas | 0 | 12/1/2014 |
| 12INR0085 | Stonewall | Wind | 24 | 7/1/2014 |  | 14INR0009 | Kent | Wind | 248 | 12/1/2014 |
| 14INR0025 | Floyd | Wind | 500 | 7/1/2014 |  | 14INR0028 | Live Oak | Wind | 300 | 12/1/2014 |
| 14INR0029 | Uvalde | Solar | 42 | 7/1/2014 |  | 14INR0033 | Armstrong | Wind | 500 | 12/1/2014 |
| 12INR0059 | Pecos | Solar | 50 | 12/1/2012 |  | 14INR0043 | Sterling | Solar | 40 | 12/1/2014 |
| 14INR0040 | Hidalgo | Gas | 225 | 6/7/2014 |  | 12INR0079 | Kenedy | Wind | 200 | 12/15/2014 |
| 13INR0057 | Archer | Wind | 65 | 6/1/2013 |  | 12INR0029 | Swisher | Wind | 500 | 12/31/2014 |
| 11INR0057 | Cameron | Wind | 165 | 12/31/2013 |  | 14INR0020 | Floyd | Wind | 150 | 12/31/2014 |
| 08INR0019a | Gray | Wind | 250 | 6/1/2014 |  | 14INR0045a | Webb | Wind | 502 | 12/31/2014 |
| 08INR0019b | Gray | Wind | 250 | 6/1/2014 |  | 14INR0049 | Jack | Wind | 102 | 12/31/2014 |
| 08INR0019c | Gray | Wind | 250 | 6/1/2014 |  | 14INR0056 | Mills | Wind | 101 | 12/31/2014 |
| 13INR0049 | Harris | Gas | 352 | 6/1/2014 |  | 14INR0057 | Erath | Wind | 48 | 12/31/2014 |
| 14INR0031 | Harris | Gas | 270 | 6/1/2014 |  | 15INR0021 | Starr | Wind | 200 | 12/31/2014 |
| 14INR0038 | Galveston | Gas | 390 | 6/1/2014 |  | 10INR0009 | Castro | Wind | 300 | 3/31/2015 |
| 14INR0027 | Guadalupe | Gas | 471 | 5/1/2014 |  | 15INR0032 | Hale | Gas | 197 | 6/1/2015 |
| 11INR0062 | Nueces | Wind | 178 | 12/1/2013 |  | 15INR0033 | Hale | Gas | 197 | 6/1/2015 |
| 12INR0060 | Schleicher | Wind | 58 | 4/1/2014 |  | 15INR0013 | Anderson | Storage | 324 | 10/1/2015 |
| 14INR0039 | Ector | Gas | 450 | 3/1/2014 |  | 15INR0014 | Matagorda | Storage | 280 | 10/1/2015 |
| 12INR0055 | Baylor | Wind | 40 | 1/1/2014 |  | 11INR0065 | Nueces | Wind | 350 | 10/31/2015 |
| 13INR0006 | Gray | Wind | 750 | 1/1/2014 |  | 14INR0030a1 | Carson | Wind | 322 | 11/1/2015 |
| 14INR0014 | Val Verde | Solar | 100 | 1/1/2014 |  | 14INR0018 | Nolan | Solar | 35 | 12/1/2015 |
| 14INR0013 | Cameron | Wind | 103 | 4/1/2014 |  | 12INR0018 | Gray | Wind | 500 | 12/31/2015 |
| 12INR0068 | Jim Hogg | Wind | 80 | 12/31/2013 |  | 13INR0032 | Andrews | Solar | 30 | 12/31/2015 |
| 12INR0081a | Upton | Wind | 112 | 12/31/2013 |  | 14INR0045b | Webb | Wind | 251 | 12/31/2015 |
| 14INR0024 | Kinney | Solar | 42 | 4/1/2014 |  | 16INR0005 | Cameron | Gas | 871 | 4/1/2016 |
| 13INR0038 | Swisher | Wind | 300 | 12/1/2013 |  | 16INR0008 | Grimes | Gas | 687 | 5/1/2016 |
| 13INR0052 | Starr | Wind | 200 | 12/1/2013 |  | 16INR0003 | Brazoria | Gas | 11 | 6/1/2016 |
| 13INR0056 | Scurry | Wind | 366 | 12/1/2013 |  | 16INR0004 | Cameron | Gas | 730 | 6/1/2016 |
| 13INR0055 | Zapata | Wind | 250 | 12/31/2013 |  | 16INR0006 | Angelina | Gas | 785 | 6/1/2016 |
| 13INR0026 | Oldham | Wind | 201 | 6/1/2014 |  | 17INR0002 | Henderson | Gas | 489 | 6/1/2017 |
| 13INR0059 | Castro | Wind | 499 | 3/1/2014 |  | 11INR0040 | freestone | Gas | 640 | 3/1/2018 |
| 14INR0003 | Nolan | Coal | 850 | 6/1/2019 |  |  |  |  |  |  |

## Wind Generation Capacity Installed by Year

# Regional Planning Group Project Reviews

- Sharyland submitted the Atlas-Driver Load Integration project, a Tier 2 project that is estimated to cost approximately $18.6 million. This project has completed the RPG review and ERCOT has sent the RPG acceptance letter.

- Oncor submitted the Collin-Payne 138 kV rebuild project. This is a Tier 3 project that is estimated to cost approximately $20.6 million. This project has completed the RPG review and ERCOT has sent the RPG acceptance letter.

- Oncor submitted the Permian Basin to Moss to Odessa EHV 345 kV project. This is a Tier 1 project that is estimated to cost approximately $75 million. This project is currently under ERCOT independent review.

- Bryan Texas Utilities (BTU) submitted the Southwest Brazos County 138 kV loop project. This project is estimated to cost approximately $6.2 million. This project is classified as a Tier 3 and has been submitted for RPG comments.  In accordance with Protocol Section 3.11.4.5(c), once the RPG comments are resolved this project will be reclassified as a Tier 4 Neutral project.

# Asynchronous Tie Interconnection

| Project | Notification to ERCOT | Reliability Study | RPG Review | Interconnection Agreement | In-service Year |
| --- | --- | --- | --- | --- | --- |
| Railroad DC tie expansion (150 MW - CFE) |  |  |  |  | 2014 |
| Southern Cross HVDC (3000 MW - SERC) |  |  |  |  |  |
| Tres Amigas (1500 MW - SPP) |  |  |  |  |  |

Color Legend

|  | In progress |
| --- | --- |
|  | Complete |

# Congestion Costs

Dollars shown in RUC Make Whole payment graph are of settlement quality.

RUC net Make Whole payment in $mm

Monthly Average LMP

Binding Constraints – Year to Date

| Contingency | Binding Element | Number of 5-min intervals | Shadow Price Range $/MWh | Estimated Congestion Rent $ (Shadow Price*Limit) | Transmission Project |
| --- | --- | --- | --- | --- | --- |
| Roanoke Switch - West Denton and - Lewisville Switch 345 kV; or West Denton - Roanoke Switch 345 kV; or West Denton - Rdwells 138 kV | Jim Cristal - North Denton 138kV | 1407 | 0 - 3500 | 18,679,874 | 14TPIT0047 |
| Roanoke Switch - West Denton 345 kV & Roanoke Switch - Lewisville Switch 345 kV | Fort Worth - Teasley 138 kV | 2813 | 0 - 3500 | 16,898,845 | 14TPIT0047 |
| Morgan Creek SES 345/138 kV Autotransformer 2 | Morgan Creek SES 345/138 kV Autotransformer 4 | 150 | 29 - 4500 | 12,952,199 |  |
| Golden Switch - Sun Switch 138 kV; or Sacroc - Sun Switch 138 kV; or Snyder - China Grove 138 kV | China Grove - Bluff Creek 138 kV | 742 | 0 - 3500 | 12,659,248 | 12TPIT0058, 13TPIT0098 |
| Odessa North 138/69 kV Autotransformer; or West Over - Odessa 138 kV | Moss Switch - Amoco North Cowden Tap 138 kV | 936 | 0 - 3500 | 12,458,908 | 13TPIT0098, 13TPIT0093 |
| West Denton - Rdwells 138 kV | Teasley - Pockrus Substation 138 kV | 939 | 0 - 3500 | 11,088,886 | 14TPIT0047 |
| Wink 138/69 kV Autotransformer; or Wink - Wink Sub 138 kV | Wink Basin Tap - Wink Sub 69 kV | 772 | 0 - 2800 | 6,378,270 | 13TPIT0204, 14TPIT0105 |
| Ajo - Rio Hondo 345 kV | North Edinburg - Lon Hill 345 kV | 34 | 2 - 4500 | 5,859,545 | 14TPIT0050 |
| Asphalt Mines - Odlaw Switch 138 kV | Hamilton Road - Marverick 138 kV | 5071 | 0 - 2905 | 5,788,616 | 16TPIT0024 |
| Meadow - PH Robinson 345 kV | Alvin - Freeway Park 138 kV | 1869 | 0 - 3500 | 3,712,885 | 15TPIT0030 |

Binding Constraints – May 2013

| Contingency | Binding Element | Number of 5-min intervals | Shadow Price Range $/MWh | Estimated Congestion Rent $ (Shadow Price*Limit) | Transmission Project | Comments |
| --- | --- | --- | --- | --- | --- | --- |
| Wink 138/69 kV Autotransformer; or Wink - Wink Sub 138 kV | Wink Basin Tap - Wink Sub 69 kV | 753 | 0 - 2800 | 6,261,858 | 13TPIT0204, 14TPIT0105 | High load and low wind conditions |
| Odessa North 138/69 kV Autotransformer; or West Over - Odessa 138 kV | Moss Switch - Amoco North Cowden Tap 138 kV | 475 | 0 - 3500 | 5,945,661 | 13TPIT0098, 13TPIT0093 | Outage on Moss Switch 138 kV breaker |
| Golden Switch - Sun Switch 138 kV; or Sacroc - Sun Switch 138 kV; or Snyder - China Grove 138 kV | China Grove - Bluff Creek 138 kV | 330 | 2 - 3500 | 5,650,503 | 12TPIT0058, 13TPIT0098 | High load and low wind conditions |
| Ajo - Rio Hondo 345 kV | North Edinburg - Lon Hill 345 kV | 23 | 2 - 4500 | 4,244,993 | 14TPIT0050 | Generation outages in the area |
| Meadow - PH Robinson 345 kV | Alvin - Freeway Park 138 kV | 1714 | 0 - 3500 | 2,917,651 | 15TPIT0030 | High load and outage on Hastings - Friendswoord 138 kV line |
| McNeil - Gilleand Creek 138 kV | Hutto - Round Rock NE 138 kV | 366 | 1 - 3500 | 2,731,644 |  | Outage on Hutto Switch 138 kV circuit breaker |
| Fayette - Holman & Fayette - Lytton Springs 345 kV | Austrop - Lost Pines 345 kV | 1200 | 0 - 4500 | 2,341,544 | 10TPIT0031 | Outage on Lost Pines - Austrop 345 kV line |
| Singleton - Zenith 345 kV | Singleton - Tomball 345 kV | 867 | 0 - 153 | 1,999,546 |  | Outage on Roans Prairie - Kuykendahl and Kuykendahl - King 345 kV line |
| Lobo 345/138 kV Autotransformer; or Lobo - San Miguel 345 kV | San Diego - Freer 69 kV | 374 | 0 - 2800 | 1,877,406 | 13TPIT0132 | Outage on Cotulla - Dilley Switch 138 kV line |
| Garfield - Hicross & Garfield - Onion Creek 138 kV | Austrop - Daffin 138 kV | 448 | 0 - 3500 | 1,861,853 | 10TPIT0031 | Outage on Austrop - Decker 138 kV and Decker - Webber Tap 138 kV line |

# Wind Generation as a Percent of Load

One-hour average of total wind power output as a percentage of ERCOT load.

# Planning Model Activities

- The short term calendar of major planning model events follows:

  - Jun 11-13, 2013	SSWG Data Set A meeting in Taylor

  - Jun 14, 2013	Projected posting of 13DSA/DSB TPIT updates

  - Jul 5, 2013	Projected posting 14 Data Set A

- Status update on SCR760, Changes Needed for Information Model Manager and Topology Processor for Planning Models, which was approved by the ERCOT Board in March 2011.

  - Bundle 1 (Items 3, 7 and 8): In Production.

  - Bundle 2 (Items 2a, 4, 9):  In Production.

  - Bundle 3 (Item 5, 2b, 2c):  In Production

  - Bundle 4 (Items 1, 6):  First vendor release arrived at ERCOT on April 19, 2013.  ERCOT is testing the release for both Planning and CRR environments.  Expected off-cycle release to the environments used to create the products used for production planned for July 2013.

| SCR Sub Part | SCR Description | Status |
| --- | --- | --- |
| SCR760-1 | Upgrade to PSS/E v32 | Production |
| SCR760-2 | Distribution Capacitor banks | Production |
| SCR760-3 | Zero Impedance Line Ratings | Production |
| SCR760-4 | Associate Loads and Capacitor banks with the correct CNG | Production |
| SCR760-5 | Additional Transformer Data for Planning | Production |
| SCR760-6 | FACTS Devices | Release |
| SCR760-7 | Assign valid PSSE IDs to Breakers/ Switches/ Series Devices | Production |
| SCR760-8 | Phase shift of Autos for short circuit studies | Production |
| SCR760-9 | Multisection Line Grouping | Production |

Table 1:  In the following table:

- Red will be used to show status of Not Submitted, meaning that the SCR sub part has not been submitted to Siemens as a Service Request.

- Yellow will indicate that the SCR sub part has been submitted.  The color will remain yellow and the status will change in order to Submitted, Planning (Requirements, SOW, Code Writing), Release (Siemens produces first code to test), and Testing (code has completed internal test and is moving through release management).

- Green will indicate that the code has been tested and installed on the machines that ERCOT uses to produce Topology Processor output for Planning and CRR.

# Other Notable Activities

- The project to complete the missing and questionable data for the remaining Resource Asset Registration Forms (RARF) that are still incomplete is underway.  ERCOT and Siemens created a list of 3339 individual data items that are missing or suspect.  To date, 11 calls to Resource Entities regarding 19 different sites and 324 items within the list have been completed.

- Work on the 2013 Regional Transmission Plan (formerly the Five-Year Transmission Plan) has begun.

- ERCOT is currently performing the study to analyze the system needs in the West Texas area due to oil and gas load growth. The initial reliability analysis results were presented at the May RPG meeting. The steady-state base cases used for this study are posted at the ERCOT POI.

- ERCOT is preparing the report on the results of the Long-Term System Assessment and the improvements to the long-term study process as a result of the grant received from the Department of Energy.  The report is expected to be published in July.

- ERCOT has begun a study to plan the long-term transmission roadmap for the Panhandle Region.  With CREZ lines now extending the ERCOT transmission system into the area, ERCOT has received a significant amount of wind generation interconnection study activity in the Panhandle.  Currently, there are almost 2,600 MW of wind generation with signed generation interconnection agreeements in the region with another approximately 2,500 MW that have completed the full interconnection study phase of the process.  An additional approximately 5,400 MW is in the advanced stages of the interconnection study process.