## Slide 1
Project Prioritization Review
June 20, 2013

## Slide 2: 2013 Project Update – Agenda
  Project Prioritization Action Items p. 3-4
    Planned Revision Requests Starts – 2013/2014
    Guiding Principles Document
Location of Project Priority List (PPL): http://www.ercot.com/services/projects/index

## Slide 3: Approved Revision Requests “Not Started” – Planned to Start in Future Months
Revision Request | Target Start Date | Release Target | Cost Estimate | Author
NOGRR101 – Market Notice for DC-TIE Outage Information | Jun 2013 | 2013-R5 | <$10k | Tenaska
SCR756 – MarkeTrak Enhancements - Remaining SCR756 Items | Jun 2013 | 2014-R2 | $250k-$300k | MarkeTrak TF
NPRR210 – Wind Forecasting Change to P50, Sync with PRR841 | Jul 2013 | 2013-R6 | $45k-$55k | Morgan Stanley
NPRR492 – Addition of System Lambda Information | Jul 2013 | 2013-R6 | $15k-$20k | MISUG
NOGRR105 – Generation Resource Frequency Response Test Procedure | Jul 2013 | 2013-R6 | $30k-$40k | PDCWG
NPRR240 – Proxy Energy Offer Curve | Aug 2013 | 2013-R6 | $50k-$60k | Potomac Econ
SCR771 – Allow Ind. Master QSE to Represent Split Gen. Resources | Sep 2013 | 2014-R2 | $95k-$110k | Sandy Creek
NOGRR084 – Daily Grid Operations Summary Report | Sep 2013 | 2014-R4 | $300k-$500k | MISUG
NPRR256 – Sync PRR787, Add Non-Compliance Lang. to QSE Perf. Standards | Oct 2013 | 2014-R3 | $100k-$250k | Luminant
NPRR407 – Credit Monitoring Posting Requirements – CRR Portion | Jun 2013 | 2014-R2 | $90k-$110k | Tenaska
SCR769 – CRRAH Digital Certificate New Role for Read Only Access | Nov 2013 | 2014-R2 | $100k-$110k | Austin Energy
NPRR439 – Updating a Counter-Party’s Available Credit Limit for Current Day DAM | Jan 2014 | 2014-R4 | $125k-$135k | ERCOT
ERCOT requests your input: Are these the most important revision requests to work on in 2013?
Moved from June 2013

## Slide 4: Guiding Principles Document – Discuss Latest Draft
Guiding Principles of Project Prioritization
  General document structure:
    Definition of Key Prioritization Terms
    Approach to Project Prioritization
      New Additions to the PPL
      Reprioritizing Projects on the PPL
    Periodic Review of Upcoming Project Starts
Updates
  Input received from Oncor on comparison of total project cost to total project benefit
  Additional minor edits from ERCOT