## Slide 1
Project Update and Summary of Project Priority List (PPL) Activity to Date
June 20, 2013

## Slide 2: 2013 Project Update – Agenda
  Project Portfolio Update p. 3-7
    Recent/Upcoming Project Implementations
    2013 Release Targets
    2013 Project Spending Update
    2014 Release Targets
    2014 Project Funding
  Appendix
    Project Portfolio Gantt Chart p. 8-18
Location of Project Priority List (PPL): http://www.ercot.com/services/projects/index

## Slide 3: Recent/Upcoming Project Implementations
Release 3 Go-Lives (6/10/2013 – 6/14/2013)
  SCR773 – Addition of Regulation Feedback to Generation to be Dispatched Calculation
    Potential for early release before 6/10/2013 – see market notice dated 5/13/2013
  NPRR481 – Report of Hourly Actual System Load by Weather Zone
  NPRR520 – Real-Time Mitigation Rules and Creation of a Real-Time Constraint Competitiveness Test
    MMS, MIS, CDR portions – see market notice dated 5/13/2013
  NOGRR093 – Synchronization with NPRR365
  MarkeTrak Upgrade
  Macomber Map NERC SA/Compliance Enhancements
  Information Lifecycle Mgmt – Mkt Systems, Archive, Reporting
  Backup Software Strategy
  Cyber Security Project #8
Off-Cycle Release (July)
  SCR760 – Enhancements to IMM and TP to support Planning
    Final release
Note: Projected Go-Live dates are subject to change. Please watch for market notices as the effective dates approach.

## Slide 4: 2013 Release Targets – Board-Approved NPRRs/SCRs/xGRRs
Release Approach | Release 1 2/11 – 2/15 | Release 2 4/22 – 4/26 | Release 3 6/10 – 6/14 | Release 4 7/29 – 8/2 | Release 5 9/23 – 9/27 | Release 6 12/9-12/13 | 2013 TBD
On-Cycle | NPRR260 NPRR313 NPRR322 NPRR377 NPRR397 NPRR407(a) NPRR464 NPRR469 SCR768 | NPRR456 | NPRR481 NPRR520(a) NOGRR093 | NPRR207 NPRR393 NPRR461 NPRR479 NPRR520(b) | NPRR272 NPRR385 NPRR407(b) NPRR416 NPRR425 NPRR457 NOGRR101 SCR770 | NPRR210 NPRR240 NPRR272 NPRR327 NPRR476 NPRR492 NOGRR105 | NPRR153 NPRR484(1a) NPRR493 NPRR495 NPRR514
Off-Cycle |  | NPRR463 | SCR773 | SCR760(d) | NPRR514 |  | NPRR327
Counts Total = 38 | 9 | 2 | 4 | 6 | 8 | 6 | 3
Early April
None
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
(a), (b), etc. indicates multiple phases
Release targets are subject to change
Red Text: New additions and target release changes
Strike-Through Text: Previous target release changes
July
None
August
Late May
Moved to Future Years
NPRR407(a) – MMS portion
NPRR407(b) – CRR portion
NPRR484(1a) – initial CMM/CRR components
NPRR520(a) – MMS, MIS, CDR portions
NPRR520(b) – EMS, NMMS, ICCP portions
SCR760(d) – final phase
ü
ü
ü
ü
ü

## Slide 5: 2013 Cash Flow Projection – Approved Projects
ERCOT Board of Directors approved a project budget increase of $1M on 5/14/2013
Revised 2013 project budget is $16M

## Slide 6: 2014 Release Targets – Board-Approved NPRRs/SCRs/xGRRs
Release Approach | Release 1 TBD | Release 2 TBD | Release 3 TBD | Release 4 TBD | Release 5 TBD | Release 6 TBD | 2014 TBD
On-Cycle |  | SCR756(b) SCR769 SCR771 | NPRR256 NPRR439 | NOGRR084 |  |  | NPRR327 NPRR455 NPRR467 NPRR484(1b) NPRR485 NPRR487 NPRR500 NPRR509 SCR772
Off-Cycle |  |  |  |  |  |  | NPRR419 NPRR484(2) NPRR493
Counts Total = 18 | 0 | 3 | 2 | 1 | 0 | 0 | 12
Early April
None
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
(a), (b), etc. indicates multiple phases
Release targets are subject to change
Red Text: New additions and target release changes
Strike-Through Text: Previous target release changes
None
None
None
Late June
2015
NPRR484(Ph1b) – Remaining Phase 1 items
NPRR484(Ph2) – S&B portions
SCR756(b) – Remaining portions of SCR

## Slide 7: 2014 Project Funding (no change from May PRS)
ERCOT’s 2014 budget filing was previewed at the May Board meeting
  July Board review and approval targeted
$25M is being requested for capital projects in 2014
  ~$30M current demand in 2014
  Growing demand for Technical Foundation efforts
Multi-Year PPL is being used to forecast projects expected in 2014
For Revision Requests that are approved over the next 18 months, ERCOT has forecasted $4M in PPL funding
  This is in addition to $1.5M forecasted for Revision Requests that are already Board approved or in the stakeholder process

## Slide 8: Business Integration Update – Appendix
  Appendix
    6/18/2013 Project Gantt
      In-flight items sorted by Project End Date
      “Not Started” items sorted by Project Start Date

## Slide 9
Project Portfolio Status – as of 6/18/2013

## Slide 10
Project Portfolio Status – as of 6/18/2013

## Slide 11
Project Portfolio Status – as of 6/18/2013

## Slide 12
Project Portfolio Status – as of 6/18/2013

## Slide 13
Project Portfolio Status – as of 6/18/2013

## Slide 14
Project Portfolio Status – as of 6/18/2013

## Slide 15
Project Portfolio Status – as of 6/18/2013

## Slide 16
Project Portfolio Status – as of 6/18/2013

## Slide 17
Project Portfolio Status – as of 6/18/2013

## Slide 18
Project Portfolio Status – as of 6/18/2013