|  |  | System Planning |
| --- | --- | --- |
|  |  | Monthly Status Report June 2013 |
|  | Report Highlights |  |
|  | ERCOT is currently tracking 161 active generation interconnection requests totaling over 41,000 MW. This includes over 21,000 MW of wind generation. |  |
|  | ERCOT is currently reviewing proposed transmission improvements with a total cost of $75 Million Transmission Projects endorsed in 2013 total $349.8 Million All projects (in engineering, routing, licensing and construction) total approximately $8.82 Billion. Transmission Projects energized in 2013 total about $1.29 Billion. |  |

Table of Contents

1.	Generation Interconnection	1

1.1	Signed Generation Interconnection Agreements	1

1.2	New Generation Registering for Commercial Operations	1

1.3	Summary of Generation Interconnection Requests	1

1.4	Projects with Interconnection Agreements	4

1.5	Projects Undergoing Full Interconnection Studies with Confidentiality Waived	5

1.6	Generation Projects Undergoing Full Interconnection Studies	5

1.7	Wind Generation Capacity Installed by Year	8

2.	Regional Planning Group Project Reviews	9

3.	Asynchronous Tie Interconnection	10

4.	Congestion Costs	11

5.	Wind Generation as a Percent of Load	14

6.	Planning Model Activities	15

7.	Other Notable Activities	16

# 1.	Generation Interconnection

Additional information regarding detailed generation interconnection and impact studies is contained in the “Generation Project Interconnection Information” folder in the “Operations and System Planning” area on the ERCOT website:  http://planning.ercot.com/login/login.

## Signed Generation Interconnection Agreements

13INR0059 – Hereford Wind  –  499 MW of Wind in Castro County

## New Generation Registering for Commercial Operations

13DGR0001 – Bryan Solar  –  10 MW of Solar in Presidio County

12INR0086 – WA Parish Addition  –  75 MW of Gas in Fort Bend County

The total installed wind capacity is now reported as 10,570 MW by the resource owners through the registration process. Capacity by North, South and West is 832 MW, 2,375 MW, and 7,363 MW respectively.  Eight-hundred fifty MW is able to switch between the West and South zones and is currently shown in the South zone.

## Summary of Generation Interconnection Requests

| GENERATION INTERCONNECTION REQUESTS CURRENTLY UNDER REVIEW |
| --- |
| Currently tracking 161 generation interconnection or change requests |
| As of June 30, 2013 | Total |
| Security Screening Study | 12 |
| SSS Completed | 12 |
| Full Interconnect Study | 96 |
| FIS Completed | 9 |
| Suspended Studies | 0 |
| Capacity of Suspended Study Projects | 0 |
| Interconnect Agreement Completed | 35 |
| Capacity under Interconnection Agreements | 13,295 |
| Capacity for Grid, MW | 44,372 |
| Wind Capacity, MW | 21,669 |

| Fuel Type | Confidential Projects (MW) | Projects Under Full Study (MW) | Public Projects (MW) | Suspended Studies (MW) | Grand Total (MW) |
| --- | --- | --- | --- | --- | --- |
| Gas-AllOther |  |  | 449 | - | 6,903 |
| Gas-CombinedCycle |  |  | 6,506 | - | 12,457 |
| Total Gas | 2,615 | 9,790 | 6,955 | - | 19,360 |
| Nuclear | - | - | - | - | - |
| Coal | - | - | 1,165 | - | 1,165 |
| Wind | 2,748 | 13,859 | 5,062 | - | 21,669 |
| Solar | 395 | 719 | 150 | - | 1,264 |
| Biomass | - | - | - | - | - |
| Storage | - | 874 | 40 | - | 914 |
| Petroleum Coke | - | - | - | - | - |
| Grand Total | 5,758 | 25,242 | 13,372 | - | 44,372 |

County Location of Installed Generation and Interconnection Requests (all fuels)

## Projects with Interconnection Agreements

| Generation Interconnections as of June 30, 2013 |
| --- |
| INR | Site Name | County | COD | Fuel | MW For Grid | Change from Last Report |
| 10INR0089 | Deepwater Energy Storage | Harris | Jul-13 | Storage | 40 |  |
| 11INR0033 | Los Vientos | Cameron | Jul-13 | Wind | 400 | Date |
| 12INR0075 | Blue Summit Windfarm | Wilbarger | Jul-13 | Wind | 135 | Date |
| 09INR0001 | Sandy Creek 1 | McLennan | Jul-13 | Coal | 925 | Date |
| 13INR0059 | Hereford Wind | Castro | Oct-13 | Wind | 499 | New |
| 13INR0058 | OCI Alamo 1 | Bexar | Oct-13 | Solar | 50 |  |
| 11INR0094 | White Camp Solar | Kent | Nov-13 | Solar | 100 |  |
| 11INR0013 | Goldthwaite Wind Energy | Mills | Dec-13 | Wind | 150 |  |
| 12INR0034 | Stephens Ranch Wind Energy | Borden | Dec-13 | Wind | 378 |  |
| 14INR0012 | Miami Wind 1 Project | Gray | May-14 | Wind | 401 |  |
| 13INR0048 | Spinning Spur Wind Two | Oldham | Jun-14 | Wind | 161 |  |
| 14INR0015 | Deer Park Energy Center | Harris | Jun-14 | Gas | 192 |  |
| 14INR0016 | Channel Energy Center 138/345kV CT | Harris | Jun-14 | Gas | 190 |  |
| 10INR0021 | Panda Sherman Power | Grayson | Jun-14 | Gas | 809 |  |
| 10INR0020a | Panda Temple Power | Bell | Jun-14 | Gas | 809 |  |
| 13INR0021 | Ferguson Replacement Project | Llano | Jul-14 | Gas | 570 |  |
| 13INR0040 | Agrifos Steam Unit | Harris | Aug-14 | Gas | - |  |
| 14INR0030a2 | Panhandle Wind | Carson | Aug-14 | Wind | 218 |  |
| 11INR0050 | Moore Wind 1 | Crosby | Aug-14 | Wind | 149 |  |
| 13INR0010a | Mariah Wind | Parmer | Oct-14 | Wind | 200 |  |
| 11INR0054 | Midway Farms Wind | San Patricio | Oct-14 | Wind | 161 | Date |
| 14INR0023 | Longhorn Energy Center | Briscoe | Dec-14 | Wind | 361 |  |
| 13INR0005 | Conway Windfarm | Carson | Dec-14 | Wind | 600 |  |
| 06INR0022c | Penascal Wind Farm 3 | Kenedy | Dec-14 | Wind | 202 |  |
| 11INR0079a | South Clay Windfarm | Clay | Dec-14 | Wind | 200 |  |
| 09INR0051 | Mesquite Creek | Borden | Mar-15 | Wind | 249 |  |
| 08INR0018 | Gunsight Mountain | Howard | Aug-15 | Wind | 120 |  |
| 10INR0020b | Panda Temple Power | Bell | Aug-15 | Gas | 780 |  |
| 13INR0010b | Mariah Wind | Parmer | Dec-15 | Wind | 200 |  |
| 13INR0023 | Texas Clean Energy Project | Ector | Jan-16 | Coal | 240 |  |
| 13INR0028 | Antelope Station | Hale | Jun-16 | Gas | 359 |  |
| 10INR0022 | Pondera King Power Project | Harris | Jun-16 | Gas | 1,380 |  |
| 06INR0006 | Cobisa-Greenville | Hunt | Dec-16 | Gas | 1,792 | Date |
| 13INR0010c | Mariah Wind | Parmer | Dec-16 | Wind | 200 | Date |

## Projects Undergoing Full Interconnection Studies with Confidentiality Waived

| INR | Site Name | County | COD | Fuel | MW for Grid | Change from Last Report |
| --- | --- | --- | --- | --- | --- | --- |

## Generation Projects Undergoing Full Interconnection Studies

| Interconnection Database Reference Number | County | Fuel | Capacity to Grid (MW) | Commercial Operation Date (as specified by the resource developer) |
| --- | --- | --- | --- | --- |
| 13INR0026 | Oldham | Wind | 201 | 12/1/2013 |
| 13INR0056 | Scurry | Wind | 366 | 12/1/2013 |
| 13INR0055 | Zapata | Wind | 250 | 12/1/2013 |
| 13INR0052 | Starr | Wind | 200 | 12/1/2013 |
| 13INR0038 | Swisher | Wind | 300 | 12/1/2013 |
| 15INR0021 | Starr | Wind | 200 | 12/31/2013 |
| 14INR0024 | Kinney | Solar | 42 | 12/31/2013 |
| 12INR0068 | Jim Hogg | Wind | 78 | 12/31/2013 |
| 14INR0014 | Val Verde | Solar | 100 | 1/1/2014 |
| 12INR0055 | Baylor | Wind | 40 | 1/1/2014 |
| 13INR0006 | Gray | Wind | 750 | 1/1/2014 |
| 14INR0013 | Cameron | Wind | 103 | 1/1/2014 |
| 14INR0059 | Kaufman | Gas | 52 | 2/1/2014 |
| 14INR0039 | Ector | Gas | 450 | 3/1/2014 |
| 13INR0059 | Castro | Wind | 499 | 3/1/2014 |
| 12INR0060 | Schleicher | Wind | 58 | 4/1/2014 |
| 14INR0027 | Guadalupe | Gas | 471 | 5/1/2014 |
| 11INR0057 | Cameron | Wind | 165 | 6/1/2014 |
| 08INR0019a | Gray | Wind | 250 | 6/1/2014 |
| 08INR0019b | Gray | Wind | 250 | 6/1/2014 |
| 08INR0019c | Gray | Wind | 250 | 6/1/2014 |
| 14INR0048 | Wilbarger | Wind | 114 | 6/1/2014 |
| 14INR0038 | Galveston | Gas | 390 | 6/1/2014 |
| 13INR0057 | Archer | Wind | 65 | 6/1/2014 |
| 14INR0040 | Hidalgo | Gas | 225 | 6/7/2014 |
| 12INR0059 | Pecos | Solar | 50 | 6/30/2014 |
| 12INR0085 | Stonewall | Wind | 24 | 7/1/2014 |
| 11INR0093 | San Patricio | Wind | 41 | 7/1/2014 |
| 14INR0029 | Uvalde | Solar | 42 | 7/1/2014 |
| 14INR0047 | Dickens | Wind | 301 | 10/1/2014 |
| Interconnection Database Reference Number | County | Fuel | Capacity to Grid (MW) | Commercial Operation Date (as specified by the resource developer) |
| 12INR0070 | Knox | Wind | 300 | 10/15/2014 |
| 13INR0036 | Hidalgo | Wind | 200 | 10/31/2014 |
| 12INR0045 | Kleberg | Wind | 135 | 10/31/2014 |
| 14INR0060 | Haskell | Wind | 400 | 11/1/2014 |
| 13INR0025 | Randall | Wind | 150 | 11/1/2014 |
| 14INR0030b | Carson | Wind | 322 | 11/1/2014 |
| 14INR0033 | Armstrong | Wind | 500 | 12/1/2014 |
| 13INR0050 | Comanche | Wind | 200 | 12/1/2014 |
| 14INR0032a | Randall | Wind | 200 | 12/1/2014 |
| 13INR0054 | Bee | Gas | 0 | 12/1/2014 |
| 14INR0025a | Floyd | Wind | 200 | 12/1/2014 |
| 14INR0041 | Willacy | Wind | 300 | 12/1/2014 |
| 14INR0043 | Sterling | Solar | 40 | 12/1/2014 |
| 11INR0082A | Val Verde | Wind | 50 | 12/1/2014 |
| 11INR0082B | Val Verde | Wind | 150 | 12/1/2014 |
| 14INR0044 | Reeves | Solar | 100 | 12/1/2014 |
| 10INR0085 | Ector | Solar | 56.5 | 12/1/2014 |
| 14INR0028 | Live Oak | Wind | 300 | 12/1/2014 |
| 14INR0009 | Kent | Wind | 248 | 12/1/2014 |
| 12INR0079 | Kenedy | Wind | 200 | 12/15/2014 |
| 13INR0045 | Castro | Wind | 288 | 12/30/2014 |
| 14INR0057b | Erath | Wind | 48 | 12/31/2014 |
| 14INR0020 | Floyd | Wind | 150 | 12/31/2014 |
| 14INR0049_2 | Jack | Wind | 102 | 12/31/2014 |
| 14INR0057 | Erath | Wind | 48 | 12/31/2014 |
| 14INR0049_1 | Jack | Wind | 102 | 12/31/2014 |
| 13INR0010d | Parmer | Wind | 200 | 12/31/2014 |
| 14INR0056 | Mills | Wind | 101 | 12/31/2014 |
| 14INR0045a | Webb | Wind | 502 | 12/31/2014 |
| 10INR0009 | Castro | Wind | 300 | 3/31/2015 |
| 15INR0028 | Freestone | Gas | 160 | 6/1/2015 |
| 15INR0042 | Hood | Gas | 460 | 6/1/2015 |
| 15INR0027 | Hidalgo | Gas | 79 | 6/1/2015 |
| 15INR0022 | Presidio | Solar | 75 | 6/1/2015 |
| 15INR0023 | Wharton | Gas | 700 | 6/15/2015 |
| 14INR0026 | Presidio | Solar | 28 | 9/1/2015 |
| 15INR0013 | Anderson | Gas | 324 | 10/1/2015 |
| 15INR0014 | Matagorda | Gas | 280 | 10/1/2015 |
| 11INR0065 | Nueces | Wind | 350 | 10/31/2015 |
| 14INR0030a1 | Carson | Wind | 322 | 11/1/2015 |
| 14INR0032b | Randall | Wind | 300 | 12/1/2015 |
| 14INR0018 | Nolan | Solar | 35 | 12/31/2015 |
| Interconnection Database Reference Number | County | Fuel | Capacity to Grid (MW) | Commercial Operation Date (as specified by the resource developer) |
| 13INR0010e | Parmer | Wind | 200 | 12/31/2015 |
| 12INR0002a | Briscoe | Wind | 200 | 12/31/2015 |
| 15INR0037 | Starr | Wind | 200 | 12/31/2015 |
| 13INR0032 | Andrews | Solar | 30 | 12/31/2015 |
| 14INR0045b | Webb | Wind | 251 | 12/31/2015 |
| 16INR0010 | Mitchell | Gas | 799 | 2/1/2016 |
| 16INR0005 | Cameron | Gas | 871 | 4/1/2016 |
| 16INR0009 | Calhoun | Gas | 510 | 4/14/2016 |
| 15INR0032 | Hale | Gas | 197 | 5/1/2016 |
| 15INR0033 | Hale | Gas | 197 | 5/1/2016 |
| 16INR0008 | Grimes | Gas | 687 | 5/1/2016 |
| 16INR0004 | Cameron | Gas | 730 | 6/1/2016 |
| 16INR0007 | Hidalgo | Gas | 95 | 6/1/2016 |
| 16INR0003 | Brazoria | Gas | 11 | 6/1/2016 |
| 16INR0006 | Angelina | Gas | 785 | 6/1/2016 |
| 14INR0011 | Swisher | Gas | 270 | 7/1/2016 |
| 13INR0010f | Parmer | Wind | 200 | 12/31/2016 |
| 12INR0002b | Briscoe | Wind | 200 | 12/31/2016 |
| 12INR0018 | Gray | Wind | 500 | 3/31/2017 |
| 17INR0004 | Hale | Gas | 170 | 5/1/2017 |
| 17INR0002 | Henderson | Gas | 489 | 6/1/2017 |
| 11INR0040 | Freestone | Gas | 640 | 3/1/2018 |

## Wind Generation Capacity Installed by Year

# Regional Planning Group Project Reviews

- Oncor submitted the Permian Basin to Moss to Odessa EHV 345 kV project. This is a Tier 1 project that is estimated to cost approximately $75 million. This project is currently under ERCOT independent review.

- Bryan Texas Utilities (BTU) submitted the Southwest Brazos County 138 kV loop project. This project is estimated to cost approximately $6.2 million. This project was initially classified as a Tier 3 and and the project has statisfied all the RPG comments.  In accordance with Protocol Section 3.11.4.5, the Southwest Brazos County 138 kV loop project has been reclassified as a “Tier 4 Neutral Project.”

- Sharyland Utilities submitted the Stanton/Midland Northern loop project. This project is classified as a Tier 3 and has been submitted for RPG comments.  In accordance with Protocol Section 3.11.4.5(c), once the RPG comments are resolved this project will be reclassified as a Tier 4 Neutral project.

# Asynchronous Tie Interconnection

| Project | Notification to ERCOT | Reliability Study | RPG Review | Interconnection Agreement | In-service Year |
| --- | --- | --- | --- | --- | --- |
| Railroad DC tie expansion (150 MW - CFE) |  |  |  |  | 2014 |
| Southern Cross HVDC (3000 MW - SERC) |  |  |  |  |  |
| Tres Amigas (1500 MW - SPP) |  |  |  |  |  |

Color Legend

|  | In progress |
| --- | --- |
|  | Complete |

# Congestion Costs

Dollars shown in RUC Make Whole payment graph are of settlement quality.

RUC net Make Whole payment in $mm

Monthly Average LMP

Binding Constraints – Year to Date

| Contingency | Binding Element | Number of 5-min intervals | Shadow Price Range $/MWh | Estimated Congestion Rent $ (Shadow Price*Limit) | Transmission Project |
| --- | --- | --- | --- | --- | --- |
| Roanoke Switch - West Denton and - Lewisville Switch 345 kV; or West Denton - Roanoke Switch 345 kV; or West Denton - Rdwells 138 kV | Jim Cristal - North Denton 138kV | 1407 | 0 - 3500 | 18,679,874 | 14TPIT0047 |
| Roanoke Switch - West Denton 345 kV & Roanoke Switch - Lewisville Switch 345 kV | Fort Worth - Teasley 138 kV | 2813 | 0 - 3500 | 16,898,845 | 14TPIT0047 |
| Odessa North 138/69 kV Autotransformer; or West Over - Odessa 138 kV | Moss Switch - Amoco North Cowden Tap 138 kV | 1204 | 0 - 3500 | 15,801,329 | 13TPIT0098, 13TPIT0093 |
| Midland East to Moss Switch 138 kV | Odessa - Odessa North 138 kV | 1385 | 0 - 3500 | 14,067,127 | 13TPIT0136,14TPIT0054 |
| Golden Switch - Sun Switch 138 kV; or Sacroc - Sun Switch 138 kV; or Snyder - China Grove 138 kV | China Grove - Bluff Creek 138 kV | 755 | 0 - 3500 | 12,781,489 | 12TPIT0058, 13TPIT0098 |
| Morgan Creek SES 345/138 kV Autotransformer 2 | Morgan Creek SES 345/138 kV Autotransformer 4 | 131 | 29 - 4500 | 11,206,208 |  |
| West Denton - Rdwells 138 kV | Teasley - Pockrus Substation 138 kV | 939 | 0 - 3500 | 11,088,886 |  |
| Ajo - Rio Hondo 345 kV | North Edinburg - Lon Hill 345 kV | 39 | 2 - 4500 | 7,633,932 | 14TPIT0050 |
| McNeil - Gilleand Creek 138 kV | Hutto - Round Rock NE 138 Kv | 1446 | 0 - 3500 | 7,205,932 |  |
| Asphalt Mines - Odlaw Switch 138 kV | Hamilton Road - Marverick 138 kV | 5604 | 0 - 2905 | 6,451,792 | 16TPIT0024 |

Binding Constraints – June 2013

| Contingency | Binding Element | Number of 5-min intervals | Shadow Price Range $/MWh | Estimated Congestion Rent $ (Shadow Price*Limit) | Transmission Project | Comments |
| --- | --- | --- | --- | --- | --- | --- |
| Midland East to Moss Switch 138 kV | Odessa - Odessa North 138 kV | 1122 | 0 - 3500 | 12,833,493 | 13TPIT0136,14TPIT0054 | High load and low wind conditions. |
| McNeil - Gilleland Creek 138 kV;Gabriel To Bell County & Round Rock | Hutto - Round Rock NE 138 Kv | 1012 | 0 - 3500 | 4,190,809 |  | Outage on Austrop – Decker 138 kV line and Decker to Webber Tap 138 kV line. |
| DCKT Singleton - Tomball 345 kV | Singleton - Zenith 345 kV | 816 | 0 - 4500 | 4,168,352 |  |  |
| Amoco South Foster to Westover 138 kV | Moss Switch - Amoco North Cowden Tap 138 kV | 268 | 0 - 3500 | 3,342,420 | 13TPIT0098, 13TPIT0093 | High load and low wind conditions. |
| Sun Switch - Morgan Creek 138 kV | Chinagrove Switch - Snyder 138 kV | 45 | 3500 - 3500 | 2,596,242 | 12TPIT0058, 13TPIT0098 | Forced outage on Bluff Creek Switch – China Grove Switch 138 kV line. |
| Atkins - Dansby 138 kV | BTU Industrial Park - BTU North 69 kV | 127 | 9 - 2800 | 2,232,480 |  |  |
| DCKT Garfield - Hicross 138 kV; DCKT Austrop - Garfield 345 kV; DCKT Garfield - Lytton Springs 345 kV; DCKT Garfield - Stoney Ridge 138 kV | Austrop - Daffin 138 kV | 585 | 0 - 3500 | 2,190,356 | 10TPIT0031 | Outage on Austrop – Decker 138 kV line and Decker to Webber Tap 138 kV line. |
| Cagnon 345/138 kV XFMR 3; DCKT Skyline - Calaveras 345 kV | Cagnon345/138kV XFMR 4 | 594 | 0 - 979 | 2,094,881 | 14TPIT0031 |  |
| Morgan Creek SES 345/138 kV AXFMR 2 | Morgan Creek SES 345/138 kV AXFMR 1 | 497 | 0 - 462 | 2,000,902 |  |  |
| Ajo - Rio Hondo 345 kV | North Edinburg - Lon Hill 345 kV | 5 | 4500 - 4500 | 1,774,388 | 14TPIT0050 | Generation outages in the area. |

# Wind Generation as a Percent of Load

One-hour average of total wind power output as a percentage of ERCOT load.

The hourly wind generation and load data used to develop these charts are available in the Nodal Monthly Aggregate WPF Report provided by ERCOT Operations to the QMWG.

# Planning Model Activities

- The short term calendar of major planning model events follows:

  - Jun 14, 2013	13DSA/DSB TPIT updates posted

  - Jul 12, 2013	Projected posting 14 Data Set A

  - Aug 1, 2013	Project start of 14 Data Set B case build

- Status update on SCR760, Changes Needed for Information Model Manager and Topology Processor for Planning Models, which was approved by the ERCOT Board in March 2011.

  - Bundle 1 (Items 3, 7 and 8): In Production.

  - Bundle 2 (Items 2a, 4, 9):  In Production.

  - Bundle 3 (Item 5, 2b, 2c):  In Production

  - Bundle 4 (Items 1, 6):  Development testing completed, moved to ITEST for more testing.  Expected off-cycle release to the environments used to create the products used for production planned for end of July 2013.

| SCR Sub Part | SCR Description | Status |
| --- | --- | --- |
| SCR760-1 | Upgrade to PSS/E v32 | Production |
| SCR760-2 | Distribution Capacitor banks | Production |
| SCR760-3 | Zero Impedance Line Ratings | Production |
| SCR760-4 | Associate Loads and Capacitor banks with the correct CNG | Production |
| SCR760-5 | Additional Transformer Data for Planning | Production |
| SCR760-6 | FACTS Devices | Testing |
| SCR760-7 | Assign valid PSSE IDs to Breakers/ Switches/ Series Devices | Production |
| SCR760-8 | Phase shift of Autos for short circuit studies | Production |
| SCR760-9 | Multisection Line Grouping | Production |

Table 1:  In the following table:

- Red will be used to show status of Not Submitted, meaning that the SCR sub part has not been submitted to Siemens as a Service Request.

- Yellow will indicate that the SCR sub part has been submitted.  The color will remain yellow and the status will change in order to Submitted, Planning (Requirements, SOW, Code Writing), Release (Siemens produces first code to test), and Testing (code has completed internal test and is moving through release management).

- Green will indicate that the code has been tested and installed on the machines that ERCOT uses to produce Topology Processor output for Planning and CRR.

# Other Notable Activities

- The project to complete the missing and questionable data for the remaining Resource Asset Registration Forms (RARF) that are still incomplete is underway.  ERCOT and Siemens created a list of 3339 individual data items that are missing or suspect.  To date, 24 calls to Resource Entities regarding 40 different sites and 199 items within the list have been completed.

- ERCOT is working on the 2013 Regional Transmission Plan (RTP). The study base case modeling assumptions (load, generation, DC ties etc.) were presented at the June RPG meeting. ERCOT is currently working on preparing the Reliability start cases for the 2013 RTP.

- ERCOT is currently performing the study to analyze the system needs in the West Texas area due to oil and gas load growth. The preliminary reliability analysis results were presented at the June RPG meeting. The steady-state base cases used for this study are posted at the ERCOT POI. ERCOT is currently performing the economic analysis for the West Texas Sensitivity study.

- ERCOT is preparing the report on the results of the Long-Term System Assessment and the improvements to the long-term study process as a result of the grant received from the Department of Energy.  The report is expected to be published in July.