## Slide 1
Project Update and Summary of Project Priority List (PPL) Activity to Date
July 18, 2013
Notes: <number>

## Slide 2: 2013 Project Update – Agenda
  Project Portfolio Update p. 3-7
    Recent/Upcoming Project Implementations
    2013 Release Targets
    2013 Project Spending Update
    2014 Release Targets
    2014/2015 Project Funding
  Appendix
    Project Portfolio Gantt Chart p. 8-18
Location of Project Priority List (PPL): http://www.ercot.com/services/projects/index
Notes: <number>

## Slide 3: Recent/Upcoming Project Implementations
Release 4 Go-Lives (7/29/2013 – 8/2/2013)
  NPRR393 – SCED Constraint Management Transparency
    Report going into Production in R4 but posting will not begin until after a stabilization period is complete
  NPRR461 – Energy Storage Settlements Consistent with PUCT Project 39917
  NPRR520 – Real-Time Mitigation Rules and Creation of a Real-Time Constraint Competitiveness Test
    2nd of 2 phases – EMS, NMMS, ICCP portions
  SCR760 – Enhancements to IMM and TP to support Planning
    Final release
  EPG Synchrophasor Upgrade
  Emergency Notification System Hardware Refresh
  Moody’s Analytics
  Mobile Application Enhancement
Note: Projected Go-Live dates are subject to change. Please watch for market notices as the effective dates approach.

## Slide 4: 2013 Release Targets – Board-Approved NPRRs/SCRs/xGRRs
ERCOT Public
Early April
None
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
(a), (b), etc. indicates multiple phases
Release targets are subject to change
Red Text: New additions and target release changes
Strike-Through Text: Previous target release changes
July
October
August
Late May
Moved to Future Years
NPRR407(a) – MMS portion
NPRR484(1a) – initial CMM/CRR components
NPRR520(a) – MMS, MIS, CDR portions
NPRR520(b) – EMS, NMMS, ICCP portions
SCR760(d) – final phase






## Slide 5: 2013 Cash Flow Projection – Approved Projects
ERCOT Board of Directors approved a project budget increase of $1M on 5/14/2013
Revised 2013 project budget is $16M

## Slide 6: 2014 Release Targets – Board-Approved NPRRs/SCRs/xGRRs
ERCOT Public
Early April
None
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
(a), (b), etc. indicates multiple phases
Release targets are subject to change
Red Text: New additions and target release changes
Strike-Through Text: Previous target release changes
None
None
None
Late June
2015
NPRR407(b) – CRR portion
NPRR484(Ph1b) – Remaining Phase 1 items
NPRR484(Ph2) – S&B portions
SCR756(b) – Remaining portions of SCR

## Slide 7: 2014/2015 Project Funding
ERCOT’s 2014/2015 budget filing was approved at the July Board meeting
$25M is being requested for capital projects in both 2014 and 2015
  ~$30M current demand each year
Multi-Year PPL is being used to forecast projects expected in future years
For Revision Requests that are approved over the next 36+ months, ERCOT has forecasted $4M in PPL funding per year
  This is in addition to $1.5M forecasted for 2013 Revision Requests that are already Board approved or in the stakeholder process

## Slide 8: Business Integration Update – Appendix
  Appendix
    7/12/2013 Project Gantt
      In-flight items sorted by Project End Date
      “Not Started” items sorted by Project Start Date
Notes: <number>

## Slide 9
ERCOT Public
Project Portfolio Status – as of 7/12/2013

## Slide 10
ERCOT Public
Project Portfolio Status – as of 7/12/2013

## Slide 11
ERCOT Public
Project Portfolio Status – as of 7/12/2013

## Slide 12
ERCOT Public
Project Portfolio Status – as of 7/12/2013

## Slide 13
ERCOT Public
Project Portfolio Status – as of 7/12/2013

## Slide 14
ERCOT Public
Project Portfolio Status – as of 7/12/2013

## Slide 15
ERCOT Public
Project Portfolio Status – as of 7/12/2013

## Slide 16
ERCOT Public
Project Portfolio Status – as of 7/12/2013

## Slide 17
ERCOT Public
Project Portfolio Status – as of 7/12/2013

## Slide 18
ERCOT Public
Project Portfolio Status – as of 7/12/2013