## Slide 1
<number>
PWG Update Report
By
Ed Echols
Of Oncor
ERCOT PWG Chair
Jim Lee
of Direct Energy
ERCOT PWG Vice Chair
for
COPS Meeting
July 24 and Aug 6, 2013
Notes: <number>

## Slide 2
<number>
NO. | PWG 2013 Goals | Target Date | Completion
1 | Protocol Requirement Review of UFE for the Prior year due 4/30 | May | 100%
2 | Profile ID Annual Validation Residential | Nov | 30%
3 | Profile ID Annual Validation Business | Nov | 
4 | LPGRR changes as needed | Dec | 

## Slide 3
<number>
Annual Validation Schedule 2013
Date | Residential Annual Validation Task List | Status
07/19/2013 | ERCOT to provide list of ESI IDs to TDSPs | Complete
08/02/2013 | TDSPs to provide finalized list of ESI IDs to ERCOT | Complete
08/09/2013 | Market Notice announcing lists are available to CR of record | Complete
09/06/2013 | TDSPs to begin submitting 814_20 transactions | 
10/18/2013 | TDSPs to complete submissions of all 814_20 transactions | 
11/01/2013 | ERCOT to review database for expected changes | 
Date | Business Annual Validation Task List | Status
08/20/2013 | ERCOT to provide list of ESI IDs to TDSPs | 
08/27/2013 | TDSPs to provide finalized list of ESI IDs to ERCOT | 
10/01/2013 | Market Notice announcing lists are available to CR of record | 
10/01/2013 | TDSPs to begin submitting 814_20 transactions | 
11/22/2013 | TDSPs to complete submissions of all 814_20 transactions | 
12/06/2013 | ERCOT to review database for expected changes | 
12/06/2013 | All TDSPs have submitted at least 99% of changes | 
 |  | Last Updated 08/07/2013
Notes: <number>

## Slide 4
<number>
Quarterly Validation Requirements
Load Profiling Guide Section 11.3
LPG Section | Validation Description | ESIID Counts 2nd QTR 2013
11.3.1 | BUSNODEM profile type | 0
11.3.2 | BUS Load Factor profile types | 351
11.3.3 | BUSOGFLT profile type | 1
11.3.4 | NMFLAT and NMLIGHT profile types | 191
11.3.5 | Distributed Generation | 94
11.3.6 | Profile type to Premise type | 75
11.3.7 | ZIP Code to Substation | 0
11.3.8 | ZIP Code to Weather Zone code | 53
11.3.9 | Meter Data Type code to Profile Type code | 0
11.3.10 | Weather Sensitivity code to Meter Data Type | 0
Total |  | 765
Notes: <number>

## Slide 5
<number>
Next PWG meet date;
August 26, 2013
All meetings are posted and planned as half day morning WebEx calls
248 Load Profiles
8 Weather Zones
31 Profile Types
http://www.ercot.com/committees/board/tac/cops/pwg/