## Slide 1: MP Online Data Entry Project Update WMS / ROS August 2013 Troy Anderson

## Slide 2: Agenda
MP Online Data Entry Project Update
Next Steps
Appendix
  Project Objectives
  Project Benefits

## Slide 3: MP Online Data Entry Project Update
Project Status Update
  This effort has been on the Project Priority List for several years
  Major areas to be addressed
    RARF (Resource Asset Registration Form)
    Market Participant Registration
    Verifiable Costs (VC)
  3 project phases anticipated over 3 years
  Total project cost likely to be $2M-$3M
    Cost estimate will be refined during Planning of Phase 1
  Phase 1 expected to gate to Planning in the near future
    $300k cost estimate for Planning phase
    4-5 months duration
    All phases will be planned out during this time
Notes: Review where on the PPL these projects are
Planning (for all three phases) has been estimated at $362,000 and will run for 5 months
Execution estimates -
  Phase 1: $700,000
  Phase 2: $900,000
  Phase 3: $900,000
Like all large projects, ERCOT has an obligation to update the BOD.
Moving to planning phase, which will provide the necessary data to refine the accuracy of the estimates

## Slide 4: MP Online Data Entry Project Update
Project Portfolio Notes
  The PPL has 3 separate phases targeted for funding
    MP Online Data Entry Phase 1 – 2013-2014
    MP Online Data Entry Phase 2 – 2014
    MP Online Data Entry Phase 3 – 2015
  “Business Strategy” category, ERCOT-sponsored
  Phases 2 and 3 occur in future years
    Schedule subject to change based on results of Phase 1 Planning
  Spending on these efforts is already included in the forecast project spend from 2013 – 2015
Location of Project Priority List (PPL): http://www.ercot.com/services/projects/index
Notes: Review where on the PPL these projects are
Planning (for all three phases) has been estimated at $362,000 and will run for 5 months
Execution estimates -
  Phase 1: $700,000
  Phase 2: $900,000
  Phase 3: $900,000
Like all large projects, ERCOT has an obligation to update the BOD.
Moving to planning phase, which will provide the necessary data to refine the accuracy of the estimates

## Slide 5: Next Steps
  ERCOT would like to confirm that the market is still supportive of this effort moving forward
    MP Online Data Entry has a direct impact on Market Participants
    It is also expected to require significant project funding so stakeholder agreement on relative importance is needed
If the market supports this project, ERCOT will gate to Planning and begin defining detailed requirements
Frequent communications with market stakeholders is expected
  Provide regular project updates to RDWG and other impacted subcommittees and working groups
  Conduct requirements workshops, hosted by RDWG, to get market feedback
    Input on requirements
    Input on placement of requirements into the 3 phases

## Slide 6: Questions
?

## Slide 7
Appendix

## Slide 8: MP Online Project Objectives
# | Objectives / Scope | Priority | Phase(s)
OB-001 | Market Participants and ERCOT teams should interact with a logical, consistent and easily navigable interface when providing registration and operational model data (includes NDCRC, and Verifiable Costs to ERCOT. | High | 1 – RES Reg, VC 2 – MP Reg 3 - VC
OB-002 | Users (Market Participants and ERCOT) should be able to retrieve and review current (production), future (what is in the workflow for validation), and activity history (where relevant) for registration and operational data sets (including comments, attached files) on demand. | High | 1 – RES Reg, VC 2 – MP Reg 3 - VC
OB-003 | Existing validation checks should not be compromised by a new interface. Data entry validations on characteristics and business rules validations should be incorporated where appropriate. | Medium | 1 – RES Reg, VC 2 – MP Reg 3 - VC
OB-004 | Market Participant can enter part of the required data and return later to complete the remaining and not lose what was submitted (save vs. submit). | High | 1
OB-005 | When new data elements are approved to be added to the business process, need flexibility to add for Market Participant data entry (example – new fields needed for solar or user defined variables). | Low | 1
OB-006 | User activity should be managed per assigned security role (single sign in / digital certificate). Access is controlled by data type, function and type of user. Roles may be different within a Market Participant. | High | 1
OB-007 | Users should be able view work flow status of data submission or modifications. | High | 1 – RES Reg, VC 2 – MP Reg 3 - VC
OB-008 | All MP data submissions should be categorized (modeling, registration, verifiable cost, etc.) and adopted by a system of record (NMMS, lodestar, etc.). The ERCOT system of record is identified for each discreet data item and the interfaces transmits data to its system of record. | High | 1 – RES Reg, VC 2 – MP Reg 3 - VC
OB-009 | Interconnecting Entities should have the ability to enter data based on their progress through the Generation Interconnection timeline such that data for these future resources can be extracted similarly to registered resources. | Medium | 1
Notes: Talking points –
Worked across teams at ERCOT to define the objectives and begin prioritization. If the market has feedback on these, we’ll make note and take back to the business owners.
Anytime ERCOT has a larger project, we manage in phases to be successful and mitigate risk
Phase 1 (which RDWG is likely most interested in) includes the RARF
Additional phases include Verifiable Costs & Market Participant Registration and NDCRC. As we go into planning, if we learn we can leverage efficiencies, we may try and move things into earlier phases. However, key message is we are starting with the RARF.

## Slide 9: Benefits
Resource asset registration, MP Registration and NDCRC
  Elimination of manual processes
    FTE allocations spent on manual tasks can be re-purposed to improving processes
    Eliminates the risks of error and improves overall data quality and completeness
  Provides timely feedback on validation whereas today a RARF could take up to 3 days for validation
  Provides a facility for MPs to directly manage their own data
    Stale data can lead to operational incidents with financial impacts
    MPs would no longer be required to request data from ERCOT
  Establishes transparency to what data ERCOT has on record as well as the status of new data
Notes: As we’ve heard from the market, and from internal ERCOT teams, there are multiple benefits to be gained.

## Slide 10: Benefits
Resource asset registration, MP Registration and NDCRC (continued)
  Increases the quality of data
    Managing data submissions in a spreadsheet is a very brittle process (e.g. an RE can break the import process by accidently removing a formula)
    Provides more explanations and context of the data being requested
  Eliminates MPs from having to re-submit a RARF after seasonal and reactive capability testing

## Slide 11: Benefits
Verifiable Costs (VC)
  Establishes automated workflow management, tracking and transparency (e.g. removes email dependency)
    Email is single threaded (e.g. cases where an update is sent to the MP and they are unavailable)
    Process is completely manual today – this would allow integration with downstream systems
    Automating workflow transparency to better meet protocol requirements
  Increases the auditability of VC submissions
  Reduces risks of MMS using stale, outdated or inaccurate data which can impact pricing market-wide
  System could be leveraged for notification of deadlines and due dates