|  |  |  |  | System Planning |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Monthly Status Report July 2013 |  |  |
|  |  | Report Highlights |  |  |  |  |  |  |
|  | - ERCOT is currently tracking 163 active generation interconnection requests totaling over 42,800 MW. This includes over 21,000 MW of wind generation. |  |  |  |  |  |  |  |
|  | - ERCOT is currently reviewing proposed transmission improvements with a total cost of $607 Million - Transmission Projects endorsed in 2013 total $349.8 Million - All projects (in engineering, routing, licensing and construction) total approximately $8.82 Billion. - Transmission Projects energized in 2013 total about $1.29 Billion. - SCR 760 Changes Needed for Information Model Manager and Topology Processor for Planning Models completed with migration of final items to ERCOT production systems on 7/31/2013. |  |  |  |  |  |  |  |

Table of Contents

1.	Generation Interconnection	1

1.1	Signed Generation Interconnection Agreements	1

1.2	New Generation Registering for Commercial Operations	1

1.3	Summary of Generation Interconnection Requests	1

1.4	Projects with Interconnection Agreements	5

1.5	Projects Undergoing Full Interconnection Studies with Confidentiality Waived	6

1.6	Generation Projects Undergoing Full Interconnection Studies	6

1.7	Wind Generation Capacity Installed by Year	9

2.	Regional Planning Group Project Reviews	10

3.	Asynchronous Tie Interconnection	11

4.	Congestion Costs	12

5.	Wind Generation as a Percent of Load	13

6.	Planning Model Activities	14

7.	Other Notable Activities	15

# 1.	Generation Interconnection

Additional information regarding detailed generation interconnection and impact studies is contained in the “Generation Project Interconnection Information” folder in the “Operations and System Planning” area on the ERCOT website:  http://planning.ercot.com/login/login.

## Signed Generation Interconnection Agreements

11INR0062 – Patriot (Petronilla) Wind – 178 MW wind in Nueces County

12INR0029 – Comanche Run Wind – 500 MW wind in Swisher County

12INR0068 – Sendero Wind Energy Project – 78 MW wind in Jim Hogg County

13INR0020a – CPV Rattlesnake Den Ph 1 – 200 MW wind in Glasscock County

13INR0020b -  CPV Rattlesnake Den Ph 2 – 150 MW wind in Glasscock County

## New Generation Approved for Commercial Operations

09INR0001 – Sandy Creek 1 – 970 MW Coal in Mclennan County

The total installed wind capacity is now reported as 10,570 MW by the resource owners through the registration process. Capacity by North, South and West is 832 MW, 2,375 MW, and 7,363 MW respectively.  Eight-hundred fifty MW is able to switch between the West and South zones and is currently shown in the South zone.

## Summary of Generation Interconnection Requests

| GENERATION INTERCONNECTION REQUESTS CURRENTLY UNDER REVIEW |  |
| --- | --- |
| Currently tracking 161 generation interconnection or change requests |  |
| As of July 31, 2013 | Total |
| Security Screening Study | 8 |
| SSS Completed | 14 |
| Full Interconnect Study | 104 |
| FIS Completed | 7 |
| Suspended Studies | 0 |
| Capacity of Suspended Study Projects | 0 |
| Interconnect Agreement Completed | 37 |
| Capacity under Interconnection Agreements | 12,840 |
| Capacity for Grid, MW | 42,872 |
| Wind Capacity, MW | 21,160 |

| Fuel Type | Confidential Projects (MW) | Projects Under Full Study (MW) | Public Projects (MW) | Suspended Studies (MW) | Grand Total (MW) |
| --- | --- | --- | --- | --- | --- |
| Gas-AllOther |  |  | 359 | - | 7,542 |
| Gas-CombinedCycle |  |  | 6,522 | - | 11,729 |
| Total Gas | 2,420 | 9,952 | 6,881 | - | 19,253 |
| Nuclear | - | - | - | - | - |
| Coal | - | - | 240 | - | 240 |
| Wind | 2,627 | 13,859 | 5,062 | - | 21,160 |
| Solar | 346 | 809 | 150 | - | 1,305 |
| Biomass | - | - | - | - | - |
| Storage | - | 874 | 40 | - | 914 |
| Petroleum Coke | - | - | - | - | - |
| Grand Total | 5,393 | 24,639 | 12,840 | - | 42,872 |

County Location of Installed Generation and Interconnection Requests (all fuels)

## Projects with Interconnection Agreements

| Generation Interconnection Agreements as of July 31, 2013 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| INR | Site Name | County | COD | Fuel | MW For Grid | Change from Last Report |
| 11INR0033 | Los Vientos | Cameron | Jul-13 | Wind | 400 |  |
| 12INR0075 | Blue Summit Windfarm | Wilbarger | Jul-13 | Wind | 135 |  |
| 13INR0059 | Hereford Wind | Castro | Oct-13 | Wind | 499 |  |
| 13INR0058 | OCI Alamo 1 | Bexar | Oct-13 | Solar | 50 |  |
| 11INR0094 | White Camp Solar | Kent | Nov-13 | Solar | 100 |  |
| 11INR0013 | Goldthwaite Wind Energy | Mills | Dec-13 | Wind | 150 |  |
| 12INR0068 | Sendero Wind Energy Project | Jim Hogg | Feb-14 | Wind | 78 | New |
| 10INR0089 | Deepwater Energy Storage | Harris | Mar-14 | Storage | 40 | Date |
| 12INR0034 | Stephens Ranch Wind Energy | Borden | Apr-14 | Wind | 378 | Date |
| 11INR0062 | Patriot (Petronilla) Wind | Nueces | Apr-14 | Wind | 178 | New |
| 14INR0012 | Miami Wind 1 Project | Gray | May-14 | Wind | 401 |  |
| 13INR0048 | Spinning Spur Wind Two | Oldham | Jun-14 | Wind | 161 |  |
| 14INR0015 | Deer Park Energy Center | Harris | Jun-14 | Gas | 192 |  |
| 14INR0016 | Channel Energy Center 138/345kV CT | Harris | Jun-14 | Gas | 190 |  |
| 10INR0020a | Panda Temple Power | Bell | Jun-14 | Gas | 809 |  |
| 10INR0021 | Panda Sherman Power | Grayson | Jun-14 | Gas | 809 |  |
| 13INR0021 | Ferguson Replacement Project | Llano | Jul-14 | Gas | 570 |  |
| 14INR0030a2 | Panhandle Wind | Carson | Aug-14 | Wind | 218 |  |
| 11INR0050 | Moore Wind 1 | Crosby | Aug-14 | Wind | 149 |  |
| 13INR0010a | Mariah Wind | Parmer | Oct-14 | Wind | 200 |  |
| 11INR0054 | Midway Farms Wind | San Patricio | Oct-14 | Wind | 161 |  |
| 13INR0020a | CPV Rattlesnake Den Ph 1 | Glasscock | Oct-14 | Wind | 200 | New |
| 13INR0020b | CPV Rattlesnake Den Ph 2 | Glasscock | Oct-14 | Wind | 150 | New |
| 14INR0023 | Longhorn Energy Center | Briscoe | Dec-14 | Wind | 200 | MW for Grid |
| 13INR0005 | Conway Windfarm | Carson | Dec-14 | Wind | 600 |  |
| 06INR0022c | Penascal Wind Farm 3 | Kenedy | Dec-14 | Wind | 202 |  |
| 11INR0079a | South Clay Windfarm | Clay | Dec-14 | Wind | 200 |  |
| 09INR0051 | Mesquite Creek | Borden | Mar-15 | Wind | 249 |  |
| 08INR0018 | Gunsight Mountain | Howard | Aug-15 | Wind | 120 |  |
| 10INR0020b | Panda Temple Power | Bell | Aug-15 | Gas | 780 |  |
| 12INR0029 | Comanche Run Wind | Swisher | Dec-15 | Wind | 500 | New |
| 13INR0010b | Mariah Wind | Parmer | Dec-15 | Wind | 200 |  |
| 13INR0023 | Texas Clean Energy Project | Ector | Jan-16 | Coal | 240 |  |
| 13INR0028 | Antelope Station | Hale | Jun-16 | Gas | 359 |  |
| 10INR0022 | Pondera King Power Project | Harris | Jun-16 | Gas | 1,380 |  |
| 06INR0006 | Cobisa-Greenville | Hunt | Dec-16 | Gas | 1,792 |  |
| 13INR0010c | Mariah Wind | Parmer | Dec-16 | Wind | 200 |  |

## Projects Undergoing Full Interconnection Studies with Confidentiality Waived

| INR | Site Name | County | COD | Fuel | MW for Grid | Change from Last Report |
| --- | --- | --- | --- | --- | --- | --- |

## Generation Projects Undergoing Full Interconnection Studies

| Interconnection Database Reference Number | County | Fuel | Capacity to Grid (MW) | Commercial Operation Date (as specified by the resource developer) |
| --- | --- | --- | --- | --- |
| 13INR0026 | Oldham | Wind | 201 | 12/1/2013 |
| 13INR0052 | Starr | Wind | 200 | 12/1/2013 |
| 13INR0055 | Zapata | Wind | 250 | 12/1/2013 |
| 13INR0056 | Scurry | Wind | 366 | 12/1/2013 |
| 12INR0081a | Upton | Wind | 112 | 12/31/2013 |
| 14INR0024 | Kinney | Solar | 42 | 12/31/2013 |
| 15INR0021 | Starr | Wind | 200 | 12/31/2013 |
| 12INR0055 | Baylor | Wind | 40 | 1/1/2014 |
| 13INR0006 | Gray | Wind | 750 | 1/1/2014 |
| 14INR0013 | Cameron | Wind | 103 | 1/1/2014 |
| 14INR0014 | Val Verde | Solar | 100 | 1/1/2014 |
| 14INR0059 | Kaufman | Gas | 52 | 2/1/2014 |
| 14INR0039 | Ector | Gas | 450 | 3/1/2014 |
| 12INR0060 | Schleicher | Wind | 58 | 4/1/2014 |
| 08INR0019a | Gray | Wind | 250 | 6/1/2014 |
| 08INR0019b | Gray | Wind | 250 | 6/1/2014 |
| 08INR0019c | Gray | Wind | 250 | 6/1/2014 |
| 11INR0057 | Cameron | Wind | 165 | 6/1/2014 |
| 13INR0049 | Harris | Gas | 352 | 6/1/2014 |
| 13INR0057 | Archer | Wind | 65 | 6/1/2014 |
| 14INR0031 | Harris | Gas | 270 | 6/1/2014 |
| 14INR0038 | Galveston | Gas | 390 | 6/1/2014 |
| 14INR0048 | Wilbarger | Wind | 114 | 6/1/2014 |
| 14INR0040 | Hidalgo | Gas | 225 | 6/7/2014 |
| 12INR0059 | Pecos | Solar | 50 | 6/30/2014 |
| 11INR0093 | San Patricio | Wind | 41 | 7/1/2014 |
| 12INR0085 | Stonewall | Wind | 24 | 7/1/2014 |
| 14INR0029 | Uvalde | Solar | 42 | 7/1/2014 |
| 13INR0038 | Swisher | Wind | 300 | 9/15/2014 |
| 14INR0042 | Deaf Smith | Solar | 80 | 9/30/2014 |
| Interconnection Database Reference Number | County | Fuel | Capacity to Grid (MW) | Commercial Operation Date (as specified by the resource developer) |
| 14INR0062 | Hall/Motley | Wind | 161 | 9/30/2014 |
| 14INR0047 | Dickens | Wind | 301 | 10/1/2014 |
| 12INR0070 | Knox | Wind | 300 | 10/15/2014 |
| 12INR0045 | Kleberg | Wind | 135 | 10/31/2014 |
| 13INR0031 | Travis | Solar | 30 | 10/31/2014 |
| 13INR0036 | Hidalgo | Wind | 200 | 10/31/2014 |
| 13INR0025 | Randall | Wind | 150 | 11/1/2014 |
| 14INR0030b | Carson | Wind | 198 | 11/1/2014 |
| 14INR0060 | Haskell | Wind | 400 | 11/1/2014 |
| 14INR0066 | Lamar | Gas | 130 | 11/30/2014 |
| 10INR0085 | Ector | Solar | 57 | 12/1/2014 |
| 11INR0081 | Live Oak | Wind | 72 | 12/1/2014 |
| 11INR0082A | Val Verde | Wind | 50 | 12/1/2014 |
| 11INR0082B | Val Verde | Wind | 150 | 12/1/2014 |
| 13INR0050 | Comanche | Wind | 200 | 12/1/2014 |
| 13INR0054 | Bee | Gas | 0 | 12/1/2014 |
| 14INR0009 | Kent | Wind | 248 | 12/1/2014 |
| 14INR0025a | Floyd | Wind | 200 | 12/1/2014 |
| 14INR0028 | Live Oak | Wind | 300 | 12/1/2014 |
| 14INR0032a | Randall | Wind | 200 | 12/1/2014 |
| 14INR0033 | Armstrong | Wind | 500 | 12/1/2014 |
| 14INR0041 | Willacy | Wind | 114 | 12/1/2014 |
| 14INR0043 | Sterling | Solar | 40 | 12/1/2014 |
| 14INR0044 | Reeves | Solar | 100 | 12/1/2014 |
| 14INR0053 | Oldham | Wind | 161 | 12/1/2014 |
| 14INR0058 | Brewster | Solar | 100 | 12/1/2014 |
| 12INR0079 | Kenedy | Wind | 200 | 12/15/2014 |
| 13INR0045 | Castro | Wind | 288 | 12/30/2014 |
| 13INR0010d | Parmer | Wind | 200 | 12/31/2014 |
| 14INR0020 | Floyd | Wind | 150 | 12/31/2014 |
| 14INR0057b | Erath | Wind | 48 | 12/31/2014 |
| 14INR0067 | Briscoe and Floyd | Wind | 161 | 12/31/2014 |
| 14INR0049_1 | Jack | Wind | 102 | 12/31/2014 |
| 14INR0056 | Mills | Wind | 101 | 12/31/2014 |
| 14INR0057 | Erath | Wind | 48 | 12/31/2014 |
| 14INR0045a | Webb | Wind | 502 | 12/31/2014 |
| 10INR0009 | Castro | Wind | 300 | 3/31/2015 |
| 14INR0027 | Guadalupe | Gas | 471 | 6/1/2015 |
| 15INR0022 | Presidio | Solar | 75 | 6/1/2015 |
| 15INR0028 | Freestone | Gas | 160 | 6/1/2015 |
| 15INR0042 | Hood | Gas | 460 | 6/1/2015 |
| 15INR0027 | Hidalgo | Gas | 79 | 6/1/2015 |
| Interconnection Database Reference Number | County | Fuel | Capacity to Grid (MW) | Commercial Operation Date (as specified by the resource developer) |
| 15INR0023 | Wharton | Gas | 700 | 6/15/2015 |
| 14INR0026 | Presidio | Solar | 28 | 9/1/2015 |
| 15INR0013 | Anderson | Storage/Gas | 324 | 10/1/2015 |
| 15INR0014 | Matagorda | Storage/Gas | 280 | 10/1/2015 |
| 11INR0065 | Nueces | Wind | 350 | 10/31/2015 |
| 14INR0025b | Floyd | Wind | 300 | 12/1/2015 |
| 14INR0032b | Randall | Wind | 300 | 12/1/2015 |
| 12INR0002a | Briscoe | Wind | 200 | 12/31/2015 |
| 13INR0010e | Parmer | Wind | 200 | 12/31/2015 |
| 14INR0018 | Nolan | Solar | 35 | 12/31/2015 |
| 13INR0032 | Andrews | Solar | 30 | 12/31/2015 |
| 15INR0037 | Starr | Wind | 200 | 12/31/2015 |
| 14INR0045b | Webb | Wind | 251 | 12/31/2015 |
| 16INR0010 | Mitchell | Gas | 799 | 2/1/2016 |
| 16INR0005 | Cameron | Gas | 871 | 4/1/2016 |
| 16INR0009 | Calhoun | Gas | 510 | 4/14/2016 |
| 15INR0032 | Hale | Gas | 197 | 5/1/2016 |
| 15INR0033 | Hale | Gas | 197 | 5/1/2016 |
| 16INR0008 | Grimes | Gas | 687 | 5/1/2016 |
| 16INR0004 | Cameron | Gas | 730 | 6/1/2016 |
| 16INR0006 | Angelina | Gas | 785 | 6/1/2016 |
| 16INR0007 | Hidalgo | Gas | 95 | 6/1/2016 |
| 16INR0003 | Brazoria | Gas | 11 | 6/1/2016 |
| 14INR0011 | Swisher | Storage/Gas | 270 | 7/1/2016 |
| 12INR0002b | Briscoe | Wind | 200 | 12/31/2016 |
| 13INR0010f | Parmer | Wind | 200 | 12/31/2016 |
| 12INR0018 | Gray | Wind | 500 | 3/31/2017 |
| 17INR0004 | Hale | Gas | 202 | 5/1/2017 |
| 17INR0002 | Henderson | Gas | 489 | 6/1/2017 |
| 11INR0040 | freestone | Gas | 640 | 3/1/2018 |

## Wind Generation Capacity Installed by Year

# Regional Planning Group Project Reviews

- Oncor submitted the Permian Basin to Moss to Odessa EHV 345 kV project. This is a Tier 1 project that is estimated to cost approximately $75 million. This project is currently under ERCOT independent review.

- Sharyland Utilities submitted the Stanton/Midland Northern loop project. This project was initially classified as a Tier 3 and and the project has statisfied all the RPG comments.  In accordance with Protocol Section 3.11.4.5, the Stanton/Midland Northern loop project has been reclassified as a “Tier 4 Neutral Project.”

- CenterPoint Energy submitted the Houston Region Import Capacity project. This is a Tier 1 project that is estimated to cost between $297 to $532 million. This project has been submitted for RPG comments.

- Garland Power & Light (GP&L) and Cross Texas Transmission (CTT) have jointly submitted the Houston Import project. This is a Tier 1 project that is estimated to cost between $ 195 to $ 317 million. This project has been submitted for RPG comments.

- Denton Municipal Electric has submitted the Spencer-Pockrus 138 kV project. The project is estimated to cost approximately $5.5 million. The project been submitted for RPG comments. The Spencer-Pockrus 138 kV project is initially classified as a Tier 3 project and once the RPG comments are resolved it will be reclassified as a Tier 4 Neutral project..

# Asynchronous Tie Interconnection

| Project | Notification to ERCOT | Reliability Study | RPG Review | Interconnection Agreement | In-service Year |
| --- | --- | --- | --- | --- | --- |
| Railroad DC tie expansion (150 MW - CFE) |  |  |  |  | 2014 |
| Southern Cross HVDC (3000 MW - SERC) |  |  |  |  |  |
| Tres Amigas (1500 MW - SPP) |  |  |  |  |  |

Color Legend

|  | In progress |
| --- | --- |
|  | Complete |

# Congestion Costs

Dollars shown in RUC Make Whole payment graph are of settlement quality.

RUC net Make Whole payment in $mm

Monthly Average LMP

# Wind Generation as a Percent of Load

One-hour average of total wind power output as a percentage of ERCOT load.

The hourly wind generation and load data used to develop these charts are available in the Nodal Monthly Aggregate WPF Report provided by ERCOT Operations to the QMWG.

# Planning Model Activities

- The short term calendar of major planning model events follows:

  - Jun 14, 2013	13DSA/DSB TPIT updates posted

  - Jul 15, 2013	14 Data Set A posted

  - Aug 1, 2013	Project start of 14 Data Set B case build

  - Aug 7, 2013	SSWG Meeting to discuss HWLL case

- Status update on SCR760, Changes Needed for Information Model Manager and Topology Processor for Planning Models, which was approved by the ERCOT Board in March 2011.

- Final bundle migrated to ERCOT Production system on 7/31/2013.  SCR760 is COMPLETE.

  - Bundle 1 (Items 3, 7 and 8): In Production.

  - Bundle 2 (Items 2a, 4, 9):  In Production.

  - Bundle 3 (Item 5, 2b, 2c):  In Production

  - Bundle 4 (Items 1, 6):  In Production.

| SCR Sub Part | SCR Description | Status |
| --- | --- | --- |
| SCR760-1 | Upgrade to PSS/E v32 | Production |
| SCR760-2 | Distribution Capacitor banks | Production |
| SCR760-3 | Zero Impedance Line Ratings | Production |
| SCR760-4 | Associate Loads and Capacitor banks with the correct CNG | Production |
| SCR760-5 | Additional Transformer Data for Planning | Production |
| SCR760-6 | FACTS Devices | Production |
| SCR760-7 | Assign valid PSSE IDs to Breakers/ Switches/ Series Devices | Production |
| SCR760-8 | Phase shift of Autos for short circuit studies | Production |
| SCR760-9 | Multisection Line Grouping | Production |

Table 1:  In the following table:

- Red will be used to show status of Not Submitted, meaning that the SCR sub part has not been submitted to Siemens as a Service Request.

- Yellow will indicate that the SCR sub part has been submitted.  The color will remain yellow and the status will change in order to Submitted, Planning (Requirements, SOW, Code Writing), Release (Siemens produces first code to test), and Testing (code has completed internal test and is moving through release management).

- Green will indicate that the code has been tested and installed on the machines that ERCOT uses to produce Topology Processor output for Planning and CRR.

# Other Notable Activities

- The project to complete the missing and questionable data for the remaining Resource Asset Registration Forms (RARF) that are still incomplete is underway.  ERCOT and Siemens created a list of 3387 individual data items that are missing or suspect.  To date, 33 calls to Resource Entities regarding 51 different sites and 482 items within the list have been completed.

- ERCOT is working on the 2013 Regional Transmission Plan (RTP). The Reliability start cases including initial projects (previous 5YTP projects) was posted at the ERCOT POI on July 27, 2013. ERCOT is currently working on Reliability analysis to resolve the thermal and voltage issues.

- ERCOT is performing the study to analyze the system needs in the West Texas area due to oil and gas load growth. The preliminary reliability analysis results were presented at the June RPG meeting. The steady-state base cases used for this study are posted at the ERCOT POI. ERCOT is currently working on preparing the West Texas Sensitivity study report.

- ERCOT is preparing the report on the results of the Long-Term System Assessment and the improvements to the long-term study process as a result of the grant received from the Department of Energy.

- ERCOT is preparing a Request For Proposal (RFP) in order to hire a consultant to perform a small signal stability study.  A draft study scope was presented to the PDCWG in July in order to obtain comments.