SCR756 Part B – High Level Timeline DRAFT:

- Planning Phase: ~ 2-3 Months

  - July/August – Review remaining Requirements and Use Cases for PartB before the initial planning phase begins

- Execution/Development: ~ 3 Months

- Testing: ~ 3 Months

  - Includes UAT Testing/ITesting/Training documentation

  - Begin developing training materials and identify dates for training sessions

  - Start identifying sections in the User’s Guide (UG) to update (Start August 2013 – End of 2013)

    - Define what’s not working well in the current UG

    - Clarification

- Market Training: ~ 1 Month (April 20, 2014)

  - Coordinate training sessions close to implementation weekend at least 5 weeks before migration weekend

  - TF provide ERCOT with final draft for PartB training materials.  (February 2014)

- Implementation: ~ Weekend (End of May 2014)

  - Usually implemented during an ERCOT I.T. Retail release (Included in SLA)

- Stabilization: ~ 4 -6 Weeks

  - Lessons Learned