|  |  |  |  | System Planning |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Monthly Status Report August 2013 |  |  |
|  |  | Report Highlights |  |  |  |  |  |  |
|  | - ERCOT is currently tracking 162 active generation interconnection requests totaling over 41,400 MW. This includes over 20,900 MW of wind generation. |  |  |  |  |  |  |  |
|  | - ERCOT is currently reviewing proposed transmission improvements with a total cost of $750 Million - Transmission Projects endorsed in 2013 total $349.8 Million - All projects (in engineering, routing, licensing and construction) total approximately $8.82 Billion. - Transmission Projects energized in 2013 total about $1.29 Billion. |  |  |  |  |  |  |  |

Table of Contents

1.	Generation Interconnection	1

1.1	Signed Generation Interconnection Agreements	1

1.2	New Generation Approved for Commercial Operations	1

1.3	Summary of Generation Interconnection Requests	1

1.4	Projects with Interconnection Agreements	4

1.5	Projects Undergoing Full Interconnection Studies with Confidentiality Waived	5

1.6	Generation Projects Undergoing Full Interconnection Studies	6

1.7	Wind Generation Capacity Installed by Year	9

2.	Regional Planning Group Project Reviews	11

3.	Asynchronous Tie Interconnection	12

4.	Congestion Costs	13

5.	Planning Model Activities	14

6.	Other Notable Activities	14

# 1.	Generation Interconnection

Additional information regarding detailed generation interconnection and impact studies is contained in the “Generation Project Interconnection Information” folder in the “Operations and System Planning” area on the ERCOT website:  http://planning.ercot.com/login/login.

## Signed Generation Interconnection Agreements

13INR0057 – Windhorst 2 – 65 MW located in Archer County

14INR0012a – Miami Wind 1 Project – 231 MW located in Gray County

14INR0012b - Miami Wind 1 Project – 170 MW located in Gray County

11INR0057 – Cameron County Wind – 165 MW located in Cameron County

## New Generation Approved for Commercial Operations

11INR0033 – Los Vientos (LV1A) – 200 MW Wind in Cameron County

The total installed wind capacity is now reported as 10,570 MW by the resource owners through the registration process. Capacity by North, South and West is 832 MW, 2,375 MW, and 7,363 MW respectively.  Eight-hundred fifty MW is able to switch between the West and South zones and is currently shown in the South zone.

## Summary of Generation Interconnection Requests

| GENERATION INTERCONNECTION REQUESTS CURRENTLY UNDER REVIEW |  |
| --- | --- |
| Currently tracking 161 generation interconnection or change requests |  |
| As of August 31, 2013 | Total |
| Security Screening Study | 4 |
| SSS Completed | 13 |
| Full Interconnect Study | 97 |
| FIS Completed | 7 |
| Suspended Studies | 0 |
| Capacity of Suspended Study Projects | 0 |
| Interconnect Agreement Completed | 41 |
| Capacity under Interconnection Agreements | 13,485 |
| Capacity for Grid, MW | 41,403 |
| Wind Capacity, MW | 20,932 |
| Cancelled Projects | 5 |

| Fuel Type | Confidential Projects (MW) | Projects Under Full Study (MW) | Public Projects (MW) | Suspended Studies (MW) | Grand Total (MW) |
| --- | --- | --- | --- | --- | --- |
| Gas-AllOther |  |  | 374 | - | 4,428 |
| Gas-CombinedCycle |  |  | 6,522 | - | 13,568 |
| Total Gas | 320 | 10,780 | 6,896 | - | 17,996 |
| Nuclear | - | - | - | - | - |
| Coal | - | - | 240 | - | 240 |
| Wind | 2,111 | 13,859 | 5,959 | - | 20,931 |
| Solar | 271 | 809 | 150 | - | 1,322 |
| Biomass | - | - | - | - | - |
| Storage | - | 874 | 40 | - | 914 |
| Petroleum Coke | - | - | - | - | - |
| Grand Total | 2,702 | 25,416 | 13,285 | - | 41,403 |

County Location of Installed Generation and Interconnection Requests (all fuels)

## Projects with Interconnection Agreements

| Generation Interconnection Agreements as of August 31, 2013 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| INR | Site Name | County | COD | Fuel | MW For Grid | Change from Last Report |
| 12INR0075 | Blue Summit Windfarm | Wilbarger | Oct-13 | Wind | 135 |  |
| 11INR0033 | Los Vientos | Cameron | Oct-13 | Wind | 200 | MW for Grid |
| 13INR0058 | OCI Alamo 1 | Bexar | Oct-13 | Solar | 50 |  |
| 11INR0094 | White Camp Solar | Kent | Nov-13 | Solar | 100 |  |
| 11INR0013 | Goldthwaite Wind Energy | Mills | Dec-13 | Wind | 150 |  |
| 12INR0068 | Sendero Wind Energy Project | Jim Hogg | Feb-14 | Wind | 78 |  |
| 10INR0089 | Deepwater Energy Storage | Harris | Mar-14 | Storage | 40 |  |
| 12INR0034 | Stephens Ranch Wind Energy | Borden | Apr-14 | Wind | 378 |  |
| 13INR0059 | Hereford Wind | Castro | Apr-14 | Wind | 499 |  |
| 13INR0057 | Windthorst 2 | Archer | Jun-14 | Wind | 65 | New |
| 13INR0048 | Spinning Spur Wind Two | Oldham | Jun-14 | Wind | 161 |  |
| 14INR0015 | Deer Park Energy Center | Harris | Jun-14 | Gas | 192 |  |
| 14INR0016 | Channel Energy Center 138/345kV CT | Harris | Jun-14 | Gas | 190 |  |
| 11INR0062 | Patriot (Petronilla) Wind | Nueces | Jun-14 | Wind | 178 |  |
| 14INR0012a | Miami Wind 1 Project | Gray | Jul-14 | Wind | 231 | New |
| 13INR0021 | Ferguson Replacement Project | Llano | Jul-14 | Gas | 570 |  |
| 14INR0030a_2 | Panhandle Wind | Carson | Aug-14 | Wind | 218 |  |
| 10INR0021 | Panda Sherman Power | Grayson | Jun-14 | Gas | 720 |  |
| 13INR0040 | Rentech Project | Harris | Aug-14 | Gas | 15 | Name change |
| 10INR0020a | Panda Temple Power | Bell | Jun-14 | Gas | 717 |  |
| 11INR0050 | Moore Wind 1 | Crosby | Jun-14 | Wind | 149 |  |
| 13INR0010a | Mariah Wind | Parmer | Oct-14 | Wind | 200 |  |
| 13INR0020a | CPV Rattlesnake Den Ph 1 | Glasscock | Oct-14 | Wind | 200 |  |
| 13INR0020b | CPV Rattlesnake Den Ph 2 | Glasscock | Oct-14 | Wind | 150 |  |
| 11INR0054 | Midway Farms Wind | San Patricio | Oct-14 | Wind | 161 |  |
| 14INR0023 | Longhorn Energy Center | Briscoe | Dec-14 | Wind | 200 |  |
| 13INR0005 | Conway Windfarm | Carson | Dec-14 | Wind | 600 |  |
| 11INR0057 | Cameron County Wind | Cameron | Dec-14 | Wind | 165 | New |
| 11INR0079a | South Clay Windfarm | Clay | Dec-14 | Wind | 200 |  |
| 06INR0022c | Penascal Wind Farm 3 | Kenedy | Dec-14 | Wind | 202 |  |
| 09INR0051 | Mesquite Creek | Borden | Jan-15 | Wind | 249 |  |
| 08INR0018 | Gunsight Mountain | Howard | Aug-15 | Wind | 120 |  |
| 14INR0012b | Miami Wind 1 Project | Gray | Aug-15 | Wind | 170 | New |
| 10INR0020b | Panda Temple Power | Bell | Aug-15 | Gas | 780 |  |
| 13INR0010b | Mariah Wind | Parmer | Dec-15 | Wind | 200 |  |
| 12INR0029 | Comanche Run Wind | Swisher | Dec-15 | Wind | 500 |  |
| 13INR0023 | Texas Clean Energy Project | Ector | Jan-16 | Coal | 240 |  |
| 13INR0028 | Antelope Station | Hale | Jun-16 | Gas | 359 |  |
| 10INR0022 | Pondera King Power Project | Harris | Jun-16 | Gas | 1,380 |  |
| 06INR0006 | Cobisa-Greenville | Hunt | Dec-16 | Gas | 1,792 |  |
| 13INR0010c | Mariah Wind | Parmer | Dec-16 | Wind | 200 |  |

## Projects Undergoing Full Interconnection Studies with Confidentiality Waived

| INR | Site Name | County | COD | Fuel | MW for Grid | Change from Last Report |
| --- | --- | --- | --- | --- | --- | --- |

## Generation Projects Undergoing Full Interconnection Studies

| Interconnection Database Reference Number | County | Fuel | Capacity to Grid (MW) | Commercial Operation Data (as specified by the resource developer) |
| --- | --- | --- | --- | --- |
| 12INR0055 | Baylor | Wind | 40 | Jan-14 |
| 13INR0006 | Gray | Wind | 750 | Jan-14 |
| 14INR0014 | Val Verde | Solar | 100 | Jan-14 |
| 14INR0039 | Ector | Gas | 450 | Mar-14 |
| 12INR0060 | Schleicher | Wind | 58 | Apr-14 |
| 14INR0013 | Cameron | Wind | 103 | Apr-14 |
| 14INR0024 | Kinney | Solar | 42 | Apr-14 |
| 08INR0019a | Gray | Wind | 250 | Jun-14 |
| 08INR0019b | Gray | Wind | 250 | Jun-14 |
| 08INR0019c | Gray | Wind | 250 | Jun-14 |
| 13INR0026 | Oldham | Wind | 201 | Jun-14 |
| 14INR0031 | Harris | Gas | 270 | Jun-14 |
| 14INR0038 | Galveston | Gas | 390 | Jun-14 |
| 14INR0048 | Wilbarger | Wind | 114 | Jun-14 |
| 14INR0040 | Hidalgo | Gas | 225 | Jun-14 |
| 12INR0059 | Pecos | Solar | 50 | Jun-14 |
| 11INR0093 | San Patricio | Wind | 41 | Jul-14 |
| 12INR0085 | Stonewall | Wind | 24 | Jul-14 |
| 14INR0029 | Uvalde | Solar | 42 | Jul-14 |
| 14INR0059 | Kaufman | Gas | 52 | Aug-14 |
| 13INR0055 | Zapata | Wind | 250 | Sep-14 |
| 13INR0038 | Swisher | Wind | 300 | Sep-14 |
| 14INR0042 | Deaf Smith | Solar | 80 | Sep-14 |
| 14INR0062 | Hall/Motley | Wind | 161 | Sep-14 |
| 14INR0047 | Dickens | Wind | 301 | Oct-14 |
| 12INR0070 | Knox | Wind | 300 | Oct-14 |
| 12INR0045 | Kleberg | Wind | 135 | Oct-14 |
| 13INR0036 | Hidalgo | Wind | 200 | Oct-14 |
| 13INR0031 | Travis | Solar | 30 | Oct-14 |
| 11INR0065 | Nueces | Wind | 350 | Oct-14 |
| 13INR0025 | Randall | Wind | 150 | Nov-14 |
| 14INR0060 | Haskell | Wind | 400 | Nov-14 |
| 14INR0030b | Carson | Wind | 198 | Nov-14 |
| 13INR0056 | Scurry | Wind | 366 | Nov-14 |

| Interconnection Database Reference Number | County | Fuel | Capacity to Grid (MW) | Commercial Operation Data (as specified by the resource developer) |
| --- | --- | --- | --- | --- |
| 14INR0066 | Lamar | Gas | 130 | Nov-14 |
| 13INR0050 | Comanche | Wind | 200 | Dec-14 |
| 14INR0025a | Floyd | Wind | 200 | Dec-14 |
| 14INR0032a | Randall | Wind | 200 | Dec-14 |
| 10INR0085 | Ector | Solar | 57 | Dec-14 |
| 11INR0081 | Live Oak | Wind | 72 | Dec-14 |
| 11INR0082a | Val Verde | Wind | 50 | Dec-14 |
| 11INR0082b | Val Verde | Wind | 150 | Dec-14 |
| 13INR0054 | Bee | Gas | 0 | Dec-14 |
| 14INR0009 | Kent | Wind | 248 | Dec-14 |
| 14INR0028 | Live Oak | Wind | 300 | Dec-14 |
| 14INR0033 | Armstrong | Wind | 500 | Dec-14 |
| 14INR0041 | Willacy | Wind | 114 | Dec-14 |
| 14INR0043 | Sterling | Solar | 40 | Dec-14 |
| 14INR0044 | Reeves | Solar | 100 | Dec-14 |
| 14INR0058 | Brewster | Solar | 100 | Dec-14 |
| 12INR0079 | Kenedy | Wind | 200 | Dec-14 |
| 13INR0045 | Castro | Wind | 288 | Dec-14 |
| 13INR0010d | Parmer | Wind | 200 | Dec-14 |
| 13INR0052 | Starr | Wind | 200 | Dec-14 |
| 14INR0053 | Oldham | Wind | 161 | Dec-14 |
| 14INR0020 | Floyd | Wind | 150 | Dec-14 |
| 14INR0045a | Webb | Wind | 502 | Dec-14 |
| 14INR0049_1 | Jack | Wind | 102 | Dec-14 |
| 14INR0049_2 | Jack | Wind | 102 | Dec-14 |
| 14INR0056 | Mills | Wind | 101 | Dec-14 |
| 14INR0057a | Erath | Wind | 48 | Dec-14 |
| 14INR0057b | Erath | Wind | 48 | Dec-14 |
| 14INR0067 | Briscoe and Floyd | Wind | 161 | Dec-14 |
| 15INR0036 | Uvalde | Solar | 105 | Mar-15 |
| 10INR0009 | Castro | Wind | 300 | Mar-15 |
| 15INR0021 | Starr | Wind | 200 | May-15 |
| 14INR0027 | Guadalupe | Gas | 471 | Jun-15 |
| 15INR0022 | Presidio | Solar | 75 | Jun-15 |
| 15INR0027 | Hidalgo | Gas | 79 | Jun-15 |

| Interconnection Database Reference Number | County | Fuel | Capacity to Grid (MW) | Commercial Operation Data (as specified by the resource developer) |
| --- | --- | --- | --- | --- |
| 15INR0028 | Freestone | Gas | 160 | Jun-15 |
| 15INR0042 | Hood | Gas | 460 | Jun-15 |
| 15INR0023 | Wharton | Gas | 700 | Jun-15 |
| 14INR0026 | Presidio | Solar | 30 | Sep-15 |
| 15INR0013 | Anderson | Storage/Gas | 324 | Oct-15 |
| 15INR0014 | Matagorda | Storage/Gas | 280 | Oct-15 |
| 14INR0030a_1 | Carson | Wind | 322 | Nov-15 |
| 14INR0025b | Floyd | Wind | 300 | Dec-15 |
| 14INR0032b | Randall | Wind | 300 | Dec-15 |
| 15INR0035 | Kenedy | Wind | 200 | Dec-15 |
| 13INR0010e | Parmer | Wind | 200 | Dec-15 |
| 12INR0002a | Briscoe | Wind | 200 | Dec-15 |
| 14INR0018 | Nolan | Solar | 20 | Dec-15 |
| 13INR0032 | Andrews | Solar | 30 | Dec-15 |
| 14INR0045b | Webb | Wind | 251 | Dec-15 |
| 15INR0037 | Starr | Wind | 200 | Dec-15 |
| 16INR0010 | Mitchell | Gas | 799 | Feb-16 |
| 16INR0005 | Cameron | Gas | 871 | Apr-16 |
| 16INR0009 | Calhoun | Gas | 510 | Apr-16 |
| 15INR0032 | Hale | Gas | 197 | May-16 |
| 15INR0033 | Hale | Gas | 197 | May-16 |
| 16INR0008 | Grimes | Gas | 687 | May-16 |
| 16INR0003 | Brazoria | Gas | 11 | Jun-16 |
| 16INR0004 | Cameron | Gas | 730 | Jun-16 |
| 16INR0006 | Angelina | Gas | 785 | Jun-16 |
| 16INR0007 | Hidalgo | Gas | 95 | Jun-16 |
| 17INR0004 | Hale | Gas | 202 | Jun-16 |
| 14INR0011 | Swisher | Storage/Gas | 270 | Jul-16 |
| 16INR0013 | Nacogdoches | Gas | 215 | Jul-16 |
| 13INR0010f | Parmer | Wind | 200 | Dec-16 |
| 12INR0002b | Briscoe | Wind | 200 | Dec-16 |
| 12INR0018 | Gray | Wind | 500 | Mar-17 |
| 17INR0002 | Henderson | Gas | 489 | Jun-17 |
| 17INR0003 | Jackson | Gas | 965 | Jun-17 |
| 11INR0040 | Freestone | Gas | 640 | Mar-18 |

## Wind Generation Capacity Installed by Year

# Regional Planning Group Project Reviews

- Oncor submitted the Permian Basin to Moss to Odessa EHV 345 kV project. This is a Tier 1 project that is estimated to cost approximately $75 million. This project is currently under ERCOT independent review.

- CenterPoint Energy submitted the Houston Region Import Capacity project. This is a Tier 1 project that is estimated to cost between $297 to $532 million. This project has received several RPG comments and it is under study mode.

- Garland Power & Light (GP&L) and Cross Texas Transmission (CTT) have jointly submitted the Houston Import project. This is a Tier 1 project that is estimated to cost between $195 to $317 million. This project has received several RPG comments and it is under study mode.

- Denton Municipal Electric has submitted the Spencer-Pockrus 138 kV project. The project is estimated to cost approximately $5.5 million. The project is under study mode. The Spencer-Pockrus 138 kV project is initially classified as a Tier 3 project and once the RPG comments are resolved it will be reclassified as a Tier 4 Neutral project.

- Lone Star Transmission has submitted the Houston Import project. This is a Tier 1 project that is estimated to cost between $417 to $675 million. This project has been submitted for RPG comments.

# Asynchronous Tie Interconnection

| Project | Notification to ERCOT | Reliability Study | RPG Review | Interconnection Agreement | In-service Year |
| --- | --- | --- | --- | --- | --- |
| Railroad DC tie expansion (150 MW - CFE) |  |  |  |  | 2014 |
| Southern Cross HVDC (3000 MW - SERC) |  |  |  |  |  |
| Tres Amigas (1500 MW - SPP) |  |  |  |  |  |

Color Legend

|  | In progress |
| --- | --- |
|  | Complete |

# Congestion Costs

Dollars shown in RUC Make Whole payment graph are of settlement quality.

RUC net Make Whole payment in $mm

Monthly Average LMP

# Planning Model Activities

- The short term calendar of major planning model events follows:

  - Aug 1, 2013	Start of 14 Data Set B case build

  - Aug 7, 2013	SSWG Meeting to discuss HWLL case

  - Sept 30 – Oct 2, 2013	SSWG Data Set B Meeting

  - Oct 15, 2013	SSWG Data Set B posted

  - Oct 31, 2013	Contingency files posted

# Other Notable Activities

- The project to complete the missing and questionable data for the remaining Resource Asset Registration Forms (RARF) that are still incomplete is underway.  ERCOT and Siemens created a list of 3387 individual data items that are missing or suspect.

- ERCOT is working on the 2013 Regional Transmission Plan (RTP). The Reliability start cases including initial projects (previous 5YTP projects) was posted at the ERCOT POI on Aug. 19, 2013. ERCOT is currently working on reliability analysis to resolve the thermal and voltage issues.

- ERCOT has performed the study to analyze the system needs in the West Texas area due to oil and gas load growth. The final reliability and economic study results were presented at the August RPG meeting. ERCOT is currently working on the West Texas Sensitivity study report and anticipates to complete the report in Sept. 2013.

- ERCOT is preparing the report on the results of the Long-Term System Assessment and the improvements to the long-term study process as a result of the grant received from the Department of Energy.

- ERCOT has issued a Request For Proposal (RFP) in order to hire a consultant to perform a small signal stability study.