## Slide 1
Project Update and Summary of Project Priority List (PPL) Activity to Date
September 19, 2013

## Slide 2: 2013 Project Update – Agenda
  Project Portfolio Update p. 3-7
    Recent/Upcoming Project Highlights
    2013 Release Targets
    2013 Project Spending Update
    2014 Release Targets
  Appendix
    Project Portfolio Gantt Chart p. 8-16
Location of Project Priority List (PPL): http://www.ercot.com/services/projects/index

## Slide 3: Recent/Upcoming Project Highlights
Release 4 Off-Cycle Go-Lives (August) Complete
  Mobile Application Enhancements
Release 5 Go-Lives (9/23/2013 – 9/29/2013) In-Flight
  NPRR207 – Unit Deselection
  NPRR385 – Negative Price Floor
  NPRR416 – Removal of the RUC Clawback Charge for Resources Other than RMR Units
  NPRR457 – Daily Update of New ESI IDs and AMS Meter and Switch Hold Indicators Changes
  NPRR479 – Daily Net Outage MW
  NPRR514 – Seasonal Generation Resource
  NOGRR101 – Market Notice for DC-TIE Outage Information
  SCR770 – Revision to Outage Scheduling Entry for Resource Maintenance Outage Level Designation
  Siebel Upgrade
  EPG Synchrophasor Upgrade
Release 5 Off-Cycle Go-Lives (October 2013) In-Flight
  Cyber Security Project #7
  OTS Forum Hotline
Note: Projected Go-Live dates are subject to change. Please watch for market notices as the effective dates approach.

## Slide 4: 2013 Release Targets – Board-Approved NPRRs/SCRs/xGRRs
Release Approach | Release 1 2/11 – 2/15 | Release 2 4/22 – 4/26 | Release 3 6/10 – 6/14 | Release 4 7/29 – 8/2 | Release 5 9/23 – 9/29 | Release 6 12/9-12/13 | 2013 TBD
On-Cycle | NPRR260 NPRR313 NPRR322 NPRR377 NPRR397 NPRR407(a) NPRR464 NPRR469 SCR768 | NPRR456 | NPRR481 NPRR520(a) NOGRR093 | NPRR393 NPRR461 NPRR520(b) SCR760(d) | NPRR207 NPRR385 NPRR416 NPRR457 NPRR479 NPRR514 NOGRR101 SCR770 | NPRR240 NPRR272 NPRR425(a) NPRR476 NPRR492 NOGRR105 | NPRR153 NPRR210 NPRR495
Off-Cycle |  | NPRR463 | SCR773 |  |  | NPRR484 (1a) | NPRR210 NPRR240 NPRR272 NOGRR105
Counts Total = 33 | 9 | 2 | 4 | 4 | 8 | 4 | 2
Early April
None
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
(a), (b), etc. indicates multiple phases
Release targets are subject to change
Red Text: New additions and target release changes
Strike-Through Text: Previous target release changes
None
October
None
Late May
Moved to Future Years
NPRR407(a) – MMS portion
NPRR425(a) – RARF, EMS portions
NPRR484(1a) – initial CMM/CRR components
NPRR520(a) – MMS, MIS, CDR portions
NPRR520(b) – EMS, NMMS, ICCP portions
SCR760(d) – final phase
ü
ü
ü
ü
ü
ü

## Slide 5: 2013 Cash Flow Projection – Approved Projects
ERCOT Board of Directors approved a project budget increase of $1M on 5/14/2013
Revised 2013 project budget is $16M

## Slide 6: 2014 Release Targets – Board-Approved NPRRs/SCRs/xGRRs
Release Approach | Release 1 TBD | Release 2 TBD | Release 3 TBD | Release 4 TBD | Release 5 TBD | Release 6 TBD | 2014 TBD
On-Cycle | NPRR425(b) NPRR500 NOGRR105 SCR772 | NPRR272 NPRR407(b) NPRR485 SCR756(b) SCR769 SCR771 OBD (Shadow Price Caps) | NPRR256 NPRR532 NPRR555 | NPRR439 NOGRR084 |  |  | NPRR240 NPRR327 NPRR455 NPRR467 NPRR484(1b) NPRR485 NPRR487 NPRR491 NPRR509 NPRR524 NPRR527 NPRR543
Off-Cycle |  |  |  |  |  |  | NPRR553
Counts Total = 28 | 4 | 7 | 3 | 2 | 0 | 0 | 12
None
None
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
None
None
None
None
NPRR407(b) – CRR portion
NPRR425(b) – GREDP, EIS portions
NPRR484(Ph1b) – Remaining Phase 1 items
NPRR484(Ph2) – S&B portions
SCR756(b) – Remaining portions of SCR
(a), (b), etc. indicates multiple phases
Red Text: New additions and target release changes
Strike-Through Text: Previous target release changes

## Slide 7: Business Integration Update – Appendix
  Appendix
    9/11/2013 Project Gantt
      In-flight items sorted by Project End Date
      “Not Started” items sorted by Project Start Date

## Slide 8
Project Portfolio Status – as of 9/11/2013

## Slide 9
Project Portfolio Status – as of 9/11/2013

## Slide 10
Project Portfolio Status – as of 9/11/2013

## Slide 11
Project Portfolio Status – as of 9/11/2013

## Slide 12
Project Portfolio Status – as of 9/11/2013

## Slide 13
Project Portfolio Status – as of 9/11/2013

## Slide 14
Project Portfolio Status – as of 9/11/2013

## Slide 15
Project Portfolio Status – as of 9/11/2013

## Slide 16
Project Portfolio Status – as of 9/11/2013