SCR756 Part B – High Level Timeline DRAFT:

- Planning Phase: ~ (End of 2013)

  - July/August – Review remaining Requirements and Use Cases for PartB before the initial planning phase begins

  - Business requirements recevived from ERCOT end of Oct. 2013

- Execution/Development: ~ 3 Months( Start Jan 2014 –March 2014)

- Testing: ~ 3 Months( Start April 2014)

  - Includes UAT Testing/ITesting/Training documentation

  - Begin developing training materials and identify dates for training sessions

  - Start identifying sections in the User’s Guide (UG) to update (Start August 2013 – End of 2013)

    - Define what’s not working well in the current UG

    - Clarification

- Market Training: ~ 1 Month ( May 2014)

  - Coordinate training sessions close to implementation weekend at least 5 weeks before migration weekend

  - TF provide ERCOT with final draft for PartB training materials.  (February 2014)

- Implementation: ~ Weekend (End of  June 2014)

  - Usually implemented during an ERCOT I.T. Retail release (Included in SLA)

- Stabilization: ~ 4 -6 Weeks

  - Lessons Learned