## Settlement Timeline Issues List
Settlement Timeline Change - Issues List
Purpose: Raise awareness of issues and impacts resulting from the reduction of the RTM Settlement timeline required by NPR509, Shortened RTM Settlement Timeline, such that issues can be considered prior to effective date of NPRR509 Phase 2. NPRR 509 - Phase 1: RTM Settlement Statements issued on Operating Day + 8, effective beginning OD April 1, 2013 NPRR 509 - Phase 2: RTM Settlement Statements issued on Operating Day + 7, tentatively effective on August 1, 2013 barring any BOD approved proposal to delay the transition to OD+7. http://www.ercot.com/mktrules/issues/nprr/501-525/509/index
Please raise issues at the weekly WebEx calls (Mondays 3-3:30p) or log via email to CSWG leadership (Jim Galvin and Heddie Lookadoo) and ERCOT (Pamela Shaw). james.galvin@luminant.com heddie.lookadoo@nrgenergy.com pshaw@ercot.com
REF # | COMPANY | ISSUE CATEGORY | DESCRIPTION | PRIORITY provided by MP | ERCOT Lead | Status | ERCOT / MP Comments | ERCOT Ranking
1 | PCI Thompson Thyall | Extracts | Settlement extracts received on Tues/Wed randomly arrive later than Statement (but within 48 hour deadline) |  | S. Lang | closed | Most likely DAM CODE: We have experienced some creep on runtimes since the December system outage, but nothing real outrageous and it is probably due to the increased backup/recovery monitoring that was put in place after the big outage.
2 | Tenaska John Moschos Eli Worley | Retail Extracts timeline | Are the retail extracts triggered by the Settlement statement and under the same 48 hour timeline for delivery? Will the Retail Extracts timeline, in general, be compressed as the Settlement timeline is compressed? |  | J. Mikus | open | 4/29/13 update: The retail extracts published on a given date include data that was added, changed or deleted to/from the settlement system during a window that is 72-48 hours back; these are not keyed off of statement approval. To note, for generation site ESI IDs that ERCOT populates when the generation site is "net load" the data is not added to the system until the Data Aggregation job is executed; currently this is on OD+7. The data populated to such ESI IDs is a calculated output of the Data Aggregation process. Following the methodology for the retail extracts, the data will not be included in the retail extracts until 3 days later, which is 10 days after the Operating Day. Given the current design and the removal of the buffer window between Data Aggregation execution and posting of the statement, it is anticipated that data for Generation Site ESI IDs which are populated by ERCOT would continue to be available 2 days after posting of Settlement Statements and settlement extracts. From the IDR user guide: The Supplemental IDR Required Interval Data Extract is posted daily using the same ADDTIME window as the ESIID Service History & Usage Extract. With the Supplemental IDR Required Interval Data Extract being used in conjunction with the ESIID Service History and Usage Extract, these extracts utilize the same DDL for data storage though they do each have their own User Guides. From the ESIID Service History and Usage Extract user guide: ERCOT will post the ESIID Service History & Usage Extract Data to the ERCOT MIS every day by EOD 23:59:59. Record Addtimes are three days prior - i.e. On Thursdays, we run for Monday-Tuesday dataset. The extracts are available seven days a week and are posted daily if data is available for the given Market Participant. 4/29/13 WebEx Discussion: Jim Galvin - this leads in to something to consider regarding availability of data/extracts to guage accuracy. Let's not close this issue as the ability to have access to the data to make an assessment of accuracy is an important aspect of this effort
3 | Tenaska Eli Worley | Retail Extracts timeline | Why is it a 3-day lookback window for the retail extracts, rather than 1 day? |  | J. Mikus | new | The extract was built on providing data that was sysdate-3 through sysdate -2 due to the complexity of the extract and the SLA data stability for the archiving system. If the market is looking for us to change the range, we will need to do some analysis to determine impacts. ACTION: As posting data agg deadline changes ERCOT will look at other possible solutions for the outputs from Data Ag in the retail extracts. 5/13 no update
4 | Lin GDF Suez Thompson PCI | Late posting Settlement extract | ERCOT settlement statement posted Friday May 3rd but no corresponding extract |  |  | closed | Related to May 3rd Outage:Dispute deadline extended but not payment deadline. Will dispute calendar be updated? No will send out manual notice (Art Dellar)
5 | Lin GDF Suez Thompson PCI | Settlement extract 48-hour posting deadline | Does 48 hour deadline mean business hours or all hours? |  |  | closed | 48 hours is tied to regular hours not business hours.
6 | Jim Galvin Michelle | Roll up available TDSP ESIID count availability | Show ERCOT wide meter type availability for IDR, AMS, and Non-IDR data by 1, 2, and 3 day look back |  | D. Tucker | new | update 5/13: ERCOT will bring sample to the Monday May 20th call. Provide ESI ID counts by meter type, by operating day of initial, 3 days to shorter timeline.
7 | ERCOT | CARD and Balancing Account payout | Due to moving the RTM Initial up one day, the CARD and Balancing Account payouts occur one day earlier than before. |  | M. Tozer | closed | Benefit to the market to receive funds from the CARD and Balancing Account allocations sooner.
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61 | [8 empty] | 62
62 | [8 empty] | 66
63 | [8 empty] | 67
64 | [8 empty] | 68
65 | [8 empty] | 69
66 | [8 empty] | 74
67 | [8 empty] | 75
68 | [8 empty] | 76
69 | [8 empty] | 78
70 | [8 empty] | 79
71 | [8 empty] | 80
72 | [8 empty] | 85
73 | [8 empty] | 91
74 | [8 empty] | 98
75 | [8 empty] | 100
76