## Sheet1
TX SET Meeting Notes / Action Items
9/11/2013 ( 2 day meeting)
Agenda Item: | Decision / Resolution | Action Items :
August 2013 Meeting Notes | Reviewed and adjusted meeting notes as needed
AMS OPT OUT | Discuss changes needed to accommodate the AMS OPT OUT rule in the market | Analysis of the rule and updated matrix with action items. The 3 Day Notice--Via MarkeTrak D2D "MARKET RULE" subtype will be populated with "AMSOPTOUT" in the MARKET RULE field.
TX SET Procedures | Discuss reline changes sent to the TXSET listserv for review | Leave current issue process in tact and continue to review document to identify where additional process improvements can be made--On Hold to be discussed at later date
Market Test Update | Flight 1013 Summary-7 New CRs (includes 2 Additional DUNS) are testing Existing CRs: 23 CRs are testing with Sharyland, 6 CRs are testing for a service provider change, and 1 CRs is testing for an additional TDSP territory 4430 tasks are scheduled Schedule Flight signup began 09/04/13 Flight deadline was 09/11/13 Connectivity kick-off conference call was 09/17/13 Flight kick-off conference call is 10/04/13 Day 1 transactions begin 10/07/13 Flight scheduled to conclude 11/19/13 (contingency period until 12/10/13)
Change Control Call | 2013-800(Tabled-no rep from Nueces Energy present ), 2013-801, 2013-802 Recommended to be sent to RMS for approval as an emergency
Acquisition Transfer | RMGRR116 Tabled at RMS-request to add stronger language for pre-event requirements. TAC requested to lower the number of days to process transactions
Issues
134-Non-CSA CR sends a MVO with the indicator for bypass CSA at ERCOT. Non-CSA CR is not always the owner of the CSA, causing the ESI ID to become de-energized without CSA CRs knowledge | Issue closed. TX SET to submit a protocol change request and draft NPRR for approval | Sandra to draft the NPRR and submit for October RMS meeting for endorsement
Other Business | 814-03 N1*8R and PER*IC segments What was the history around making these 2 mandatory | Determined No Action Needed- Closed
Next Meeting |  | October 9&10--Room 168 ERCOT MET Center
Attendees
Kathryn Thurman (ERCOT) Gene Cervenka (ERCOT - WebEx) Becky Taylor (CNP) Jim Lee (Direct Energy) Diana Rehfeldt (TNMP) Ed Echols (Oncor ) Kathy Scott (CNP) John Schatz (TXUE) Monica Jones (Reliant) Teresa Rodriguez (Stream - WebEx) Gricelda Calzada(AEP) | Bryan Kelly( PUCT- webex) Barbara Goubeaud(EC Info Systems) Suzanne Clark (liberty power WebEx) Sandra Tindall(ERCOT- webex) Joe Lindsey (Sys-trends WebEx) Amy Rafferty (WebEx) Carolyn Reed (CNP) Kyle Patrick (Reliant) Cliff Crouch (PUCT-webex) | Kaci Jacobs Paul Yockey(ERCOT-WebEx) Suzy Clifton (ERCOT-WebEx) Roger Tenenbown (ISTA NA-webex)