## Slide 1: NPRR568 – Real-Time Reserve Price Adder Based on Operating Reserve Demand Curve Impact Analysis Summary for TAC November 2013 Troy Anderson

## Slide 2: Agenda
Preliminary Impact Analysis
Four Components of Revised Impact Analysis
Cost and Schedule Impact per IA Component
ERCOT Recommendation
Revised Impact Analysis

## Slide 3: Preliminary Impact Analysis (IA)
Preliminary IA filed with Public Utility Commission in Docket No. 40000 on 5/17/2013
Cost Estimate = $100k – $200k
Duration Estimate = 6 – 8 months
Scope
  Implement an Operating Reserve Demand Curve (ORDC) in the Real-Time Market to determine the Real-Time price adder for Real Time Settlement Point Prices
  Implement an Ancillary Service imbalance settlement to ensure that resources are indifferent between providing energy and reserves in Real-Time

## Slide 4: Four Components of Revised Impact Analysis
Revised IA Baseline
  Preliminary IA scope plus:
    Posting of system-level data used to calculate reserve level
    Wind Generation Resources (WGR) in reserves
    Reliability Unit Commitment (RUC) floor logic
    Load allocation
    Settlements calculation discount factor
OFF10/OFF30 Telemetry to Show Extra Offline Capacity Available in 10/30 Minutes
    Add 4 new telemetry points and integrate with MMS and S&B
Resource Asset Registration (RARF) Validation and Testing
    Validate telemetry with RARF data
    Combined Cycle transition time from Common Info. Model (CIM)
    Warmth state from EMS
Addition of Current Operating Plan (COP) Data Points
    See ERCOT comments filed on 11/5/2013

## Slide 5: Impacts per Component
Revised IA Baseline
  Cost = $400k – $500k
  Project Duration = 7 – 9 months
OFF10/OFF30 Telemetry to Show Extra Offline Capacity Available in 10/30 Minutes
  Incremental Cost = $50k – $100k
  Incremental Duration = 1 – 3 months
Resource Asset Registration (RARF) Validation and Testing
  Incremental Cost = $100k – $250k
  Incremental Duration = 3 – 6 months
  Dependencies with MMS Tech Refresh
Addition of Current Operating Plan (COP) Data Points
  Incremental Cost = $10k – $20k
  Incremental Duration = 1 – 2 months

## Slide 6: ERCOT Recommendation
ERCOT recommends a phased approach to NPRR568
  Include scope of Revised Baseline in Phase 1
  Deliver remaining components in Phase 2
Phase 1 – Revised NPRR568 Baseline
  Include in “2014 Market System Enhancements” project
    Project was recently initiated
    Includes: NPRR555, NPRR532, NPRR495, NPRR240, and Shadow Price Cap Methodology OBD
  Targeted for go-live the week of 6/1/2014
  Scope and schedule to be finalized when Planning phase completes
    Monthly communication at TAC meetings
Phase 2 – Remaining NPRR568 Components
  ERCOT recommends that these items be bundled together
  Dependencies with MMS Tech Refresh project will determine timeline

## Slide 7: Revised Impact Analysis
Total Cost Estimate = $600k – $850k
  Phase 1 = $400k – $500k
  Phase 2 = $200k – $350k
Duration Estimate = 9 – 12 months (as a single phase project)
  Phase 1 = 7 – 9 months
    Target go-live remains the week of 6/1/2014
    Project bundle contents may be adjusted to meet target date
  Phase 2 = 4 – 6 months
    Target go-live TBD
ERCOT Staffing Impacts = +1 FTE
  Operations Analysis – 1 FTE for testing and qualification
  Other departments with minor impacts that can be absorbed
Impacts to Other In-Flight Projects
  ERCOT will manage project activity based on overall prioritization

## Slide 8: Questions
?