## Sheet1
TX SET Meeting Notes / Action Items
10/09/2013and 10/10/2013 ( 2 day meeting)
Agenda Item: | Decision / Resolution | Action Items :
October 2013 Meeting Notes | Reviewed and adjusted meeting notes as needed
Mass Transition/Default-POLR Rule | Mass TransitionRMS assignment Possible POLR Rule change from two days out to one day out. Drafted document with impacts associated with shortening the timeline for discussion at Subteam meeting scheduled 10/28/2013 | TDSP- look at largest REP and determine if they can receive transactions and complete the process according to the timeline in the Retail Market Guide( appendix F2). ERCOT-What is the largest number of ESIDS ERCOT can send 814_03s for on Day 0? What are the implications of all associated transactions on ERCOT meeting the timeline in the Retail Market Guide?
Non Standard Metering | Reviewed the Draft RMGRR and made changes to the language where needed. Group agreed that the same MarkeTrak Issue that will be used for the 3 day notice can also be used for the 30 day notice where a non-standard meter already exists. | Send Draft RMGRR to ERCOT Rules for review and submission for a number.
TX SET Procedures | On Hold-Discuss reline changes sent to the TXSET listserv for review | Leave current issue process in tact and continue to review document to identify where additional process improvements can be made
Market Test Update | Flight 1013 Summary-7 New CRs (includes 2 Additional DUNS) are testing Existing CRs: 23 CRs are testing with Sharyland, 6 CRs are testing for a service provider change, and 1 CRs is testing for an additional TDSP territory 4430 tasks are scheduled Schedule Flight signup began 09/04/13 Flight deadline was 09/11/13 Connectivity kick-off conference call was 09/17/13 Flight kick-off conference call is 10/04/13 Day 1 transactions begin 10/07/13 Flight scheduled to conclude 11/19/13 (contingency period until 12/10/13)
Mass Acquisition | RMGRR116 Tabled at RMS-request to add stronger language for pre-event requirements. TAC requested to lower the number of days to process transactions | Additional language added noting TDSP’s agreement to remove Switch Holds in the event the Losing CR fails to remove their Switch Holds from all ESI ID’s that are associated to the Acquisition Transfer. Additional language added to include new timelines that allows TDSP(s) an opportunity to remove Switch Holds(s) when needed prior to ERCOT triggering the Acquisition Transfer 814_03 transactions. Added language to give ERCOT more flexibility in the timelines identified throughout this RMGRR in case there is a decision made by ERCOT Legal to expedite the transfer of ESI IDs from Losing REP.
Issues
134-Non-CSA CR sends a MVO with the indicator for bypass CSA at ERCOT. Non-CSA CR is not always the owner of the CSA, causing the ESI ID to become de-energized without CSA CRs knowledge | Submit a protocol change request and draft NPRR for approval | On hold until Nov meeting. NPRR Draft discussion on hold
Other Business |  | No other business discussed
Next Meeting |  | Nov 13&14--Room 168 ERCOT MET Center
Attendees
Kathryn Thurman (ERCOT) Gene Cervenka (ERCOT - WebEx) Becky Taylor (CNP) Jim Lee (Direct Energy) Diana Rehfeldt (TNMP) Ed Echols (Oncor ) Kathy Scott (CNP) John Schatz (TXUE) Monica Jones (Reliant) Teresa Rodriguez (Stream - WebEx) Gricelda Calzada(AEP) Kim Wall(PPL Solutions) Rob Bevels(Green Mountain) | Bryan Kelly( PUCT- webex) Barbara Goubeaud(EC Info Systems) Suzanne Clark (liberty power WebEx) Sandra Tindall(ERCOT- webex) Joe Lindsey (Sys-trends WebEx) Amy Rafferty (ESG-WebEx) Carolyn Reed (CNP) Kyle Patrick (Reliant) Cliff Crouch (PUCT-webex) | Kaci Jacobs(TXU) Mandy Bald ERCOT Paul Yockey(ERCOT-WebEx) Suzy Clifton (ERCOT-WebEx) Roger Tenenbown (ISTA NA-webex) Pam Shaw(SU) Mary Sithihao(Stream Energy-WebEx) Dave Michelsen(ERCOT-WebEx) Mark Ruane(ERCOT) Juliann Morehead(ERCOT) Cliff Couch(PUCT)