|  |  | System Planning |
| --- | --- | --- |
|  |  | Monthly Status Report October 2013 |
|  | Report Highlights |  |
|  | ERCOT is currently tracking 182 active generation interconnection requests totaling over 47,100 MW. This includes over 22,800 MW of wind generation. |  |
|  | ERCOT is currently reviewing proposed transmission improvements with a total cost of $675 Million Transmission Projects endorsed in 2013 total $349.8 Million All projects (in engineering, routing, licensing and construction) total approximately $6.23 Billion. Transmission Projects energized in 2013 total about $3.17 Billion. |  |

Table of Contents

1.	Generation Interconnection	1

1.1	Signed Generation Interconnection Agreements	1

1.2	New Generation Approved for Commercial Operations	1

1.3	Summary of Generation Interconnection Requests	1

1.4	Projects with Interconnection Agreements	5

1.5	Projects Undergoing Full Interconnection Studies with Confidentiality Waived	6

1.6	Generation Projects Undergoing Full Interconnection Studies	6

1.7	Wind Generation Capacity Installed by Year	9

2.	Regional Planning Group Project Reviews	11

3.	Asynchronous Tie Interconnection	11

4.	Planning Model Activities	12

5.	Other Notable Activities	12

# 1.	Generation Interconnection

Additional information regarding detailed generation interconnection and impact studies is contained in the “Generation Project Interconnection Information” folder in the “Operations and System Planning” area on the ERCOT website:  http://planning.ercot.com/login/login.

## Signed Generation Interconnection Agreements

## New Generation Approved for Commercial Operations

The total installed wind capacity is now reported as 10,970 MW by the resource owners through the registration process. Capacity by North, South and West is 832 MW, 2,775 MW, and 7,363 MW respectively.  Eight-hundred fifty MW is able to switch between the West and South zones and is currently shown in the South zone.

## Summary of Generation Interconnection Requests

| GENERATION INTERCONNECTION REQUESTS CURRENTLY UNDER REVIEW |
| --- |
| Currently tracking 182 generation interconnection or change requests |
| As of October 31, 2013 | Total |
| Security Screening Study | 17 |
| SSS Completed | 13 |
| Full Interconnect Study | 105 |
| FIS Completed | 8 |
| Suspended Studies | 0 |
| Capacity of Suspended Study Projects | 0 |
| Interconnect Agreement Completed | 39 |
| Capacity under Interconnection Agreements | 12,900 |
| Capacity for Grid, MW | 47,104 |
| Wind Capacity, MW | 22,881 |
| Cancelled Projects | 2 |

| Fuel Type | Confidential Projects (MW) | Projects Under Full Study (MW) | Public Projects (MW) | Suspended Studies (MW) | Grand Total (MW) |
| --- | --- | --- | --- | --- | --- |
| Gas-AllOther |  |  | 374 | - | 4,857 |
| Gas-CombinedCycle |  |  | 6,515 | - | 16,462 |
| Total Gas | 1,670 | 12,760 | 6,889 | - | 21,319 |
| Nuclear | - | - | - | - | - |
| Coal | - | 30 | 240 | - | 270 |
| Wind | 3,943 | 13,317 | 5,621 | - | 22,881 |
| Solar | 458 | 1,151 | 150 | - | 1,759 |
| Biomass | - | - | - | - | - |
| Storage | - | 874 | - | - | 874 |
| Petroleum Coke | - | - | - | - | - |
| Grand Total | 6,071 | 28,132 | 12,900 | - | 47,103 |

County Location of Installed Generation and Interconnection Requests (all fuels)

## Projects with Interconnection Agreements

| Generation Interconnection Agreements as of October 31, 2013 |
| --- |
| INR | Site Name | County | COD | Fuel | MW For Grid | Change from Last Report |
| 12INR0075 | Blue Summit Windfarm | Wilbarger | Oct-13 | Wind | 135 |  |
| 13INR0058 | OCI Alamo 1 | Bexar | Oct-13 | Solar | 50 |  |
| 11INR0094 | White Camp Solar | Kent | Nov-13 | Solar | 100 |  |
| 11INR0013 | Goldthwaite Wind Energy | Mills | Dec-13 | Wind | 150 |  |
| 12INR0068 | Sendero Wind Energy Project | Jim Hogg | Feb-14 | Wind | 78 |  |
| 12INR0034 | Stephens Ranch Wind Energy | Borden | Apr-14 | Wind | 378 |  |
| 13INR0059a | Hereford Wind | Castro | Apr-14 | Wind | 200 |  |
| 13INR0057 | Windthorst 2 | Archer | Jun-14 | Wind | 65 |  |
| 14INR0015 | Deer Park Energy Center | Harris | Jun-14 | Gas | 192 |  |
| 14INR0016 | Channel Energy Center 138/345kV CT | Harris | Jun-14 | Gas | 190 |  |
| 13INR0048 | Spinning Spur Wind Two | Oldham | Jun-14 | Wind | 161 |  |
| 11INR0062 | Patriot (Petronilla) Wind | Nueces | Jun-14 | Wind | 178 |  |
| 14INR0012a | Miami Wind 1 Project | Gray | Jul-14 | Wind | 231 |  |
| 13INR0021 | Ferguson Replacement Project | Llano | Jul-14 | Gas | 570 |  |
| 14INR0030a_2 | Panhandle Wind | Carson | Aug-14 | Wind | 218 |  |
| 10INR0021 | Panda Sherman Power | Grayson | Aug-14 | Gas | 720 |  |
| 13INR0040 | Rentech Project | Harris | Aug-14 | Gas | 15 |  |
| 10INR0020a | Panda Temple Power | Bell | Aug-14 | Gas | 717 |  |
| 11INR0050 | Moore Wind 1 | Crosby | Aug-14 | Wind | 149 |  |
| 13INR0010a | Mariah Wind | Parmer | Oct-14 | Wind | 200 |  |
| 13INR0020a | CPV Rattlesnake Den Ph 1 | Glasscock | Oct-14 | Wind | 200 |  |
| 13INR0020b | CPV Rattlesnake Den Ph 2 | Glasscock | Oct-14 | Wind | 150 |  |
| 11INR0054 | Midway Farms Wind | San Patricio | Oct-14 | Wind | 161 |  |
| 14INR0023 | Longhorn Energy Center | Briscoe | Dec-14 | Wind | 361 |  |
| 13INR0005 | Conway Windfarm | Carson | Dec-14 | Wind | 600 |  |
| 11INR0057 | Cameron County Wind | Cameron | Dec-14 | Wind | 165 |  |
| 11INR0079a | South Clay Windfarm | Clay | Dec-14 | Wind | 200 |  |
| 06INR0022c | Penascal Wind Farm 3 | Kenedy | Dec-14 | Wind | 202 |  |
| 09INR0051 | Mesquite Creek | Borden | Jan-15 | Wind | 249 |  |
| 08INR0018 | Gunsight Mountain | Howard | Aug-15 | Wind | 120 |  |
| 14INR0012b | Miami Wind 1 Project | Gray | Aug-15 | Wind | 170 |  |
| 10INR0020b | Panda Temple Power | Bell | Aug-15 | Gas | 791 |  |
| 13INR0010b | Mariah Wind | Parmer | Dec-15 | Wind | 200 |  |
| 12INR0029 | Comanche Run Wind | Swisher | Dec-15 | Wind | 500 |  |
| 13INR0023 | Texas Clean Energy Project | Ector | Jan-16 | Coal | 240 |  |
| 13INR0028 | Antelope Station | Hale | Jun-16 | Gas | 359 |  |
| 13INR0023 | Texas Clean Energy Project | Ector | Jan-16 | Coal | 240 |  |
| 06INR0006 | Cobisa-Greenville | Hunt | Dec-16 | Gas | 1,792 |  |
| 10INR0022 | Pondera King Power Project | Harris | Jun-16 | Gas | 1,380 |  |

## Projects Undergoing Full Interconnection Studies with Confidentiality Waived

| INR | Site Name | County | COD | Fuel | MW for Grid | Change from Last Report |
| --- | --- | --- | --- | --- | --- | --- |

## Generation Projects Undergoing Full Interconnection Studies

| Interconnection Database Reference Number | County | Fuel | Capacity to Grid (MW) | Commercial Operation Data (as specified by the resource developer) |
| --- | --- | --- | --- | --- |
| 14INR0039 | Ector | Gas | 450 | 3/1/2014 |
| 14INR0069 | Milam | Coal | 30 | 3/31/2014 |
| 14INR0024 | Kinney | Solar | 42 | 4/1/2014 |
| 14INR0013 | Cameron | Wind | 103 | 4/1/2014 |
| 14INR0048_1 | Wilbarger | Wind | 114 | 6/1/2014 |
| 14INR0038 | Galveston | Gas | 390 | 6/1/2014 |
| 14INR0048_2 | Wilbarger | Wind | 250 | 6/1/2014 |
| 13INR0026 | Oldham | Wind | 201 | 6/1/2014 |
| 14INR0040 | Hidalgo | Gas | 225 | 6/7/2014 |
| 12INR0059 | Pecos | Solar | 50 | 6/30/2014 |
| 11INR0093 | San Patricio | Wind | 41 | 7/1/2014 |
| 14INR0029 | Uvalde | Solar | 42 | 7/1/2014 |
| 14INR0014 | Val Verde | Solar | 100 | 7/1/2014 |
| 14INR0059 | Kaufman | Gas | 52 | 8/1/2014 |
| 13INR0055 | Zapata | Wind | 250 | 9/1/2014 |
| 14INR0030b | Carson | Wind | 198 | 9/1/2014 |
| 13INR0038 | Swisher | Wind | 300 | 9/15/2014 |
| 14INR0062 | Hall/Motley | Wind | 200 | 9/30/2014 |
| 14INR0042 | Deaf Smith | Solar | 80 | 9/30/2014 |
| 14INR0047 | Floyd and Crosby | Wind | 301 | 10/1/2014 |
| 13INR0036 | Hidalgo | Wind | 200 | 10/31/2014 |
| 11INR0065 | Nueces | Wind | 350 | 10/31/2014 |
| 12INR0045 | Kleberg | Wind | 135 | 10/31/2014 |
| 14INR0060 | Haskell | Wind | 400 | 11/1/2014 |
| 13INR0025 | Randall | Wind | 150 | 11/1/2014 |
| 13INR0056 | Scurry | Wind | 366 | 11/21/2014 |
| 14INR0066 | Lamar | Gas | 130 | 11/30/2014 |
| 14INR0044 | Reeves | Solar | 100 | 12/1/2014 |
| 10INR0085 | Ector | Solar | 57 | 12/1/2014 |
| 14INR0041 | Willacy | Wind | 114 | 12/1/2014 |
| 13INR0050 | Comanche | Wind | 200 | 12/1/2014 |
| 14INR0043 | Sterling | Solar | 40 | 12/1/2014 |
| 14INR0028 | Live Oak | Wind | 300 | 12/1/2014 |

| Interconnection Database Reference Number | County | Fuel | Capacity to Grid (MW) | Commercial Operation Data (as specified by the resource developer) |
| --- | --- | --- | --- | --- |
| 14INR0033 | Armstrong | Wind | 500 | 12/1/2014 |
| 13INR0054 | Bee | Gas | 25 | 12/1/2014 |
| 14INR0025a | Floyd | Wind | 200 | 12/1/2014 |
| 14INR0032a | Randall | Wind | 200 | 12/1/2014 |
| 14INR0009 | Kent | Wind | 248 | 12/1/2014 |
| 11INR0082b | Val Verde | Wind | 150 | 12/1/2014 |
| 11INR0082a | Val Verde | Wind | 50 | 12/1/2014 |
| 11INR0081 | Live Oak | Wind | 72 | 12/1/2014 |
| 14INR0058 | Brewster | Solar | 100 | 12/1/2014 |
| 13INR0045 | Castro | Wind | 288 | 12/30/2014 |
| 14INR0057a | Erath | Wind | 48 | 12/31/2014 |
| 13INR0010d | Parmer | Wind | 200 | 12/31/2014 |
| 13INR0052 | Starr | Wind | 200 | 12/31/2014 |
| 14INR0045a | Webb | Wind | 502 | 12/31/2014 |
| 14INR0049_1 | Jack | Wind | 102 | 12/31/2014 |
| 14INR0056 | Mills | Wind | 101 | 12/31/2014 |
| 14INR0049_2 | Jack | Wind | 102 | 12/31/2014 |
| 12INR0055 | Baylor | Wind | 40 | 12/31/2014 |
| 14INR0057b | Erath | Wind | 48 | 12/31/2014 |
| 14INR0053 | Oldham | Wind | 161 | 12/31/2014 |
| 12INR0070 | Knox | Wind | 300 | 1/1/2015 |
| 14INR0020 | Floyd & Motley | Wind | 150 | 3/1/2015 |
| 15INR0036 | Uvalde | Solar | 105 | 3/1/2015 |
| 10INR0009 | Castro | Wind | 300 | 3/31/2015 |
| 15INR0055 | AUSTIN | Gas | 142 | 5/1/2015 |
| 15INR0053 | WINKLER | Gas | 142 | 5/1/2015 |
| 15INR0054 | REEVES | Gas | 142 | 5/1/2015 |
| 15INR0021 | Starr | Wind | 200 | 5/15/2015 |
| 14INR0027 | Guadalupe | Gas | 471 | 6/1/2015 |
| 15INR0022 | Presidio | Solar | 75 | 6/1/2015 |
| 15INR0042 | Hood | Gas | 460 | 6/1/2015 |
| 14INR0031 | Harris | Gas | 270 | 6/1/2015 |
| 15INR0027 | Hidalgo | Gas | 79 | 6/1/2015 |
| 15INR0028 | Freestone | Gas | 160 | 6/1/2015 |
| 15INR0023 | Wharton | Gas | 700 | 6/15/2015 |
| 13INR0049 | Harris | Gas | 352 | 7/15/2015 |
| 14INR0026 | Presidio | Solar | 30 | 9/1/2015 |
| 15INR0041 | Pecos | Solar | 51 | 9/1/2015 |
| 15INR0014 | Matagorda | Storage | 280 | 10/9/2015 |

| Interconnection Database Reference Number | County | Fuel | Capacity to Grid (MW) | Commercial Operation Data (as specified by the resource developer) |
| --- | --- | --- | --- | --- |
| 15INR0013 | Anderson | Storage | 324.00 | 10/9/2015 |
| 14INR0030a_1 | Carson | Wind | 322.00 | 11/1/2015 |
| 15INR0035 | Kenedy | Wind | 200.00 | 12/1/2015 |
| 12INR0060 | Schleicher | Wind | 58.00 | 12/1/2015 |
| 14INR0025b | Floyd | Wind | 300.00 | 12/1/2015 |
| 15INR0034 | San Patricio | Wind | 201.00 | 12/1/2015 |
| 08INR0019a | Gray | Wind | 250.00 | 12/1/2015 |
| 15INR0037 | Starr | Wind | 200.00 | 12/31/2015 |
| 13INR0031 | Travis | Solar | 30.00 | 12/31/2015 |
| 13INR0032 | Andrews | Solar | 30.00 | 12/31/2015 |
| 14INR0045b | Webb | Wind | 251.00 | 12/31/2015 |
| 14INR0018 | Nolan | Solar | 20.00 | 12/31/2015 |
| 12INR0002a | Briscoe | Wind | 200.00 | 12/31/2015 |
| 15INR0044 | Webb and Duval | Solar | 200.00 | 12/31/2015 |
| 13INR0010e | Parmer | Wind | 200.00 | 12/31/2015 |
| 15INR0049 | Zapata / Webb | Wind | 250.00 | 12/31/2015 |
| 16INR0010 | Mitchell | Gas | 799.00 | 2/1/2016 |
| 16INR0005 | Cameron | Gas | 871.00 | 4/1/2016 |
| 16INR0009 | Calhoun | Gas | 510.00 | 4/14/2016 |
| 15INR0033 | Hale | Gas | 197.00 | 5/1/2016 |
| 15INR0032 | Hale | Gas | 197.00 | 5/1/2016 |
| 16INR0008 | Grimes | Gas | 687.00 | 5/1/2016 |
| 17INR0004 | Hale | Gas | 202.00 | 6/1/2016 |
| 16INR0004 | Cameron | Gas | 730.00 | 6/1/2016 |
| 16INR0007 | Hidalgo | Gas | 95.00 | 6/1/2016 |
| 16INR0003 | Brazoria | Gas | 11.00 | 6/1/2016 |
| 16INR0006 | Angelina | Gas | 785.00 | 6/1/2016 |
| 14INR0011 | Swisher | Storage | 270.00 | 7/1/2016 |
| 08INR0019b | Gray | Wind | 250.00 | 7/1/2016 |
| 16INR0013 | Nacogdoches | Gas | 215.00 | 7/1/2016 |
| 13INR0006 | Gray | Wind | 750.00 | 12/1/2016 |
| 08INR0019c | Gray | Wind | 250.00 | 12/1/2016 |
| 12INR0079 | Kenedy | Wind | 200.00 | 12/15/2016 |
| 12INR0002b | Briscoe | Wind | 200.00 | 12/31/2016 |
| 13INR0010f | Parmer | Wind | 200.00 | 12/31/2016 |
| 12INR0018 | Gray | Wind | 500.00 | 3/31/2017 |
| 17INR0002 | Henderson | Gas | 489.00 | 6/1/2017 |
| 17INR0003 | Jackson | Gas | 965.00 | 6/1/2017 |
| 17INR0005 | Starr | Wind | 200.00 | 6/30/2017 |
| 17INR0007 | Wharton | Gas | 1177.00 | 7/31/2017 |
| 11INR0040 | Freestone | Gas | 640.00 | 3/1/2018 |

## Wind Generation Capacity Installed by Year

# Regional Planning Group Project Reviews

- CenterPoint Energy submitted the Houston Region Import Capacity project. This is a Tier 1 project that is estimated to cost between $297 to $532 million. This project is currently under ERCOT independent review.

- Garland Power & Light (GP&L) and Cross Texas Transmission (CTT) have jointly submitted the Houston Import project. This is a Tier 1 project that is estimated to cost between $195 to $317 million. This project has received several RPG comments and it is under study mode.

- Denton Municipal Electric submitted the Spencer-Pockrus 138 kV project. The project is estimated to cost approximately $5.5 million. This project was initially classified as a Tier 3 and and the project has statisfied all the RPG comments.  In accordance with Protocol Section 3.11.4.5, the Spencer-Pockrus 138 kV project has been reclassified as a “Tier 4 Neutral Project.”

- Lone Star Transmission has submitted the Houston Import project. This is a Tier 1 project that is estimated to cost between $417 to $675 million. This project has received several RPG comments and it is under study mode.

# Asynchronous Tie Interconnection

| Project | Notification to ERCOT | Reliability Study | RPG Review | Interconnection Agreement | In-service Year |
| --- | --- | --- | --- | --- | --- |
| Railroad DC tie expansion (150 MW - CFE) |  |  |  |  | 2014 |
| Southern Cross HVDC (3000 MW - SERC) |  |  |  |  |  |
| Tres Amigas (1500 MW - SPP) |  |  |  |  |  |

Color Legend

|  | In progress |
| --- | --- |
|  | Complete |

# Planning Model Activities

- The short term calendar of major planning model events follows:

  - Oct 15, 2013	SSWG Data Set B posted on POI, MIS

  - Nov 4, 2013	TPIT spreadsheet posted on POI

  - Nov 4, 2013	Contingency files posted on POI

  - Nov 15, 2013	Post 2014 DSB HWLL case to POI

# Other Notable Activities

- The project to complete the missing and questionable data for the remaining Resource Asset Registration Forms (RARF) that are still incomplete is underway.  ERCOT and Siemens created a list of 3387 individual data items that are missing or suspect.   Most of the estimates of missing data have been completed and the estimates are being sent to RE’s as completed.  RE’s must return completed RARF’s to ERCOT by December 1, 2013 via the normal RARF submission process using the estmates provided by ERCOT or actual or test data if available.

- ERCOT is working on the 2013 Regional Transmission Plan (RTP). The N-1 secure cases including the N-1 reliability projects was posted at the ERCOT POI on Oct. 25, 2013. ERCOT is currently working on G-1+N-1 reliability analysis and economic analysis.

- ERCOT has posted the draft report on the results of the Long-term study and the improvements to the long-term study process as a result of the grant received from the Department of Energy.

- ERCOT has issued a Request For Proposal (RFP) in order to hire a consultant to perform a small signal stability study.