## Sheet2
LRIS v2 Development Timeline
| Analysis | Development | Drafting | Editing | Committee
2013-01-01 | Collect necessary information, provide new analysis for potential impacts of achieving LRISv2 Goals, including alternate paths | Refining pros & cons, identifying outstanding issues, alternative paths
Drafting NPRR
2013-02-01
Sub-group editing
2013-03-01
Bring draft to DSWG for discussion
2013-04-01
Bring to DSWG for discussion and final revisions
2013-05-01 |  |  |  |  | Update WMS on Progress
DSWG for review of final version
2013-06-01 |  |  |  |  | Bring to WMS for Review
2013-07-01 |  |  |  |  | WMS vote