|  |  |  |  | System Planning |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Monthly Status Report November 2013 |  |  |
|  |  | Report Highlights |  |  |  |  |  |  |
|  | - ERCOT is currently tracking 194 active generation interconnection requests totaling over 50,000 MW. This includes over 22,600 MW of wind generation. |  |  |  |  |  |  |  |
|  | - ERCOT is currently reviewing proposed transmission improvements with a total cost of $720 Million - Transmission Projects endorsed in 2013 total $349.8 Million - All projects (in engineering, routing, licensing and construction) total approximately $6.23 Billion. - Transmission Projects energized in 2013 total about $3.17 Billion. |  |  |  |  |  |  |  |

Table of Contents

1.	Generation Interconnection	1

1.1	Signed Generation Interconnection Agreements	1

1.2	New Generation Approved for Commercial Operations	1

1.3	Summary of Generation Interconnection Requests	1

1.4	Projects with Interconnection Agreements	5

1.5	Projects Undergoing Full Interconnection Studies with Confidentiality Waived	6

1.6	Generation Projects Undergoing Full Interconnection Studies	6

1.7	Wind Generation Capacity Installed by Year	9

2.	Regional Planning Group Project Reviews	10

3.	Asynchronous Tie Interconnection	10

4.	Planning Model Activities	11

5.	Other Notable Activities	11

# 1.	Generation Interconnection

Additional information regarding detailed generation interconnection and impact studies is contained in the “Generation Project Interconnection Information” folder in the “Operations and System Planning” area on the ERCOT website:  http://planning.ercot.com/login/login.

## Signed Generation Interconnection Agreements

13INR0052 – Los Vientos III – 200 MW in Starr County

13INR0059b – Hereford Wind – 300 MW located in Castro County

13INR0049 – Friendswood Energy Ctr. – 316 MW located in Harris County

14INR0032a – Route66 Wind – 150 MW located in Randall County

13INR0031 – Mustang Solar – 30 MW located in Travis County

14INR0030b – Panhandle Wind 2 – 198 MW located in Carson County

14INR0049 – Keechi Wind – 102 MW located in Jack County

12INR0018 – Pampa Wind – 500 MW located in Gray County

## New Generation Approved for Commercial Operations

The total installed wind capacity is now reported as 10,970 MW by the resource owners through the registration process. Capacity by North, South and West is 832 MW, 2,775 MW, and 7,363 MW respectively.  Eight-hundred fifty MW is able to switch between the West and South zones and is currently shown in the South zone.

## Summary of Generation Interconnection Requests

| GENERATION INTERCONNECTION REQUESTS CURRENTLY UNDER REVIEW |  |
| --- | --- |
| Currently tracking 194 generation interconnection or change requests |  |
| As of November 30, 2013 | Total |
| Security Screening Study | 17 |
| SSS Completed | 18 |
| Full Interconnect Study | 103 |
| FIS Completed | 9 |
| Suspended Studies | 0 |
| Capacity of Suspended Study Projects | 0 |
| Interconnect Agreement Completed | 47 |
| Capacity under Interconnection Agreements | 14,696 |
| Capacity for Grid, MW | 50,015 |
| Wind Capacity, MW | 22,693 |
| Cancelled Projects | 0 |

| Fuel Type | Confidential Projects (MW) | Projects Under Full Study (MW) | Public Projects (MW) | Suspended Studies (MW) | Grand Total (MW) |
| --- | --- | --- | --- | --- | --- |
| Gas-AllOther |  |  | 690 | - | 7,480 |
| Gas-CombinedCycle |  |  | 6,515 | - | 16,208 |
| Total Gas | 4,075 | 12,408 | 7,205 | - | 23,688 |
| Nuclear | - | - | - | - | - |
| Coal | - | 30 | 240 | - | 270 |
| Wind | 3,127 | 12,495 | 7,071 | - | 22,693 |
| Solar | 951 | 1,359 | 180 | - | 1,759 |
| Biomass | - | - | - | - | - |
| Storage | - | 874 | - | - | 874 |
| Petroleum Coke | - | - | - | - | - |
| Grand Total | 8,153 | 27,166 | 14,696 | - | 50,015 |

Cumulative Installed MW Capacity of Interconnection Requests by Zone

## Projects with Interconnection Agreements

| Generation Interconnection Agreements as of November 30, 2013 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| INR | Site Name | County | COD | Fuel | MW For Grid | Change from Last Report |
| 12INR0075 | Blue Summit Windfarm | Wilbarger | Oct-13 | Wind | 135 |  |
| 13INR0058 | OCI Alamo 1 | Bexar | Oct-13 | Solar | 50 |  |
| 11INR0013 | Goldthwaite Wind Energy | Mills | Dec-13 | Wind | 150 |  |
| 12INR0068 | Sendero Wind Energy Project | Jim Hogg | Feb-14 | Wind | 78 |  |
| 12INR0034 | Stephens Ranch Wind Energy | Borden | Apr-14 | Wind | 378 |  |
| 13INR0059b | Hereford Wind | Castro | Apr-14 | Wind | 300 | New |
| 13INR0059a | Hereford Wind | Castro | Apr-14 | Wind | 200 |  |
| 13INR0057 | Windthorst 2 | Archer | Jun-14 | Wind | 65 |  |
| 14INR0012a | Miami Wind 1 Project | Gray | Jun-14 | Wind | 231 |  |
| 14INR0015 | Deer Park Energy Center | Harris | Jun-14 | Gas | 192 |  |
| 14INR0016 | Channel Energy Center 138/345kV CT | Harris | Jun-14 | Gas | 190 |  |
| 13INR0048 | Spinning Spur Wind Two | Oldham | Jun-14 | Wind | 161 |  |
| 13INR0049 | Friendswood Energy Generation | Harris | Jun-14 | Gas | 316 | New |
| 11INR0062 | Patriot (Petronilla) Wind | Nueces | Jun-14 | Wind | 178 |  |
| 13INR0021 | Ferguson Replacement Project | Llano | Jul-14 | Gas | 570 |  |
| 14INR0030a_2 | Panhandle Wind | Carson | Aug-14 | Wind | 218 |  |
| 13INR0040 | Rentech Project | Harris | Aug-14 | Gas | 15 |  |
| 10INR0021 | Panda Sherman Power | Grayson | Aug-14 | Gas | 809 |  |
| 10INR0020a | Panda Temple Power | Bell | Aug-14 | Gas | 791 |  |
| 11INR0050 | Moore Wind 1 | Crosby | Aug-14 | Wind | 149 |  |
| 14INR0032a | Route66 Wind | Randall | Sep-14 | Wind | 150 | New |
| 13INR0031 | Mustang Solar Project | Travis | Oct-14 | Solar | 30 | New |
| 13INR0010a | Mariah Wind | Parmer | Oct-14 | Wind | 200 |  |
| 13INR0020a | CPV Rattlesnake Den Ph 1 | Glasscock | Oct-14 | Wind | 200 |  |
| 13INR0020b | CPV Rattlesnake Den Ph 2 | Glasscock | Oct-14 | Wind | 150 |  |
| 11INR0054 | Midway Farms Wind | San Patricio | Oct-14 | Wind | 161 |  |
| 14INR0030b | Panhandle Wind 2 (Phase 2) | Carson | Nov-14 | Wind | 198 | New |
| 11INR0094 | White Camp Solar | Kent | Nov-14 | Solar | 100 |  |
| 13INR0052 | Los Vientos III | Starr | Dec-14 | Wind | 200 | New |
| 14INR0023 | Longhorn Energy Center | Briscoe | Dec-14 | Wind | 361 |  |
| 13INR0005 | Conway Windfarm | Carson | Dec-14 | Wind | 600 |  |
| 11INR0079a | South Clay Windfarm | Clay | Dec-14 | Wind | 200 |  |
| 06INR0022c | Penascal Wind Farm 3 | Kenedy | Dec-14 | Wind | 202 |  |
| 14INR0049_2 | Keechi Wind 138 kV Joplin | Jack | Dec-14 | Wind | 102 | New |
| 12INR0029 | Comanche Run Wind | Swisher | Dec-14 | Wind | 500 |  |
| 11INR0057 | Cameron County Wind | Cameron | Dec-14 | Wind | 165 |  |
| 13INR0010c | Mariah Wind | Parmer | Jan-15 | Wind | 200 |  |
| 09INR0051 | Mesquite Creek | Borden | Jan-15 | Wind | 249 |  |
| 08INR0018 | Gunsight Mountain | Howard | Aug-15 | Wind | 120 |  |
| 10INR0020b | Panda Temple Power | Bell | Aug-15 | Gas | 791 |  |
| 14INR0012b | Miami Wind 1 Project | Gray | Aug-15 | Wind | 170 |  |
| 12INR0018 | Pampa Wind Project | Gray | Dec-15 | Wind | 500 | New |
| 13INR0010b | Mariah Wind | Parmer | Dec-15 | Wind | 200 |  |
| 13INR0023 | Texas Clean Energy Project | Ector | Jan-16 | Coal | 240 |  |
| 13INR0028 | Antelope Station | Hale | Jun-16 | Gas | 359 |  |
| 10INR0022 | Pondera King Power Project | Harris | Jun-16 | Gas | 1380 |  |
| 06INR0006 | Cobisa-Greenville | Hunt | Dec-16 | Gas | 1792 |  |

## Projects Undergoing Full Interconnection Studies with Confidentiality Waived

| INR | Site Name | County | COD | Fuel | MW for Grid | Change from Last Report |
| --- | --- | --- | --- | --- | --- | --- |

## Generation Projects Undergoing Full Interconnection Studies

| Interconnection Database Reference Number | County | Fuel | Capacity to Grid (MW) | Commercial Operation Data (as specified by the resource developer) |
| --- | --- | --- | --- | --- |
| 14INR0039 | Ector | Gas | 450 | 3/1/2014 |
| 14INR0069 | Milam | Coal | 30 | 3/31/2014 |
| 14INR0013 | Cameron | Wind | 103 | 4/1/2014 |
| 14INR0024 | Kinney | Solar | 42 | 4/1/2014 |
| 14INR0048_1 | Wilbarger | Wind | 114 | 6/1/2014 |
| 14INR0038 | Galveston | Gas | 390 | 6/1/2014 |
| 13INR0026 | Oldham | Wind | 201 | 6/1/2014 |
| 14INR0048_2 | Wilbarger | Wind | 250 | 6/1/2014 |
| 14INR0040 | Hidalgo | Gas | 225 | 6/7/2014 |
| 12INR0059 | Pecos | Solar | 50 | 6/30/2014 |
| 14INR0014 | Val Verde | Solar | 100 | 7/1/2014 |
| 11INR0093 | San Patricio | Wind | 41 | 7/1/2014 |
| 14INR0059 | Kaufman | Gas | 52 | 8/1/2014 |
| 13INR0055 | Zapata | Wind | 250 | 9/1/2014 |
| 13INR0038 | Swisher | Wind | 300 | 9/15/2014 |
| 14INR0042 | Deaf Smith | Solar | 80 | 9/30/2014 |
| 14INR0062 | Hall/Motley | Wind | 200 | 9/30/2014 |
| 14INR0047 | Floyd and Crosby | Wind | 301 | 10/1/2014 |
| 13INR0036 | Hidalgo | Wind | 200 | 10/31/2014 |
| 12INR0045 | Kleberg | Wind | 135 | 10/31/2014 |
| 11INR0065 | Nueces | Wind | 350 | 10/31/2014 |
| 13INR0025 | Randall | Wind | 150 | 11/1/2014 |

| Interconnection Database Reference Number | County | Fuel | Capacity to Grid (MW) | Commercial Operation Data (as specified by the resource developer) |
| --- | --- | --- | --- | --- |
| 14INR0060 | Haskell | Wind | 400 | 11/1/2014 |
| 13INR0056 | Scurry | Wind | 366 | 11/21/2014 |
| 14INR0066 | Lamar | Gas | 130 | 11/30/2014 |
| 14INR0033 | Armstrong | Wind | 500 | 12/1/2014 |
| 14INR0043 | Sterling | Solar | 40 | 12/1/2014 |
| 14INR0041 | Willacy | Wind | 114 | 12/1/2014 |
| 14INR0028 | Live Oak | Wind | 300 | 12/1/2014 |
| 13INR0054 | Bee | Gas | 25 | 12/1/2014 |
| 14INR0025a | Floyd | Wind | 200 | 12/1/2014 |
| 14INR0044 | Reeves | Solar | 100 | 12/1/2014 |
| 13INR0050 | Comanche | Wind | 200 | 12/1/2014 |
| 10INR0085 | Ector | Solar | 57 | 12/1/2014 |
| 14INR0009 | Kent | Wind | 248 | 12/1/2014 |
| 11INR0082b | Val Verde | Wind | 150 | 12/1/2014 |
| 11INR0082a | Val Verde | Wind | 50 | 12/1/2014 |
| 13INR0045 | Castro | Wind | 288 | 12/30/2014 |
| 13INR0010d | Parmer | Wind | 200 | 12/31/2014 |
| 12INR0055 | Baylor | Wind | 40 | 12/31/2014 |
| 14INR0049_1 | Jack | Wind | 102 | 12/31/2014 |
| 14INR0045a | Webb | Wind | 502 | 12/31/2014 |
| 14INR0057a | Erath | Wind | 48 | 12/31/2014 |
| 14INR0057b | Erath | Wind | 48 | 12/31/2014 |
| 14INR0056 | Mills | Wind | 101 | 12/31/2014 |
| 14INR0053 | Oldham | Wind | 161 | 12/31/2014 |
| 12INR0070 | Knox | Wind | 300 | 1/1/2015 |
| 14INR0029 | Uvalde | Solar | 42 | 2/1/2015 |
| 15INR0036 | Uvalde | Solar | 105 | 3/1/2015 |
| 14INR0020 | Floyd & Motley | Wind | 150 | 3/1/2015 |
| 10INR0009 | Castro | Wind | 300 | 3/31/2015 |
| 15INR0053 | Winkler | Gas | 142 | 5/1/2015 |
| 15INR0054 | Reeves | Gas | 142 | 5/1/2015 |
| 15INR0055 | Austin | Gas | 142 | 5/1/2015 |
| 15INR0021 | Starr | Wind | 200 | 5/15/2015 |
| 14INR0031 | Harris | Gas | 270 | 6/1/2015 |
| 14INR0027 | Guadalupe | Gas | 471 | 6/1/2015 |
| 15INR0027 | Hidalgo | Gas | 79 | 6/1/2015 |
| 15INR0028 | Freestone | Gas | 160 | 6/1/2015 |
| 15INR0042 | Hood | Gas | 460 | 6/1/2015 |
| 15INR0022 | Presidio | Solar | 75 | 6/1/2015 |
| 15INR0023 | Wharton | Gas | 700 | 6/15/2015 |
| 14INR0026 | Presidio | Solar | 30 | 9/1/2015 |
| 15INR0041 | Pecos | Solar | 51 | 9/1/2015 |

| Interconnection Database Reference Number | County | Fuel | Capacity to Grid (MW) | Commercial Operation Data (as specified by the resource developer) |
| --- | --- | --- | --- | --- |
| 15INR0013 | Anderson | Storage | 324 | 10/9/2015 |
| 15INR0014 | Matagorda | Storage | 280 | 10/9/2015 |
| 14INR0030a_1 | Carson | Wind | 322 | 11/1/2015 |
| 14INR0025b | Floyd | Wind | 300 | 12/1/2015 |
| 08INR0019a | Gray | Wind | 250 | 12/1/2015 |
| 15INR0035 | Kenedy | Wind | 200 | 12/1/2015 |
| 12INR0060 | Schleicher | Wind | 58 | 12/1/2015 |
| 15INR0034 | San Patricio | Wind | 201 | 12/1/2015 |
| 14INR0045b | Webb | Wind | 251.00 | 12/31/2015 |
| 13INR0032 | Andrews | Solar | 30.00 | 12/31/2015 |
| 15INR0044 | Webb and Duval | Solar | 200.00 | 12/31/2015 |
| 15INR0049 | Zapata / Webb | Wind | 250.00 | 12/31/2015 |
| 14INR0072 | Briscoe | Wind | 300.00 | 12/31/2015 |
| 14INR0018 | Nolan | Solar | 20.00 | 12/31/2015 |
| 13INR0010e | Parmer | Wind | 200.00 | 12/31/2015 |
| 15INR0060 | Pecos and Crane Counties | Solar | 25.00 | 12/31/2015 |
| 15INR0059 | Pecos and Crane Counties | Solar | 102.00 | 12/31/2015 |
| 15INR0037 | Starr | Wind | 200.00 | 12/31/2015 |
| 12INR0002a | Briscoe | Wind | 200.00 | 12/31/2015 |
| 16INR0010 | Mitchell | Gas | 799.00 | 2/1/2016 |
| 16INR0005 | Cameron | Gas | 871.00 | 4/1/2016 |
| 16INR0009 | Calhoun | Gas | 510.00 | 4/14/2016 |
| 16INR0008 | Grimes | Gas | 687.00 | 5/1/2016 |
| 15INR0032 | Hale | Gas | 197.00 | 5/1/2016 |
| 15INR0033 | Hale | Gas | 197.00 | 5/1/2016 |
| 16INR0003 | Brazoria | Gas | 11.00 | 6/1/2016 |
| 16INR0004 | Cameron | Gas | 730.00 | 6/1/2016 |
| 16INR0007 | Hidalgo | Gas | 95.00 | 6/1/2016 |
| 17INR0004 | Hale | Gas | 202.00 | 6/1/2016 |
| 16INR0006 | Angelina | Gas | 785.00 | 6/1/2016 |
| 14INR0011 | Swisher | Storage | 270.00 | 7/1/2016 |
| 16INR0013 | Nacogdoches | Gas | 215.00 | 7/1/2016 |
| 08INR0019b | Gray | Wind | 250.00 | 7/1/2016 |
| 16INR0017 | Culberson County | Solar | 70.00 | 12/1/2016 |
| 08INR0019c | Gray | Wind | 250.00 | 12/1/2016 |
| 13INR0006 | Gray | Wind | 750.00 | 12/1/2016 |
| 16INR0018 | Upton | Solar | 40.00 | 12/1/2016 |
| 16INR0019 | Coke/Sterling | Solar | 100.00 | 12/1/2016 |
| 12INR0079 | Kenedy | Wind | 200.00 | 12/15/2016 |
| Interconnection Database Reference Number | County | Fuel | Capacity to Grid (MW) | Commercial Operation Data (as specified by the resource developer) |
| 13INR0010f | Parmer | Wind | 200.00 | 12/31/2016 |
| 12INR0002b | Briscoe | Wind | 200.00 | 12/31/2016 |
| 16INR0011a | Cameron | Wind | 18.00 | 12/31/2016 |
| 17INR0002 | Henderson | Gas | 489.00 | 6/1/2017 |
| 17INR0003 | Jackson | Gas | 965.00 | 6/1/2017 |
| 17INR0005 | Starr | Wind | 200.00 | 6/30/2017 |
| 17INR0007 | Wharton | Gas | 1177.00 | 7/31/2017 |
| 16INR0011b | Cameron | Wind | 132.00 | 12/30/2017 |

## Wind Generation Capacity Installed by Year

# Regional Planning Group Project Reviews

- CenterPoint Energy submitted the Houston Region Import Capacity project. This is a Tier 1 project that is estimated to cost between $297 to $532 million. This project is currently under ERCOT independent review.

- Garland Power & Light (GP&L) and Cross Texas Transmission (CTT) have jointly submitted the Houston Import project. This is a Tier 1 project that is estimated to cost between $195 to $317 million. This project has received several RPG comments and it is under study mode.

- Lone Star Transmission has submitted the Houston Import project. This is a Tier 1 project that is estimated to cost between $417 to $675 million. This project has received several RPG comments and it is under study mode.

- Oncor has submitted the West Texas Area project. This is a Tier 2 project that is estimated to cost between $45 million. This project has received several RPG comments and it is under study mode.

# Asynchronous Tie Interconnection

| Project | Notification to ERCOT | Reliability Study | RPG Review | Interconnection Agreement | In-service Year |
| --- | --- | --- | --- | --- | --- |
| Railroad DC tie expansion (150 MW - CFE) |  |  |  |  | 2014 |
| Southern Cross HVDC (3000 MW - SERC) |  |  |  |  |  |
| Tres Amigas (1500 MW - SPP) |  |  |  |  |  |

Color Legend

|  | In progress |
| --- | --- |
|  | Complete |

# Planning Model Activities

- The short term calendar of major planning model events follows:

  - Nov 15, 2013	Post 2014 DSB HWLL case to POI

  - Dec 13, 2013	Complete Transmission Loss Factor calculations

  - Jan 10, 2014	Post Planning Data Dictionary

# Other Notable Activities

- The project to complete the missing and questionable data for the remaining Resource Asset Registration Forms (RARF) nearing the end.  A list of entities that received data estimates and did not return a completed RARF by December 2, 2013 was compiled and sent to ERCOT Compliance.

- ERCOT is working on the 2013 Regional Transmission Plan (RTP). The economic start cases were posted at the ERCOT POI on Nov. 22, 2013. ERCOT is currently working on economic analysis and the 2013 RTP draft report.

- ERCOT has posted the draft report on the results of the Long-term study and the improvements to the long-term study process as a result of the grant received from the Department of Energy.

- ERCOT has issued a Request For Proposal (RFP) in order to hire a consultant to perform a small signal stability study.