|  |  |  |  | System Planning |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Monthly Status Report December 2013 |  |  |
|  |  | Report Highlights |  |  |  |  |  |  |
|  | - ERCOT is currently tracking active generation interconnection requests totaling over 51,100 MW. This includes over 24,200 MW of wind generation. |  |  |  |  |  |  |  |
|  | - ERCOT is currently reviewing proposed transmission improvements with a total cost of $849.7 Million - Transmission Projects endorsed in 2013 total $349.8 Million - All projects (in engineering, routing, licensing and construction) total approximately $6.23 Billion. - Transmission Projects energized in 2013 total about $3.17 Billion. |  |  |  |  |  |  |  |

Table of Contents

1.	Generation Interconnection	1

1.1	Signed Generation Interconnection Agreements	1

1.2	New Generation Approved for Commercial Operations	1

1.3	Summary of Generation Interconnection Requests	1

1.4	Projects with Interconnection Agreements	5

1.5	Projects Undergoing Full Interconnection Studies with Confidentiality Waived	6

1.6	Generation Projects Undergoing Full Interconnection Studies	6

1.7	Wind Generation Capacity Installed by Year	9

2.	Regional Planning Group Project Reviews	10

3.	Asynchronous Tie Interconnection	10

4.	Planning Model Activities	11

5.	Other Notable Activities	11

# 1.	Generation Interconnection

Additional information regarding detailed generation interconnection and impact studies is contained in the “Generation Project Interconnection Information” folder in the “Operations and System Planning” area on the ERCOT website:  http://planning.ercot.com/login/login.

## Signed Generation Interconnection Agreements

14INR0053 – Spinning Spur Wind III – 161 MW in Oldham County

12INR0070 – Green Pastures – 300 MW located in Knox County

13INR0050 – Logans Gap Wind 1 – 200 MW located in Comanche County

## New Generation Approved for Commercial Operations

The total installed wind capacity is now reported as 11,255 MW by the resource owners through the registration process. Capacity by North, South and West is 982 MW, 2,775 MW, and 7,498 MW respectively.  Eight-hundred fifty MW is able to switch between the West and South zones and is currently shown in the South zone.

## Summary of Generation Interconnection Requests

| GENERATION INTERCONNECTION REQUESTS CURRENTLY UNDER REVIEW |  |
| --- | --- |
| Currently tracking 205 generation interconnection or change requests |  |
| As of December 31, 2013 | Total |
| Security Screening Study | 19 |
| SSS Completed | 19 |
| Full Interconnect Study | 109 |
| FIS Completed | 10 |
| Suspended Studies | 0 |
| Capacity of Suspended Study Projects | 0 |
| Cancelled Projects | 5 |
| Interconnect Agreement Completed | 48 |
| Capacity under Interconnection Agreements | 15,465 |
| Capacity for Grid, MW | 51,113 |
| Wind Capacity, MW | 24,266 |
| Capacity of Cancelled Projects | 453 |

| Fuel Type | Confidential Projects (MW) | Projects Under Full Study (MW) | Public Projects (MW) | Suspended Studies (MW) | Grand Total (MW) |
| --- | --- | --- | --- | --- | --- |
| Gas-AllOther |  |  | 690 | - | 7,352 |
| Gas-CombinedCycle |  |  | 6,794 | - | 15,492 |
| Total Gas | 3,260 | 12,110 | 7,484 | - | 22,854 |
| Nuclear | - | - | - | - | - |
| Coal | - | 30 | 240 | - | 270 |
| Wind | 4,083 | 12,736 | 7,447 | - | 24,266 |
| Solar | 966 | 1,753 | 130 | - | 2,849 |
| Biomass | - | - | - | - | - |
| Storage | - | 874 | - | - | 874 |
| Petroleum Coke | - | - | - | - | - |
| Grand Total | 8,309 | 27,503 | 15,301 | - | 51,113 |

Cumulative Installed MW Capacity of Interconnection Requests by Zone

## Projects with Interconnection Agreements

| Generation Interconnection Agreements as of December 31, 2013 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| INR | Site Name | County | COD | Fuel | MW For Grid | Change from Last Report |
| 12INR0068 | Sendero Wind Energy Project | Jim Hogg | Feb-14 | Wind | 78 | Projected COD |
| 11INR0094 | White Camp Solar | Kent | Apr-14 | Solar | 100 | Projected COD |
| 14INR0016 | Channel Energy Center 138/345kV CT | Harris | Jun-14 | Gas | 190 |  |
| 13INR0048 | Spinning Spur Wind Two | Oldham | Jun-14 | Wind | 161 |  |
| 14INR0015 | Deer Park Energy Center | Harris | Jul-14 | Gas | 190 | MW for Grid |
| 13INR0021 | Ferguson Replacement Project | Llano | Jul-14 | Gas | 570 |  |
| 14INR0012a | Miami Wind 1 Project | Gray | Jul-14 | Wind | 289 | MW for Grid |
| 13INR0040 | Rentech Project | Harris | Aug-14 | Gas | 15 |  |
| 14INR0030a_2 | Panhandle Wind | Carson | Aug-14 | Wind | 218 |  |
| 10INR0021 | Panda Sherman Power | Grayson | Aug-14 | Gas | 720 |  |
| 10INR0020a | Panda Temple Power | Bell | Aug-14 | Gas | 717 |  |
| 11INR0050 | Moore Wind 1 | Crosby | Aug-14 | Wind | 149 |  |
| 14INR0030b | Panhandle Wind 2 (Phase 2) | Carson | Sep-14 | Wind | 198 | Projected COD |
| 13INR0059a | Hereford Wind | Castro | Sep-14 | Wind | 200 |  |
| 13INR0020a | CPV Rattlesnake Den Ph 1 | Glasscock | Oct-14 | Wind | 200 |  |
| 12INR0034 | Stephens Ranch Wind Energy | Borden | Oct-14 | Wind | 378 |  |
| 13INR0010a | Mariah Wind | Parmer | Oct-14 | Wind | 200 |  |
| 13INR0020b | CPV Rattlesnake Den Ph 2 | Glasscock | Oct-14 | Wind | 150 |  |
| 11INR0054 | Midway Farms Wind | San Patricio | Oct-14 | Wind | 161 |  |
| 14INR0032a | Route66 Wind | Randall | Dec-14 | Wind | 150 |  |
| 13INR0005 | Conway Windfarm | Carson | Dec-14 | Wind | 600 |  |
| 14INR0023 | Longhorn Energy Center | Briscoe | Dec-14 | Wind | 361 |  |
| 11INR0057 | Cameron County Wind | Cameron | Dec-14 | Wind | 165 |  |
| 14INR0053 | Spinning Spur Wind Three | Oldham | Dec-14 | Wind | 161 | New |
| 06INR0022c | Penascal Wind Farm 3 | Kenedy | Dec-14 | Wind | 202 |  |
| 14INR0049_2 | Keechi Wind 138 kV Joplin | Jack | Dec-14 | Wind | 102 |  |
| 13INR0052 | Los Vientos III | Starr | Dec-14 | Wind | 200 |  |
| 13INR0057 | Windthorst 2 | Archer | Dec-14 | Wind | 65 |  |
| 11INR0079a | South Clay Windfarm | Clay | Dec-14 | Wind | 200 |  |
| 09INR0051 | Mesquite Creek | Borden | Jan-15 | Wind | 249 |  |
| 12INR0070 | Green Pastures | Knox | Feb-15 | Wind | 300 | New |
| 13INR0059b | Hereford Wind | Castro | Apr-15 | Wind | 300 |  |
| 13INR0050 | Logans Gap Wind I | Comanche | May-15 | Wind | 200 | New |
| 08INR0018 | Gunsight Mountain | Howard | Aug-15 | Wind | 120 |  |
| 10INR0020b | Panda Temple Power | Bell | Aug-15 | Gas | 717 |  |
| 11INR0062 | Patriot (Petronilla) Wind | Nueces | Aug-15 | Wind | 178 |  |
| 14INR0012b | Miami Wind 1 Project | Gray | Aug-15 | Wind | 112 | MW for Grid |
| 13INR0049 | Friendswood Energy Generation | Harris | Sep-15 | Gas | 316 |  |
| 13INR0031 | Mustang Solar Project | Travis | Dec-15 | Solar | 30 |  |
| 13INR0010b | Mariah Wind | Parmer | Dec-15 | Wind | 200 |  |
| 13INR0023 | Texas Clean Energy Project | Ector | Jan-16 | Coal | 240 |  |
| 13INR0028 | Antelope Station | Hale | Jun-16 | Gas | 359 |  |
| 06INR0006 | Cobisa-Greenville | Hunt | Dec-16 | Gas | 1792 | Projected COD |
| 10INR0022 | Pondera King Power Project | Harris | Dec-16 | Gas | 1629 | MW for Grid,Proj. COD |
| 12INR0029 | Comanche Run Wind | Swisher | Dec-16 | Wind | 500 |  |
| 13INR0010c | Mariah Wind | Parmer | Dec-16 | Wind | 200 |  |
| 12INR0018 | Pampa Wind Project | Gray | Mar-17 | Wind | 500 |  |

## Projects Undergoing Full Interconnection Studies with Confidentiality Waived

| INR | Site Name | County | COD | Fuel | MW for Grid | Change from Last Report |
| --- | --- | --- | --- | --- | --- | --- |

## Generation Projects Undergoing Full Interconnection Studies

| Interconnection Database Reference Number | County | Fuel | Capacity to Grid (MW) | Commercial Operation Data (as specified by the resource developer) |
| --- | --- | --- | --- | --- |
| 14INR0069 | Milam | Coal | 30 | Mar-14 |
| 14INR0013 | Cameron | Wind | 103 | Apr-14 |
| 14INR0048_1 | Wilbarger | Wind | 114 | Jun-14 |
| 14INR0048_2 | Wilbarger | Wind | 250 | Jun-14 |
| 14INR0040 | Hidalgo | Gas | 225 | Jun-14 |
| 12INR0059 | Pecos | Solar | 50 | Jun-14 |
| 11INR0093 | San Patricio | Wind | 41 | Jul-14 |
| 14INR0014 | Val Verde | Solar | 100 | Jul-14 |
| 14INR0059 | Kaufman | Gas | 52 | Aug-14 |
| 13INR0055 | Zapata | Wind | 250 | Sep-14 |
| 13INR0038 | Swisher | Wind | 300 | Sep-14 |
| 14INR0062 | Hall/Motley | Wind | 200 | Sep-14 |
| 12INR0045 | Kleberg | Wind | 135 | Oct-14 |
| 13INR0025 | Randall | Wind | 150 | Nov-14 |
| 14INR0060 | Haskell | Wind | 400 | Nov-14 |
| 13INR0056 | Scurry | Wind | 366 | Nov-14 |
| 14INR0066 | Lamar | Gas | 130 | Nov-14 |
| 11INR0082a | Val Verde | Wind | 50 | Dec-14 |
| 11INR0082b | Val Verde | Wind | 150 | Dec-14 |
| 14INR0009 | Kent | Wind | 248 | Dec-14 |
| 10INR0085 | Ector | Solar | 57 | Dec-14 |
| 14INR0025a | Floyd | Wind | 200 | Dec-14 |

| Interconnection Database Reference Number | County | Fuel | Capacity to Grid (MW) | Commercial Operation Data (as specified by the resource developer) |
| --- | --- | --- | --- | --- |
| 13INR0054 | Bee | Gas | 25 | Dec-14 |
| 14INR0028 | Live Oak | Wind | 300 | Dec-14 |
| 14INR0029 | Uvalde | Solar | 42 | Dec-14 |
| 14INR0033 | Armstrong | Wind | 500 | Dec-14 |
| 14INR0041 | Willacy | Wind | 114 | Dec-14 |
| 14INR0043 | Sterling | Solar | 40 | Dec-14 |
| 14INR0044 | Reeves | Solar | 100 | Dec-14 |
| 13INR0045 | Castro | Wind | 288 | Dec-14 |
| 12INR0055 | Baylor | Wind | 40 | Dec-14 |
| 13INR0010d | Parmer | Wind | 200 | Dec-14 |
| 14INR0045a | Webb | Wind | 502 | Dec-14 |
| 14INR0049_1 | Jack | Wind | 102 | Dec-14 |
| 14INR0056 | Mills | Wind | 101 | Dec-14 |
| 14INR0057a | Erath | Wind | 48 | Dec-14 |
| 14INR0057b | Erath | Wind | 48 | Dec-14 |
| 14INR0020 | Floyd & Motley | Wind | 150 | Mar-15 |
| 14INR0039 | Ector | Gas | 450 | Mar-15 |
| 14INR0050 | Uvalde | Solar | 40 | Mar-15 |
| 15INR0036 | Uvalde | Solar | 105 | Mar-15 |
| 15INR0069 | Pecos | Solar | 110 | Mar-15 |
| 15INR0070 | Pecos | Solar | 110 | Mar-15 |
| 10INR0009 | Castro | Wind | 300 | Mar-15 |
| 14INR0038 | Galveston | Gas | 390 | Apr-15 |
| 15INR0053 | Winkler | Gas | 123 | May-15 |
| 15INR0054 | Reeves | Gas | 123 | May-15 |
| 15INR0055 | Austin | Gas | 142 | May-15 |
| 15INR0021 | Starr | Wind | 200 | May-15 |
| 15INR0027 | Hidalgo | Gas | 79 | Jun-15 |
| 15INR0028 | Freestone | Gas | 160 | Jun-15 |
| 15INR0042 | Hood | Gas | 460 | Jun-15 |
| 15INR0023 | Wharton | Gas | 700 | Jun-15 |
| 14INR0026 | Presidio | Solar | 30 | Sep-15 |
| 15INR0013 | Anderson | Storage | 324 | Oct-15 |
| 15INR0014 | Matagorda | Storage | 280 | Oct-15 |
| 14INR0030a_1 | Carson | Wind | 322 | Nov-15 |
| 08INR0019a | Gray | Wind | 250 | Dec-15 |
| 15INR0034 | San Patricio | Wind | 201 | Dec-15 |
| 15INR0035 | Kenedy | Wind | 200 | Dec-15 |
| 14INR0025b | Floyd | Wind | 300 | Dec-15 |
| 15INR0065 | Anson | Solar | 150 | Dec-15 |
| 12INR0002a | Briscoe | Wind | 200 | Dec-15 |
| 13INR0032 | Andrews | Solar | 30 | Dec-15 |

| Interconnection Database Reference Number | County | Fuel | Capacity to Grid (MW) | Commercial Operation Data (as specified by the resource developer) |
| --- | --- | --- | --- | --- |
| 13INR0010e | Parmer | Wind | 200 | Dec-15 |
| 14INR0045b | Webb | Wind | 251 | Dec-15 |
| 15INR0037 | Starr | Wind | 200 | Dec-15 |
| 15INR0044 | Webb and Duval | Solar | 200 | Dec-15 |
| 15INR0049 | Zapata / Webb | Wind | 250 | Dec-15 |
| 14INR0072 | Briscoe | Wind | 300 | Dec-15 |
| 15INR0059 | Pecos / Crane | Solar | 102 | Dec-15 |
| 15INR0060 | Pecos / Crane | Solar | 25 | Dec-15 |
| 15INR0066 | Pecos | Solar | 80 | Dec-15 |
| 15INR0067 | Reeves | Solar | 80 | Dec-15 |
| 16INR0010 | Mitchell | Gas | 799 | Feb-16 |
| 16INR0009 | Calhoun | Gas | 510 | Apr-16 |
| 16INR0006 | Angelina | Gas | 785 | Jun-16 |
| 16INR0003 | Brazoria | Gas | 11 | Jun-16 |
| 16INR0004 | Cameron | Gas | 730 | Jun-16 |
| 16INR0005 | Cameron | Gas | 871 | Jun-16 |
| 16INR0007 | Hidalgo | Gas | 95 | Jun-16 |
| 17INR0004 | Hale | Gas | 202 | Jun-16 |
| 08INR0019b | Gray | Wind | 250 | Jul-16 |
| 14INR0011 | Swisher | Storage | 270 | Jul-16 |
| 15INR0032 | Hale | Gas | 197 | Jul-16 |
| 15INR0033 | Hale | Gas | 197 | Jul-16 |
| 16INR0013 | Nacogdoches | Gas | 215 | Jul-16 |
| 16INR0025 | Sterling | Solar | 30 | Sep-16 |
| 08INR0019c | Gray | Wind | 250 | Dec-16 |
| 13INR0006 | Gray | Wind | 750 | Dec-16 |
| 16INR0017 | Culberson County | Solar | 70 | Dec-16 |
| 16INR0018 | Upton | Solar | 40 | Dec-16 |
| 16INR0019 | Coke/Sterling | Solar | 100 | Dec-16 |
| 12INR0002b | Briscoe | Wind | 200 | Dec-16 |
| 13INR0010f | Parmer | Wind | 200 | Dec-16 |
| 16INR0011a | Cameron | Wind | 18 | Dec-16 |
| 16INR0026 | Erath, Somervell & Bosque | Wind | 100 | Dec-16 |
| 16INR0027 | Grayson & Fannin | Wind | 100 | Dec-16 |
| 16INR0028 | Jack, Wise & Parker | Wind | 100 | Dec-16 |
| 16INR0029 | Hill & Limestone | Wind | 100 | Dec-16 |
| 16INR0030 | Young & Jack | Wind | 201 | Dec-16 |
| 16INR0031 | Zapata & Starr | Wind | 100 | Dec-16 |
| 16INR0032 | Jim Hogg | Wind | 201 | Dec-16 |
| Interconnection Database Reference Number | County | Fuel | Capacity to Grid (MW) | Commercial Operation Data (as specified by the resource developer) |
| 17INR0002 | Henderson | Gas | 489 | Jun-17 |
| 17INR0003 | Jackson | Gas | 965 | Jun-17 |
| 17INR0005 | Starr | Wind | 200 | Jun-17 |
| 17INR0007 | Wharton | Gas | 1177 | Jul-17 |
| 16INR0011b | Cameron | Wind | 132 | Dec-17 |
| 11INR0040 | Freestone | Gas | 640 | Mar-18 |

## Wind Generation Capacity Installed by Year

# Regional Planning Group Project Reviews

- CenterPoint Energy submitted the Houston Region Import Capacity project. This is a Tier 1 project that is estimated to cost between $297 to $532 million. This project is currently under ERCOT independent review.

- Garland Power & Light (GP&L) and Cross Texas Transmission (CTT) have jointly submitted a Houston Import project. This is a Tier 1 project that is estimated to cost between $195 to $317 million. This project has received several RPG comments and it is under study mode.

- Lone Star Transmission has submitted a Houston Import project. This is a Tier 1 project that is estimated to cost between $417 to $675 million. This project has received several RPG comments and it is under study mode.

- Oncor has submitted the West Texas Area project. This is a Tier 2 project that is estimated to cost $45 million. This project has received several RPG comments and is under ERCOT independent review.

- CenterPoint has submitted the Katy Area project. This is a Tier 2 project that is estimated to cost $20.4 million. This project has been submitted for RPG comments.

- LCRA TSC has submitted the Leander – Round Rock 138 kV project. This is a Tier 1 project that is estimated to cost $50.9 million. This project has been submitted for RPG comments.

- Sharyland has submitted the Brady Area project. This is a Tier 2 project that is estimated to cost $18 million. This project has been submitted for RPG comments.

- Sharyland has submitted the West Texas projects for Stanton Area. This is a Tier 3 project that is estimated to cost $40.4 million. This project has been submitted for RPG comments.

# Asynchronous Tie Interconnection

| Project | Notification to ERCOT | Reliability Study | RPG Review | Interconnection Agreement | In-service Year |
| --- | --- | --- | --- | --- | --- |
| Railroad DC tie expansion (150 MW - CFE) |  |  |  |  | 2014 |
| Southern Cross HVDC (3000 MW - SERC) |  |  |  |  |  |
| Tres Amigas (1500 MW - SPP) |  |  |  |  |  |

Color Legend

|  | In progress |
| --- | --- |
|  | Complete |

# Planning Model Activities

- The short term calendar of major planning model events follows:

  - Dec 27, 2013	Transmission Loss Factor calculations completed

  - Jan 6, 2014	Start 14DSA and 14DSB update

  - Jan 10, 2014	Post Planning Data Dictionary

  - Mar 1, 2014	Post 14DSA and 14DSB updated cases

  - Mar 15, 2014	Post MODTPIT

  - Apr 1, 2014	Start 15DSA case build process

# Other Notable Activities

- The System Protection Working Group 2014 Current Year (CY) base creation process has started.  The process will include 4 passes and conclude March 21, 2014.

- ERCOT has completed the 2013 Regional Transmission Plan (RTP) study and the 2013 RTP final report was posted at the ERCOT POI on Dec. 30, 2013.

- ERCOT has posted the final report on the results of the Long-term study and the improvements to the long-term study process as a result of the grant received from the Department of Energy.

- ERCOT has completed and posted the 2013 Constraints and Needs Report.

- ERCOT has entered into an agreement with Powertech Labs to perform a small signal stability study.