## Sheet1
TX SET Meeting Notes / Action Items
12/04/2013and 12/05/2013 ( 2 day meeting)
Agenda Item: | Decision / Resolution | Action Items :
November 2013 Meeting Notes | Reviewed and adjusted meeting notes as needed | Have posted to November meeting website
Mass Transition/Default-POLR Rule | Mass TransitionRMS assignment Possible POLR Rule change from two days out to one day out. Review and discuss analysis document conference call | Discussed and drafted possible changes to current process to reduce large number of transaction flow. Continue to identify additional methods to improve processing efficiencies
2013 Goals and Accomplishments | Drafted 2013/2014 goals and accomplishments | Revised the slide deck to present to RMS
Non Standard Metering | Reviewed the Draft RMGRR and made changes to the language where needed to present to DEC RMS meeting | RMGRR118 Approved by RMS
TX SET Procedures | On Hold-Discuss reline changes sent to the TXSET listserv for review | Leave current issue process in tact and continue to review document to identify where additional process improvements can be made
Market Test Update | Flight 1013 Summary- 95% complete/ remaining banking scripts need to be completed Schedule Flight scheduled to conclude 11/19/13 (contingency period until 12/10/13)
ERCOT Market Testing | Review of current market testing process | Sub team meeting held Dec. 4th & 5th to continue discussion of testing process
Issues
134-Non-CSA CR sends a MVO with the indicator for bypass CSA at ERCOT. Non-CSA CR is not always the owner of the CSA, causing the ESI ID to become de-energized without CSA CRs knowledge | Reviewed and revised the protocol change request and draft NPRR for approval | Submitted NPRR583 validate CSA bypass code
139- Change the 814_20 to add submission to request the transmission load | Submitted by ERCOT | On hold until Jan Meeting-Send out to market for review to discuss at upcomingTx SET meeting
Other Business
Next Meeting |  | Jan 22 & 23--Room 168 ERCOT MET Center
Attendees
Kathryn Thurman (ERCOT) Becky Taylor (CNP) Diana Rehfeldt (TNMP) Ed Echols (Oncor ) Kathy Scott (CNP) John Schatz (TXUE) Monica Jones (Reliant) Christine Hughey (Constellation - WebEx) Gricelda Calzada(AEP) Kim Wall(PPL Solutions) Jennifer Teal( Big Data) Mike Woolsey(ONCOR) Sarah Heselmeyer(ERCOT) Lee Star(BTU) M Glass( Sharyland) Tiffany Lewis(ConE Solutions) | Barbara Goubeaud(EC Info Systems) Sandra Tindall(ERCOT- webex) Joe Lindsey (Sys-trends WebEx) Amy Rafferty (ESG-WebEx) Carolyn Reed (CNP) Kyle Patrick (Reliant) Deb Belin Elisa Garcia Jim Lee(Direct Energy) Darice Taipalus Heather Mesa(Sharyland) Jacqueline Stevenson Rita Cardenas(AEP) | Kaci Jacobs(TXU) Paul Yockey(ERCOT-WebEx) Suzy Clifton (ERCOT-WebEx) Roger Tenenbown (ISTA NA-webex) Pam Shaw(SU) Mary Sithihao(Stream Energy-WebEx) Dave Michelsen(ERCOT) Teresa Rodriguez(Stream) Thomas Daniels Cliff Crouch(PUCT) Vijayalakshmi(TNMP)