## Slide 1
Project Update and Summary of Project Priority List (PPL) Activity to Date
January 16, 2014

## Slide 2: 2013 Project Update – Agenda
  Project Portfolio Update p. 3-7
    Recent/Upcoming Project Highlights
    2013 Release Targets
    2013 Project Spending Update
    2014 Release Targets
    2013 Project Spending Update
  Appendix
    Project Portfolio Gantt Chart p. 8-17
Location of Project Priority List (PPL): http://www.ercot.com/services/projects/index

## Slide 3: Recent/Upcoming Project Highlights
2014 Off-Cycle Go-Lives (January 2014) Complete
  NPRR575 – Clarification of the RUC Resource Buy-Back Provision for Ancillary Services
    Allowed NPRR416 to be implemented (originally targeted for 2013-R5)
    Implemented 1/7/2014 (see market notice dated 12/23/2013)
  Emergency Notification System Hardware Refresh
  Dev Hardware Refresh and Virtualization Expansion
2014 Release 1 Go-Lives (February 2014) In-Flight
  NPRR240 – Proxy Energy Offer Curve
    Part of 2014 Market System Enhancements project
  NPRR425 – Creation of a WGR Group for GREDP and Base Point Deviation Evaluation
    Phase 2 – GREDP and EIS components
  NPRR509 – Shortened RTM Settlement Timeline
  NOGRR105 – Generation Resource Frequency Response Test Procedure
  Alstom Load Forecasting Upgrade
  Disaster Recovery: S&B, Retail and Market Data Transparency
  Cyber-Security Project #14
Note: Projected Go-Live dates are subject to change. Please watch for market notices as the effective dates approach.

## Slide 4: 2013 Release Targets – Board-Approved NPRRs/SCRs/xGRRs
Release Approach | Release 1 2/11 – 2/15 | Release 2 4/22 – 4/26 | Release 3 6/10 – 6/14 | Release 4 7/29 – 8/2 | Release 5 9/23 – 9/29 | Release 6 12/9-12/13 | 2013 TBD
On-Cycle | NPRR260 NPRR313 NPRR322 NPRR377 NPRR397 NPRR407(a) NPRR464 NPRR469 SCR768 | NPRR456 | NPRR481 NPRR520(a) NOGRR093 | NPRR393 NPRR461 NPRR520(b) SCR760(d) | NPRR207 NPRR385 NPRR457 NPRR514 NOGRR101 SCR770 | NPRR407(b) NPRR425(a) NPRR476 NPRR492 | 
Off-Cycle |  | NPRR463 | SCR773 |  |  | NPRR479 NPRR484(1a) | 
Counts Total = 31 | 9 | 2 | 4 | 4 | 6 | 6 | 0
Early April
None
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
(a), (b), etc. indicates multiple phases
Release targets are subject to change
Red Text: New additions and target release changes
Strike-Through Text: Previous target release changes
None
October
None
Late May
Moved to Future Years
NPRR407(a) – MMS portion
NPRR407(b) – CRR portion
NPRR425(a) – RARF, EMS portions
NPRR484(1a) – initial CMM/CRR components
NPRR520(a) – MMS, MIS, CDR portions
NPRR520(b) – EMS, NMMS, ICCP portions
SCR760(d) – final phase
ü
ü
ü
ü
ü
ü
ü
ü
ü

## Slide 5: 2013 Cash Flow Projection – Year-End Total
ERCOT Board of Directors approved a project budget increase of $1M on 5/14/2013
Revised 2013 project budget is $16M

## Slide 6: 2014 Release Targets – Board-Approved NPRRs/SCRs/xGRRs
Release Approach | Release 1 2/3 – 2/7 | Release 2 4/14 – 4/18 | Release 3 6/9 – 6/13 | Release 4 7/28 – 8/1 | Release 5 9/22–9/26 | Release 6 12/8–12/12 | 2014 TBD
On-Cycle | NPRR240 NPRR425(b) NPRR509 NOGRR105 | NPRR240 NPRR485 NPRR570 SCR769 SCR772 | SCR756(b) | NPRR439 NPRR491 | NPRR500 NPRR543 NPRR559 | NPRR272 NPRR487 NPRR495 NPRR500 NPRR519 NPRR524 SCR771 | NPRR327 NPRR467 NPRR484(1b) NPRR487 NPRR491 NPRR527 NPRR543 NPRR553 NPRR559
Off-Cycle | NPRR416 NPRR575 |  | NPRR532 NPRR555 NPRR564 NPRR568 NPRR571 OBD(Shadow Price Caps) |  |  |  | NPRR570 NPRR467 NPRR553
Counts Total = 31 | 6 | 4 | 7 | 2 | 3 | 6 | 3
None
January
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
None
None
None
June–1st week
NPRR425(b) – GREDP, EIS portions
NPRR484(Ph1b) – Remaining Phase 1 items
SCR756(b) – Remaining portions of SCR
(a), (b), etc. indicates multiple phases
Red Text: New additions and target release changes
Strike-Through Text: Previous target release changes
Moved to 2015
ü

## Slide 7: 2014 Cash Flow Projection – Approved Projects
2014 project budget = $25M

## Slide 8: Business Integration Update – Appendix
  Appendix
    1/6/2014 Project Gantt
      In-flight items sorted by Project End Date
      “On Hold” projects listed separately
      “Not Started” items sorted by Project Start Date

## Slide 9
Project Portfolio Status – as of 1/6/2014

## Slide 10
Project Portfolio Status – as of 1/6/2014

## Slide 11
Project Portfolio Status – as of 1/6/2014

## Slide 12
Project Portfolio Status – as of 1/6/2014

## Slide 13
Project Portfolio Status – as of 1/6/2014

## Slide 14
Project Portfolio Status – as of 1/6/2014

## Slide 15
Project Portfolio Status – as of 1/6/2014

## Slide 16
Project Portfolio Status – as of 1/6/2014

## Slide 17
Project Portfolio Status – as of 1/6/2014