## Slide 1
Project Update and Summary of Project Priority List (PPL) Activity to Date
February 13, 2014

## Slide 2: 2013 Project Update – Agenda
  Project Portfolio Update p. 3-7
    Recent/Upcoming Project Highlights
    2014 Release Targets
    2014 Project Spending Update
  Appendix
    Project Portfolio Gantt Chart p. 8-17
Location of Project Priority List (PPL): http://www.ercot.com/services/projects/index

## Slide 3: Recent/Upcoming Project Highlights
2014 Release 1 Go-Lives (February 2014) Complete
  NPRR240 – Proxy Energy Offer Curve
    Part of 2014 Market System Enhancements project
  NPRR425 – Creation of a WGR Group for GREDP and Base Point Deviation Evaluation
    Phase 2 – GREDP and EIS components
  NOGRR105 – Generation Resource Frequency Response Test Procedure
  Alstom Load Forecasting Upgrade
  Cyber-Security Project #14
2014 Release 1 Go-Lives – Retail (February 2014) In-Flight
  NPRR509 – Shortened RTM Settlement Timeline
2014 Release 2 Go-Lives (April 2014) In-Flight
  NPRR564 – Thirty-Minute Emergency Response Service (ERS) and Other ERS Services
  NPRR570 – Reduce RTM Settlement Timeline to Operating Day Plus Five
  SCR772 – New Extract for Five Minute Interval Settlement Data
  Cyber-Security Project #9
Note: Projected Go-Live dates are subject to change. Please watch for market notices as the effective dates approach.

## Slide 4: 2014 Release Targets – Board-Approved NPRRs/SCRs/xGRRs
Release Approach | Release 1 2/3 – 2/7 | Release 2 4/14 – 4/18 | Release 3 6/9 – 6/13 | Release 4 7/28 – 8/1 | Release 5 9/22–9/26 | Release 6 12/8–12/12 | 2014 TBD
On-Cycle | NPRR240 NPRR425(b) NOGRR105 NPRR509 | NPRR485 NPRR564 NPRR570 SCR769 SCR772 | SCR769 SCR756(b) | NPRR439 NPRR491 | NPRR485 NPRR500 NPRR543 NPRR559 | NPRR272 NPRR487 NPRR495 NPRR519 NPRR524 | NPRR327 NPRR484(1b) NPRR527
Off-Cycle | NPRR416 NPRR575 |  | NPRR532 NPRR555 NPRR564 NPRR568 NPRR571 OBD(Shadow Price Caps) |  |  | SCR771 | NPRR439
Counts Total = 30 | 6 | 3 | 7 | 1 | 4 | 6 | 3
None
January
Go-live dates can differ from Protocol effective dates – Please refer to market notices for more details
Release targets are subject to change
None
None
None
June–1st week
NPRR425(b) – GREDP, EIS portions
NPRR484(Ph1b) – Remaining Phase 1 items
SCR756(b) – Remaining portions of SCR
(a), (b), etc. indicates multiple phases
Red Text: New additions and target release changes
Strike-Through Text: Previous target release changes
Moved to 2015
ü
Retail: 2/22-2/23
Retail: 6/21-6/22
ü

## Slide 5: 2014 Cash Flow Projection – Approved Projects
2014 project budget = $25M

## Slide 6: Business Integration Update – Appendix
  Appendix
    2/7/2014 Project Gantt
      In-flight items sorted by Project End Date
      “On Hold” projects listed separately
      “Not Started” items sorted by Project Start Date

## Slide 7
Project Portfolio Status – as of 2/7/2014

## Slide 8
Project Portfolio Status – as of 2/7/2014

## Slide 9
Project Portfolio Status – as of 2/7/2014

## Slide 10
Project Portfolio Status – as of 2/7/2014

## Slide 11
Project Portfolio Status – as of 2/7/2014

## Slide 12
Project Portfolio Status – as of 2/7/2014

## Slide 13
Project Portfolio Status – as of 2/7/2014

## Slide 14
Project Portfolio Status – as of 2/7/2014

## Slide 15
Project Portfolio Status – as of 2/7/2014