|  |  |  |  | System Planning |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Monthly Status Report January 2014 |  |  |
|  |  | Report Highlights |  |  |  |  |  |  |
|  | - ERCOT is currently tracking 210 active generation interconnection requests totaling over 52,300 MW. This includes over 25,200 MW of wind generation. |  |  |  |  |  |  |  |
|  | - ERCOT is currently reviewing proposed transmission improvements with a total cost of $876.2 Million - Transmission Projects endorsed in 2013 total $349.8 Million - All projects (in engineering, routing, licensing and construction) total approximately $6.23 Billion. - Transmission Projects energized in 2013 total about $3.17 Billion. |  |  |  |  |  |  |  |

Table of Contents

1.	Generation Interconnection	1

1.1	Signed Generation Interconnection Agreements	1

1.2	New Generation Approved for Commercial Operations	1

1.3	Summary of Generation Interconnection Requests	1

1.4	Projects with Interconnection Agreements	5

1.5	Projects Undergoing Full Interconnection Studies with Confidentiality Waived	6

1.6	Generation Projects Undergoing Full Interconnection Studies	7

1.7	Wind Generation Capacity Installed by Year	10

2.	Regional Planning Group Project Reviews	11

3.	Asynchronous Tie Interconnection	11

4.	Planning Model Activities	12

5.	Other Notable Activities	12

# 1.	Generation Interconnection

Additional information regarding detailed generation interconnection and impact studies is contained in the “Generation Project Interconnection Information” folder in the “Operations and System Planning” area on the ERCOT website:  http://planning.ercot.com/login/login.

## Signed Generation Interconnection Agreements

14INR0024 – OCI Alamo 4 – 42 MW in Kinney County

14INR0025a – South Plains Wind 1 – 200 MW located in Floyd County

12INR0059 – Barilla Solar – 30 MW located in Pecos County

14INR0038 – PHR Peakers – 390 MW located in Galveston County

14INR0039 – Goldsmith Peaking Facility – 408 MW located in Ector County

14INR0025b – South Plains II – 300 MW located in Floyd County

## New Generation Approved for Commercial Operations

The total installed wind capacity is now reported as 11,213 MW by the resource owners through the registration process. Capacity by North, South and West is 982 MW, 2,775 MW, and 7,456 MW respectively.  Eight-hundred fifty MW is able to switch between the West and South zones and is currently shown in the South zone.

## Summary of Generation Interconnection Requests

| GENERATION INTERCONNECTION REQUESTS CURRENTLY UNDER REVIEW |  |
| --- | --- |
| Currently tracking 210 generation interconnection or change requests |  |
| As of January 31, 2013 | Total |
| Security Screening Study | 13 |
| SSS Completed | 30 |
| Full Interconnect Study | 102 |
| FIS Completed | 10 |
| Suspended Studies | 0 |
| Capacity of Suspended Study Projects | 0 |
| Cancelled Projects | 4 |
| Interconnect Agreement Completed | 55 |
| Capacity under Interconnection Agreements | 16,715 |
| Capacity for Grid, MW | 52,367 |
| Wind Capacity, MW | 25,240 |
| Capacity of Cancelled Projects | 918 |

| Fuel Type | Confidential Projects (MW) | Projects Under Full Study (MW) | Public Projects (MW) | Suspended Studies (MW) | Grand Total (MW) |
| --- | --- | --- | --- | --- | --- |
| Gas-AllOther |  |  | 1,499 | - | 7,442 |
| Gas-CombinedCycle |  |  | 7,032 | - | 15,684 |
| Total Gas | 3,382 | 11,213 | 8,531 | - | 23,126 |
| Nuclear | - | - | - | - | - |
| Coal | - | 30 | 240 | - | 270 |
| Wind | 4,582 | 12,678 | 7,979 | - | 25,240 |
| Solar | 1,326 | 1,329 | 202 | - | 2,857 |
| Biomass | - | - | - | - | - |
| Storage | - | 874 | - | - | 874 |
| Petroleum Coke | - | - | - | - | - |
| Grand Total | 9,290 | 26,124 | 16,952 | - | 52,367 |

Cumulative Installed MW Capacity of Interconnection Requests by Zone

## Projects with Interconnection Agreements

| Generation Interconnection Agreements as of January 31, 2014 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| INR | Site Name | County | COD | Fuel | MW For Grid | Change from Last Report | Sufficient Financial Security Received by TSP |
| 11INR0094 | White Camp Solar | Kent | 4/2014 | SOLAR | 100 |  | No |
| 13INR0048 | Spinning Spur Wind Two | Oldham | 6/2014 | WIND | 161 |  | Yes |
| 14INR0024 | OCI Alamo 4 | Kinney | 6/2014 | SOLAR | 42 | New | No |
| 14INR0016 | Channel Energy Center 138/345kV CT | Harris | 6/2014 | GAS | 190 |  | Yes |
| 14INR0015 | Deer Park Energy Center | Harris | 7/2014 | GAS | 190 |  | Yes |
| 13INR0021 | Ferguson Replacement Project | Llano | 7/2014 | GAS | 570 |  | Yes |
| 14INR0012a | Miami Wind 1 Project | Gray | 7/2014 | WIND | 289 |  | Yes |
| 14INR0030a_2 | Panhandle Wind | Carson | 8/2014 | WIND | 218 |  | Yes |
| 13INR0040 | Rentech Project | Harris | 8/2014 | GAS | 15 |  | Yes |
| 10INR0020a | Panda Temple Power | Bell | 8/2014 | GAS | 717 |  | Yes |
| 10INR0021 | Panda Sherman Power | Grayson | 8/2014 | GAS | 720 |  | Yes |
| 11INR0050 | Moore Wind 1 | Crosby | 8/2014 | WIND | 149 |  | No |
| 14INR0030b | Panhandle Wind 2 (Phase 2) | Carson | 9/2014 | WIND | 198 |  | Yes |
| 13INR0059a | Hereford Wind | Castro | 9/2014 | WIND | 200 |  | Yes |
| 13INR0010a | Mariah Wind | Parmer | 10/2014 | WIND | 232 | MW Change | No |
| 12INR0034 | Stephens Ranch Wind Energy | Borden | 10/2014 | WIND | 378 |  | Yes |
| 13INR0005 | Conway Windfarm | Carson | 12/2014 | WIND | 600 |  | Yes |
| 14INR0023 | Longhorn Energy Center | Briscoe | 12/2014 | WIND | 361 |  | Yes |
| 14INR0025a | South Plains Wind I | Floyd | 12/2014 | WIND | 200 | New | No |
| 14INR0032a | Route66 Wind | Randall | 12/2014 | WIND | 150 |  | No |
| 12INR0059 | Barilla Solar | Pecos | 12/2014 | SOLAR | 30 | New | Yes |
| 14INR0053 | Spinning Spur Wind Three | Oldham | 12/2014 | WIND | 194 | MW Change | Yes |
| 11INR0079a | South Clay Windfarm | Clay | 12/2014 | WIND | 200 |  | No |
| 13INR0057 | Windthorst 2 | Archer | 12/2014 | WIND | 65 |  | No |
| 13INR0052 | Los Vientos III | Starr | 12/2014 | WIND | 200 |  | Yes |
| 14INR0049_2 | Keechi Wind 138 kV Joplin | Jack | 12/2014 | WIND | 102 |  | Yes |
| 06INR0022c | Baffin (Penascal Wind Farm 3) | Kenedy | 12/2014 | WIND | 202 |  | Yes |
| 09INR0051 | Mesquite Creek | Borden | 1/2015 | WIND | 249 |  | Yes |
| 12INR0070 | Green Pastures | Knox | 2/2015 | WIND | 300 |  | Yes |
| 12INR0068 | Sendero Wind Energy Project | Jim Hogg | 2/2015 | WIND | 78 |  | Yes |
| 13INR0059b | Hereford Wind | Castro | 4/2015 | WIND | 300 |  | Yes |
| 14INR0038 | PHR Peakers | Galveston | 4/2015 | GAS | 390 | New | No |
| 13INR0020a | CPV Rattlesnake Den Ph 1 | Glasscock | 5/2015 | WIND | 201 | Date change | Yes |
| 13INR0050 | Logans Gap Wind I | Comanche | 5/2015 | WIND | 200 |  | No |
| 14INR0039 | Goldsmith Peaking Facility | Ector | 6/2015 | GAS | 408 | New | No |
| 11INR0057 | Cameron County Wind | Cameron | 6/2015 | WIND | 165 | Date change | Yes |
| 08INR0018 | Gunsight Mountain | Howard | 8/2015 | WIND | 120 |  | No |
| 10INR0020b | Panda Temple Power | Bell | 8/2015 | GAS | 717 |  | No |
| 14INR0012b | Miami Wind 1 Project | Gray | 8/2015 | WIND | 111 |  | No |
| 11INR0062 | Patriot (Petronilla) Wind | Nueces | 8/2015 | WIND | 178 |  | Yes |
| 13INR0049 | Friendswood Energy Generation | Harris | 9/2015 | GAS | 316 |  | No |
| 11INR0054 | Midway Farms Wind | San Patricio | 10/2015 | WIND | 161 |  | Yes |
| 14INR0025b | South Plains II | Floyd | 12/2015 | WIND | 300 | New | No |
| 13INR0031 | Mustang Solar Project | Travis | 12/2015 | SOLAR | 30 |  | No |
| 13INR0010b | Mariah Wind | Parmer | 12/2015 | WIND | 200 |  | No |
| 13INR0020b | CPV Rattlesnake Den Ph 2 | Glasscock | 5/2016 | WIND | 150 | Date change | No |
| 13INR0028 | Antelope Station | Hale | 6/2016 | GAS | 359 |  | No |
| 06INR0006 | Cobisa-Greenville | Hunt | 12/2016 | GAS | 1,792 |  | No |
| 10INR0022 | Pondera King Power Project | Harris | 12/2016 | GAS | 1,629 |  | No |
| 12INR0029 | Comanche Run Wind | Swisher | 12/2016 | WIND | 500 |  | No |
| 13INR0010c | Mariah Wind | Parmer | 12/2016 | WIND | 168 | MW Change | No |
| 12INR0018 | Pampa Wind Project | Gray | 3/2017 | WIND | 500 |  | No |
| 13INR0023 | Texas Clean Energy Project | Ector | 6/2018 | Coal | 240 | Date change | No |

## Projects Undergoing Full Interconnection Studies with Confidentiality Waived

| INR | Site Name | County | COD | Fuel | MW for Grid | Change from Last Report |
| --- | --- | --- | --- | --- | --- | --- |

## Generation Projects Undergoing Full Interconnection Studies

| Interconnection Database Reference Number | County | Fuel | Capacity to Grid (MW) | Commercial Operation Date (as specified by the resource developer) |
| --- | --- | --- | --- | --- |
| 14INR0069 | Milam | COAL | 30 | 3/31/2014 |
| 14INR0048_1 | Wilbarger | WIND | 114 | 6/1/2014 |
| 13INR0026 | Oldham | WIND | 201 | 6/1/2014 |
| 14INR0014 | Val Verde | SOLAR | 100 | 7/1/2014 |
| 11INR0093 | San Patricio | WIND | 41 | 7/1/2014 |
| 14INR0059 | Kaufman | GAS | 52 | 8/1/2014 |
| 13INR0055 | Zapata | WIND | 250 | 9/1/2014 |
| 13INR0038 | Swisher | WIND | 300 | 9/15/2014 |
| 14INR0062 | Hall/Motley | WIND | 200 | 9/30/2014 |
| 14INR0047 | Floyd and Crosby | WIND | 301 | 10/1/2014 |
| 14INR0013 | Cameron | WIND | 103 | 10/15/2014 |
| 14INR0048_2 | Wilbarger | WIND | 250 | 10/15/2014 |
| 13INR0036 | Hidalgo | WIND | 200 | 10/31/2014 |
| 13INR0056 | Scurry | WIND | 366 | 11/21/2014 |
| 14INR0066 | Lamar | GAS | 130 | 11/30/2014 |
| 14INR0043 | Sterling | SOLAR | 40 | 12/1/2014 |
| 11INR0082a | Val Verde | WIND | 50 | 12/1/2014 |
| 14INR0028 | Live Oak | WIND | 300 | 12/1/2014 |
| 13INR0054 | Bee | GAS | 25 | 12/1/2014 |
| 10INR0085 | Ector | SOLAR | 57 | 12/1/2014 |
| 14INR0033 | Armstrong | WIND | 500 | 12/1/2014 |
| 11INR0082b | Val Verde | WIND | 150 | 12/1/2014 |
| 14INR0009 | Kent | WIND | 248 | 12/1/2014 |
| 14INR0060 | Haskell | WIND | 400 | 12/19/2014 |
| 15INR0073 | Armstrong/Carson | WIND | 170 | 12/30/2014 |
| 15INR0074 | Deaf Smith/Randall/Castro | WIND | 156 | 12/30/2014 |
| 13INR0045 | Castro | WIND | 288 | 12/30/2014 |
| 12INR0055 | Baylor | WIND | 40 | 12/31/2014 |
| 14INR0049_1 | Jack | WIND | 102 | 12/31/2014 |
| 14INR0045a | Webb | WIND | 502 | 12/31/2014 |
| 13INR0010d | Parmer | WIND | 200 | 12/31/2014 |
| 14INR0057b | Erath | WIND | 48 | 12/31/2014 |
| 12INR0045 | Kleberg | WIND | 135 | 12/31/2014 |
| 14INR0057a | Erath | WIND | 48 | 12/31/2014 |
| 14INR0056 | Mills | WIND | 101 | 12/31/2014 |
| 14INR0020 | Floyd & Motley | WIND | 150 | 3/1/2015 |
| 15INR0070 | Pecos | SOLAR | 110 | 3/1/2015 |

| Interconnection Database Reference Number | County | Fuel | Capacity to Grid (MW) | Commercial Operation Date (as specified by the resource developer) |
| --- | --- | --- | --- | --- |
| 14INR0050 | Uvalde | SOLAR | 40 | 3/1/2015 |
| 15INR0036 | Uvalde | SOLAR | 105 | 3/1/2015 |
| 15INR0069 | Pecos | SOLAR | 110 | 3/1/2015 |
| 10INR0009 | Castro | WIND | 300 | 3/31/2015 |
| 15INR0054 | REEVES | GAS | 123 | 5/1/2015 |
| 15INR0053 | WINKLER | GAS | 123 | 5/1/2015 |
| 15INR0055 | Austin | GAS | 142 | 5/1/2015 |
| 15INR0021 | Starr | WIND | 200 | 5/15/2015 |
| 15INR0028 | Freestone | GAS | 160 | 6/1/2015 |
| 15INR0042 | Hood | GAS | 460 | 6/1/2015 |
| 14INR0041a | Willacy | WIND | 115 | 6/1/2015 |
| 15INR0027 | Hidalgo | GAS | 79 | 6/1/2015 |
| 14INR0027 | Guadalupe | GAS | 471 | 6/1/2015 |
| 14INR0040 | Hidalgo | GAS | 225 | 6/7/2015 |
| 15INR0023 | Wharton | GAS | 700 | 6/15/2015 |
| 14INR0026 | Presidio | SOLAR | 30 | 9/1/2015 |
| 13INR0025 | Randall | WIND | 150 | 9/1/2015 |
| 15INR0068 | Sterling | SOLAR | 20 | 10/1/2015 |
| 11INR0065 | Nueces | WIND | 350 | 10/31/2015 |
| 14INR0030a_1 | Carson | WIND | 322 | 11/1/2015 |
| 12INR0060 | Schleicher | WIND | 58 | 12/1/2015 |
| 15INR0034 | San Patricio | WIND | 201 | 12/1/2015 |
| 14INR0044 | Reeves | SOLAR | 100 | 12/1/2015 |
| 15INR0035 | Kenedy | WIND | 200 | 12/1/2015 |
| 14INR0041b | Willacy | WIND | 115 | 12/1/2015 |
| 08INR0019a | Gray | WIND | 250 | 12/1/2015 |
| 13INR0010e | Parmer | WIND | 200 | 12/31/2015 |
| 14INR0045b | Webb | WIND | 251 | 12/31/2015 |
| 15INR0037 | Starr | WIND | 200 | 12/31/2015 |
| 13INR0032 | Andrews | SOLAR | 30 | 12/31/2015 |
| 15INR0059 | Pecos / Crane | SOLAR | 102 | 12/31/2015 |
| 15INR0060 | Pecos / Crane | SOLAR | 25 | 12/31/2015 |
| 15INR0044 | Webb and Duval | SOLAR | 200 | 12/31/2015 |
| 14INR0072 | Briscoe | WIND | 300 | 12/31/2015 |
| 14INR0018 | Nolan | SOLAR | 20 | 12/31/2015 |
| 12INR0002a | Briscoe | WIND | 200 | 12/31/2015 |
| 15INR0049 | Zapata / Webb | WIND | 250 | 12/31/2015 |

| Interconnection Database Reference Number | County | Fuel | Capacity to Grid (MW) | Commercial Operation Date (as specified by the resource developer) |
| --- | --- | --- | --- | --- |
| 16INR0010 | Mitchell | GAS | 799 | 2/1/2016 |
| 16INR0009 | Calhoun | GAS | 510 | 4/14/2016 |
| 16INR0008 | Grimes | GAS | 687 | 5/1/2016 |
| 16INR0004 | Cameron | GAS | 730 | 6/1/2016 |
| 17INR0004 | Hale | GAS | 202 | 6/1/2016 |
| 16INR0005 | Cameron | GAS | 871 | 6/1/2016 |
| 16INR0007 | Hidalgo | GAS | 95 | 6/1/2016 |
| 16INR0006 | Angelina | GAS | 785 | 6/1/2016 |
| 08INR0019b | Gray | WIND | 250 | 7/1/2016 |
| 16INR0013 | Nacogdoches | GAS | 215 | 7/1/2016 |
| 15INR0033 | Hale | GAS | 197 | 7/1/2016 |
| 15INR0032 | Hale | GAS | 197 | 7/1/2016 |
| 14INR0011 | Swisher | Storage | 270 | 7/1/2016 |
| 16INR0024 | Hidalgo | WIND | 200 | 10/1/2016 |
| 08INR0019c | Gray | WIND | 250 | 12/1/2016 |
| 13INR0006 | Gray | WIND | 750 | 12/1/2016 |
| 16INR0017 | Culberson | SOLAR | 70 | 12/1/2016 |
| 16INR0018 | Upton | SOLAR | 40 | 12/1/2016 |
| 16INR0019 | Coke/Sterling | SOLAR | 100 | 12/1/2016 |
| 16INR0027 | Grayson & Fannin | WIND | 100 | 12/31/2016 |
| 16INR0026 | Erath, Somervell & Bosque | WIND | 100 | 12/31/2016 |
| 16INR0029 | HILL & LIMESTONE | WIND | 100 | 12/31/2016 |
| 16INR0032 | JIM HOGG | WIND | 201 | 12/31/2016 |
| 16INR0028 | Jack | WIND | 100 | 12/31/2016 |
| 13INR0010f | Parmer | WIND | 200 | 12/31/2016 |
| 16INR0030 | YOUNG & JACK | WIND | 201 | 12/31/2016 |
| 12INR0002b | Briscoe | WIND | 200 | 12/31/2016 |
| 16INR0025 | Sterling | SOLAR | 30 | 12/31/2016 |
| 16INR0011a | Cameron | WIND | 18 | 12/31/2016 |
| 16INR0031 | ZAPATA & STARR | WIND | 100 | 12/31/2016 |
| 15INR0013 | Anderson | Storage | 324 | 5/1/2017 |
| 17INR0002 | Henderson | GAS | 489 | 6/1/2017 |
| 17INR0003 | Jackson | GAS | 965 | 6/1/2017 |
| 17INR0005 | Starr | WIND | 200 | 6/30/2017 |
| 17INR0007 | Wharton | GAS | 1,141 | 7/31/2017 |
| 16INR0011b | Cameron | WIND | 132 | 12/30/2017 |
| 11INR0040 | Freestone | GAS | 640 | 3/1/2018 |
| 15INR0014 | Matagorda | Storage | 280 | 5/1/2018 |

## Wind Generation Capacity Installed by Year

# Regional Planning Group Project Reviews

- CenterPoint Energy submitted the Houston Region Import Capacity project. This is a Tier 1 project that is estimated to cost between $297 to $532 million. This project is currently under ERCOT independent review.

- Garland Power & Light (GP&L) and Cross Texas Transmission (CTT) have jointly submitted a Houston Import project. This is a Tier 1 project that is estimated to cost between $195 to $317 million. This project is currently under ERCOT independent review.

- Lone Star Transmission has submitted a Houston Import project. This is a Tier 1 project that is estimated to cost between $417 to $675 million. This project is currently under ERCOT independent review.

- Oncor has submitted the West Texas Area project. This is a Tier 2 project that is estimated to cost $45 million. This project is currently under ERCOT independent review.

- CenterPoint has submitted the Katy Area project. This is a Tier 2 project that is estimated to cost $20.4 million. This project is currently under ERCOT independent review.

- LCRA TSC has submitted the Leander – Round Rock 138 kV project. This is a Tier 1 project that is estimated to cost $50.9 million. This project has received several RPG comments and it is under study mode.

- Sharyland has submitted the Brady Area project. This is a Tier 2 project that is estimated to cost $18 million. This project has received several RPG comments and it is under study mode.

- Sharyland has submitted the West Texas projects for Stanton Area. This is a Tier 3 project that is estimated to cost $40.4 million. This project has received several RPG comments and it is under study mode.

- AEPSC has submitted the Brady Area Improvements project. This is a Tier 2 project that is estimated to cost $26.5 million. This project has been submitted for RPG comments.

# Asynchronous Tie Interconnection

| Project | Notification to ERCOT | Reliability Study | Interconnection Agreement | In-service Year |
| --- | --- | --- | --- | --- |
| Railroad DC tie expansion (150 MW - CFE) |  |  |  | 2014 |
| Southern Cross HVDC (3000 MW - SERC) |  |  |  |  |
| Tres Amigas (1500 MW - SPP) |  |  |  |  |

Color Legend

|  | In progress |
| --- | --- |
|  | Complete |

# Planning Model Activities

- The short term calendar of major planning model events follows:

  - Mar 1, 2014	Post 14DSA and 14DSB updated cases

  - Mar 15, 2014	Post MODTPIT

  - Apr 1, 2014	Start 15DSA case build process

# Other Notable Activities

- The System Protection Working Group 2014 Current Year (CY) base creation process has started.  The process will include 4 passes and conclude March 21, 2014.

- ERCOT has entered into an agreement with Powertech Labs to perform a small signal stability study.

- ERCOT held two stakeholder workshops on scenario development for the 2014 Long-Term System Assessment in January.  The third and final scenario development workshop will be held on February 14 at the ERCOT Austin office.